## CP Model
Sample Critical Path |  |  |  | Questions? Contact Eric Christoph eric@transformativems.com or https://www.linkedin.com/in/ericfchristoph/
Task Min |  | 2 |  |  |  | Target : | 80%
Task Max |  | 15
Probability Distributions
| Risk Shape |  |  |  |  | Duration |  |  |  | PERT |  | Triangle |  | Beta (50%) |  | Beta (80%)
Task ID | Uncertainty | Band | Alpha | Beta | Blank | Optimistic | Likely | P% | Pessimistic | Duration | P% | Duration | P% | Duration | P% | Duration | P%
1 | 4 | Low+ | 2.8 | 1.3434 |  | 3 | 3.6 | 0.3557% | 8.4 | 4.3 | 2.984% | 5 | 9.549% | 6.8128 | 50% | 7.7024 | 80%
2 | 9 | Very High | 5 | 1.968 |  | 10 | 18 | 0.1536% | 50 | 22 | 1.053% | 26 | 3.96% | 39.5699 | 50% | 44.5263 | 80%
3 | 4 | Low+ | 2.8 | 1.3434 |  | 12 | 14.4 | 0.3557% | 33.6 | 17.2 | 2.984% | 20 | 9.549% | 27.2512 | 50% | 30.8096 | 80%
4 | 2 | Very Low | 2.2 | 1.1605 |  | 4 | 4.4 | 0.5309% | 8.8 | 5.0667 | 4.514% | 5.7333 | 12.88% | 7.3027 | 50% | 8.1947 | 80%
5 | 6 | Medium+ | 3.6 | 1.6377 |  | 11 | 15.4 | 0.3136% | 39.6 | 18.7 | 2.194% | 22 | 7.327% | 31.3787 | 50% | 35.5946 | 80%
6 | 10 | Extreme | 6 | 1.968 |  | 9 | 18 | 0.03548% | 54 | 22.5 | 0.3636% | 27 | 1.814% | 43.8687 | 50% | 48.7409 | 80%
7 | 4 | Low+ | 2.8 | 1.3434 |  | 14 | 16.8 | 0.3557% | 39.2 | 20.0667 | 2.984% | 23.3333 | 9.549% | 31.793 | 50% | 35.9446 | 80%
8 | 7 | High | 4 | 1.7284 |  | 3 | 4.5 | 0.2408% | 12 | 5.5 | 1.717% | 6.5 | 6.034% | 9.5029 | 50% | 10.756 | 80%
9 | 1 | Minimal | 2 | 0.952 |  | 10 | 10.5 | 0.2327% | 20 | 12 | 3.742% | 13.5 | 11.53% | 17.2116 | 50% | 19.0394 | 80%
10 | 4 | Low+ | 2.8 | 1.3434 |  | 6 | 7.2 | 0.3557% | 16.8 | 8.6 | 2.984% | 10 | 9.549% | 13.6256 | 50% | 15.4048 | 80%
11 | 3 | Low | 2.5 | 1.2693 |  | 9 | 10.35 | 0.4676% | 22.5 | 12.15 | 3.776% | 13.95 | 11.31% | 18.3745 | 50% | 20.739 | 80%
12 | 5 | Medium | 3.2 | 1.5157 |  | 9 | 11.7 | 0.3691% | 28.8 | 14.1 | 2.67% | 16.5 | 8.605% | 22.9681 | 50% | 26.0604 | 80%
13 | 7 | High | 4 | 1.7284 |  | 14 | 21 | 0.2408% | 56 | 25.6667 | 1.717% | 30.3333 | 6.034% | 44.347 | 50% | 50.1949 | 80%
14 | 1 | Minimal | 2 | 0.952 |  | 13 | 13.65 | 0.2327% | 26 | 15.6 | 3.742% | 17.55 | 11.53% | 22.3751 | 50% | 24.7512 | 80%
15 | 1 | Minimal | 2 | 0.952 |  | 2 | 2.1 | 0.2327% | 4 | 2.4 | 3.742% | 2.7 | 11.53% | 3.4423 | 50% | 3.8079 | 80%
16 | 4 | Low+ | 2.8 | 1.3434 |  | 10 | 12 | 0.3557% | 28 | 14.3333 | 2.984% | 16.6667 | 9.549% | 22.7093 | 50% | 25.6747 | 80%
17 | 4 | Low+ | 2.8 | 1.3434 |  | 14 | 16.8 | 0.3557% | 39.2 | 20.0667 | 2.984% | 23.3333 | 9.549% | 31.793 | 50% | 35.9446 | 80%
18 | 1 | Minimal | 2 | 0.952 |  | 3 | 3.15 | 0.2327% | 6 | 3.6 | 3.742% | 4.05 | 11.53% | 5.1635 | 50% | 5.7118 | 80%
19 | 2 | Very Low | 2.2 | 1.1605 |  | 15 | 16.5 | 0.5309% | 33 | 19 | 4.514% | 21.5 | 12.88% | 27.385 | 50% | 30.7301 | 80%
20 | 1 | Minimal | 2 | 0.952 |  | 7 | 7.35 | 0.2327% | 14 | 8.4 | 3.742% | 9.45 | 11.53% | 12.0482 | 50% | 13.3276 | 80%
21 | 8 | High+ | 4.5 | 1.8647 |  | 6 | 9.9 | 0.2022% | 27 | 12.1 | 1.38% | 14.3 | 4.976% | 21.3239 | 50% | 24.0805 | 80%
22 | 1 | Minimal | 2 | 0.952 |  | 11 | 11.55 | 0.2327% | 22 | 13.2 | 3.742% | 14.85 | 11.53% | 18.9328 | 50% | 20.9433 | 80%
23 | 3 | Low | 2.5 | 1.2693 |  | 5 | 5.75 | 0.4676% | 12.5 | 6.75 | 3.776% | 7.75 | 11.31% | 10.2081 | 50% | 11.5216 | 80%
24 | 7 | High | 4 | 1.7284 |  | 15 | 22.5 | 0.2408% | 60 | 27.5 | 1.717% | 32.5 | 6.034% | 47.5147 | 50% | 53.7802 | 80% | Simulator Minimum Duration: | 473.2242
25 | 4 | Low+ | 2.8 | 1.3434 |  | 8 | 9.6 | 0.3557% | 22.4 | 11.4667 | 2.984% | 13.3333 | 9.549% | 18.1674 | 50% | 20.5398 | 80% | Simulator Maximum Duration: | 599.3657
[18 empty] | Simulator at target confidence: | 559.9664
[6 empty] | 223 | 286.7 | 0% | 683.8 | 342.2667 | 0% | 397.8333 | 0% | 555.0701 | 70.9% | 624.5208 | 0% | Simulator at 50% confidence: | 542.9344
[6 empty] | Schedule Buffer (Target): | 273.2664 |  |  | 217.6997 |  | 162.1331 |  | 4.8963 |  | -64.5545 |  |  | 17.032
[6 empty] | SB as a % of target duration: | 48.8% |  |  | 38.88% |  | 28.95% |  | 0.8744% |  | -11.53% |  |  | 3.042%

## Risk Bands
Rank | Uncertainty | Description | Optimistic Factor | Likely Factor | Pessimistic Factor | Alpha | Beta | PERT (10d) | PERT (P%) | Triangular (10d) | Triangular (P%) | Beta 50% (10d) | Beta 80% (10d)
1 | Minimal | Fully defined, routine task | 1 | 1.05 | 2 | 0.952 | 3.808 | 12 | 59.26% | 13.5 | 81.81% | 11.5706 | 13.3388
2 | Very Low | Routine with minor variability | 1 | 1.1 | 2.2 | 1.1605 | 4.0617 | 12.6667 | 57.9% | 14.3333 | 80.18% | 12.227 | 14.3159
3 | Low | Known task, slight challenges | 1 | 1.15 | 2.5 | 1.2693 | 4.1707 | 13.5 | 57.3% | 15.5 | 79.31% | 12.9918 | 15.5822
4 | Low+ | Routine, some dependencies | 1 | 1.2 | 2.8 | 1.3434 | 4.2369 | 14.3333 | 56.94% | 16.6667 | 78.72% | 13.7542 | 16.8465
5 | Medium | Moderate complexity, known risks | 1 | 1.3 | 3.2 | 1.5157 | 4.3686 | 15.6667 | 56.18% | 18.3333 | 77.32% | 15.037 | 18.7728
6 | Medium+ | Development with some uncertainty | 1 | 1.4 | 3.6 | 1.6377 | 4.4452 | 17 | 55.7% | 20 | 76.31% | 16.3137 | 20.6946
7 | High | Significant technical challenges | 1 | 1.5 | 4 | 1.7284 | 4.4938 | 18.3333 | 55.38% | 21.6667 | 75.54% | 17.5872 | 22.6142
8 | High+ | Novel tasks, high variability | 1 | 1.65 | 4.5 | 1.8647 | 4.5549 | 20.1667 | 54.93% | 23.8333 | 74.37% | 19.3703 | 25.1885
9 | Very High | Unfamiliar domain, major risks | 1 | 1.8 | 5 | 1.968 | 4.592 | 22 | 54.61% | 26 | 73.46% | 21.1494 | 27.7604
10 | Extreme | Experimental, no prior experience | 1 | 2 | 6 | 1.968 | 4.592 | 25 | 54.61% | 30 | 73.46% | 23.9367 | 32.2005

## Simulation
Sample critical path
Min: | 473.2242 | Max: | 599.3657 |  | Range: | 126.1415
Task ID
Run | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Total | Duration | Frequency
1 | 7.1766 | 41.5886 | 22.9204 | 8.7 | 32.5256 | 35.2696 | 30.6565 | 10.3991 | 19.0265 | 13.3314 | 11.4965 | 18.083 | 39.6943 | 15.7627 | 2.514 | 22.5855 | 22.9716 | 5.9604 | 25.8774 | 13.2014 | 23.4021 | 19.3347 | 10.3604 | 40.9754 | 21.7884 | 515.6018 | 223 | 0 | 10% | 513.6726
2 | 7.7925 | 38.2913 | 20.1945 | 8.4058 | 22.6219 | 26.2594 | 38.2826 | 11.3333 | 18.3002 | 11.8188 | 18.9129 | 21.5887 | 51.7982 | 24.0822 | 3.1462 | 13.8456 | 37.199 | 5.8673 | 25.8393 | 13.605 | 19.7969 | 21.1072 | 9.1895 | 50.0382 | 13.1822 | 532.4987 | 246.04 | 0 | 20% | 525.0663
3 | 8.3681 | 29.7782 | 29.9105 | 7.0078 | 32.9512 | 44.5959 | 32.3942 | 9.2185 | 18.4755 | 15.9479 | 16.9189 | 18.4128 | 52.8611 | 18.1955 | 3.3727 | 26.8294 | 26.7984 | 5.361 | 21.2366 | 8.5693 | 15.4111 | 21.2612 | 8.1217 | 57.0324 | 21.1268 | 550.1568 | 269.08 | 0 | 30% | 532.2329
4 | 7.6192 | 39.698 | 28.6219 | 7.0354 | 29.265 | 37.5367 | 36.7111 | 10.9098 | 19.5744 | 13.7015 | 21.2458 | 27.2554 | 30.2041 | 21.7807 | 2.2692 | 19.4751 | 34.9423 | 5.2852 | 25.6565 | 8.9117 | 17.0039 | 15.9161 | 8.6192 | 56.3405 | 13.7103 | 539.289 | 292.12 | 0 | 40% | 537.7616
5 | 6.9318 | 46.6917 | 31.7269 | 7.2836 | 35.5553 | 47.7898 | 32.4032 | 7.9982 | 19.1783 | 8.3183 | 17.8381 | 27.3933 | 50.5404 | 24.2234 | 3.5036 | 25.0488 | 34.6424 | 4.9747 | 26.9715 | 13.1064 | 18.2434 | 21.2918 | 10.2699 | 55.5023 | 16.4215 | 593.8484 | 315.16 | 0 | 50% | 542.9344
6 | 7.8376 | 42.6294 | 24.312 | 6.31 | 36.7158 | 34.4829 | 28.8181 | 10.9771 | 17.7809 | 14.5135 | 20.0553 | 25.2908 | 32.6197 | 19.5764 | 3.6795 | 24.7511 | 28.6551 | 5.9889 | 28.976 | 12.2896 | 19.0725 | 18.9284 | 11.689 | 49.0224 | 16.3083 | 541.2803 | 338.2 | 0 | 60% | 548.7708
7 | 6.8821 | 45.4378 | 29.7898 | 8.3653 | 23.7405 | 49.7909 | 33.5078 | 10.8105 | 18.5126 | 11.9539 | 17.3577 | 27.5023 | 53.4649 | 21.8825 | 3.9223 | 19.6423 | 29.1192 | 4.7635 | 25.7378 | 9.0427 | 22.5842 | 20.8627 | 10.2316 | 53.301 | 17.6431 | 575.849 | 361.24 | 0 | 70% | 554.109
8 | 7.2251 | 44.3066 | 33.0399 | 6.3783 | 37.4182 | 48.6433 | 34.1517 | 8.8682 | 13.5583 | 15.5948 | 19.0789 | 18.5109 | 32.105 | 18.3373 | 3.8143 | 17.6281 | 36.5464 | 5.1905 | 30.5307 | 10.3133 | 24.6258 | 19.879 | 6.8929 | 49.5235 | 18.71 | 560.8711 | 384.28 | 0 | 80% | 559.9664
9 | 7.1401 | 30.2732 | 27.2182 | 4.9631 | 35.4162 | 39.9181 | 36.9339 | 6.8764 | 15.0801 | 16.1538 | 19.7587 | 27.1596 | 47.3869 | 24.0578 | 3.2552 | 23.5457 | 38.3039 | 5.8743 | 26.1592 | 13.1303 | 14.7549 | 12.7925 | 6.3628 | 43.8147 | 10.5395 | 536.8691 | 407.32 | 0 | 90% | 569.8709
10 | 7.7248 | 39.9477 | 29.1722 | 7.9478 | 32.6753 | 43.8979 | 23.3238 | 10.5353 | 17.1931 | 13.7315 | 9.8273 | 19.4565 | 46.0598 | 24.4238 | 3.0496 | 25.2072 | 35.439 | 5.3462 | 24.193 | 7.9004 | 20.7679 | 14.8475 | 9.9702 | 54.4183 | 19.6991 | 546.7551 | 430.36 | 0 | 100% | 599.3657
11 | 6.091 | 42.2289 | 27.4379 | 6.1055 | 25.5961 | 47.0015 | 32.2468 | 4.198 | 14.9732 | 13.1875 | 14.7058 | 16.4984 | 53.0218 | 20.4118 | 3.3834 | 24.1627 | 30.4162 | 5.3524 | 29.2894 | 12.9192 | 22.1871 | 16.144 | 9.6524 | 50.9935 | 20.8871 | 549.0915 | 453.4 | 0
12 | 7.2456 | 36.0386 | 31.1725 | 7.9209 | 35.2316 | 40.9276 | 28.588 | 10.0292 | 17.1041 | 9.6127 | 17.6984 | 22.9372 | 41.3289 | 15.7711 | 3.5245 | 26.4091 | 39.0262 | 5.4501 | 29.5479 | 11.9908 | 20.7682 | 15.5871 | 11.037 | 39.4894 | 22.1035 | 546.5402 | 476.44 | 2
13 | 6.303 | 30.767 | 22.0588 | 5.1622 | 37.0443 | 42.7151 | 35.1855 | 8.4216 | 19.4047 | 12.968 | 15.6401 | 27.2769 | 55.6182 | 22.2454 | 3.9347 | 19.5955 | 34.8402 | 4.2415 | 17.2275 | 13.9401 | 23.2859 | 20.3842 | 10.9811 | 49.4075 | 14.5326 | 553.1817 | 499.48 | 21
14 | 3.4521 | 32.1158 | 15.8585 | 8.4751 | 25.4282 | 41.0322 | 29.6451 | 10.1073 | 16.5878 | 15.1189 | 13.2059 | 25.2704 | 45.4371 | 18.1073 | 3.9166 | 22.5655 | 29.3528 | 5.0534 | 29.8819 | 13.5057 | 26.1917 | 19.4979 | 11.2675 | 50.2301 | 17.4509 | 528.7556 | 522.52 | 153
15 | 7.1441 | 40.277 | 32.1936 | 5.7123 | 34.0023 | 40.9885 | 29.9167 | 10.4459 | 17.3646 | 13.7895 | 19.4603 | 15.2503 | 49.2837 | 23.3633 | 3.2081 | 14.0576 | 22.1182 | 4.4635 | 32.1177 | 13.7099 | 21.8104 | 18.5181 | 10.484 | 49.3165 | 20.8549 | 549.8513 | 545.56 | 362
16 | 7.1924 | 48.1535 | 32.0771 | 6.9782 | 32.5589 | 48.9499 | 34.8237 | 9.8899 | 14.801 | 13.4878 | 18.8919 | 17.3614 | 49.5649 | 14.7672 | 2.9784 | 19.276 | 35.8899 | 5.7434 | 30.5978 | 12.3581 | 18.6645 | 19.9454 | 9.7824 | 47.1072 | 19.3148 | 571.1557 | 568.6 | 356
17 | 5.5683 | 37.9309 | 33.1825 | 8.1103 | 32.3495 | 48.7213 | 31.7348 | 11.0571 | 14.3065 | 12.8359 | 20.3696 | 24.5582 | 36.9719 | 19.3364 | 3.9138 | 16.445 | 19.7891 | 5.2495 | 19.2876 | 12.5397 | 21.7089 | 20.6605 | 5.7514 | 43.6672 | 14.9349 | 520.9809 | 591.64 | 100
18 | 4.0495 | 35.2024 | 32.3314 | 8.3674 | 35.7186 | 49.4099 | 26.1165 | 10.9944 | 13.0886 | 15.6365 | 16.9478 | 24.9553 | 36.1493 | 22.2673 | 3.1611 | 23.0975 | 20.3683 | 3.9731 | 30.3246 | 9.7584 | 24.2273 | 16.3967 | 10.4064 | 40.3367 | 21.5031 | 534.788 | 614.68 | 6
19 | 4.4283 | 42.6739 | 21.7767 | 8.3998 | 37.2069 | 45.0432 | 25.3103 | 7.896 | 14.2683 | 9.3429 | 15.4751 | 27.3551 | 45.9827 | 25.276 | 2.6876 | 23.573 | 31.207 | 5.7149 | 29.0419 | 13.0044 | 16.2949 | 17.4013 | 8.4168 | 42.1411 | 15.9752 | 535.8932 | 637.72 | 0
20 | 5.2785 | 37.8807 | 30.2317 | 7.6773 | 36.344 | 42.2525 | 30.0617 | 11.3704 | 19.8076 | 10.1872 | 16.625 | 25.2075 | 41.8669 | 25.954 | 3.9802 | 22.378 | 32.5406 | 5.3719 | 25.0863 | 12.2575 | 24.0768 | 14.1779 | 11.29 | 48.4665 | 19.9486 | 560.319 | 683.8 | 0
21 | 8.0044 | 37.6581 | 23.5752 | 7.4745 | 35.956 | 32.945 | 28.6562 | 11.0879 | 13.9185 | 14.2131 | 18.8572 | 16.8396 | 50.1818 | 23.8058 | 3.5218 | 21.5103 | 34.2913 | 5.9025 | 20.8709 | 7.9093 | 19.851 | 21.3567 | 6.5041 | 35.2726 | 13.0872 | 513.251
22 | 8.3265 | 46.1254 | 31.722 | 6.2807 | 35.7947 | 22.5527 | 28.9176 | 9.1649 | 19.1347 | 7.5339 | 12.4695 | 21.9916 | 44.9759 | 25.4911 | 3.7459 | 14.5396 | 21.5848 | 5.0178 | 20.2413 | 13.302 | 22.4657 | 21.8731 | 10.3539 | 47.045 | 19.103 | 519.7532
23 | 6.1007 | 37.7286 | 26.7177 | 5.7606 | 36.4576 | 47.3291 | 28.6079 | 11.3157 | 19.6502 | 14.452 | 18.7701 | 20.7339 | 52.1878 | 22.6023 | 3.8943 | 24.0646 | 35.5671 | 5.3305 | 20.5698 | 12.5034 | 20.122 | 17.5637 | 12.0208 | 41.3047 | 17.7987 | 559.1539
24 | 8.0463 | 43.354 | 28.9832 | 6.5951 | 36.7336 | 50.4989 | 33.7837 | 10.9651 | 16.4677 | 8.1498 | 21.3665 | 21.546 | 36.9134 | 21.8507 | 2.9695 | 26.1506 | 26.4581 | 5.2872 | 28.5777 | 12.7396 | 20.449 | 20.8549 | 11.2833 | 41.0176 | 19.5828 | 560.6243
25 | 7.8253 | 39.5604 | 20.6454 | 5.4556 | 26.1386 | 49.095 | 21.7688 | 7.9886 | 12.7113 | 11.6873 | 9.6466 | 23.6929 | 54.9227 | 25.5324 | 3.2423 | 25.0338 | 33.8284 | 5.9992 | 28.2475 | 12.7993 | 23.4075 | 16.1157 | 10.2821 | 33.1445 | 19.9535 | 528.7247
26 | 8.1243 | 36.3735 | 27.8425 | 5.0556 | 21.285 | 43.7856 | 38.2376 | 9.8085 | 15.7633 | 14.0935 | 19.7701 | 24.6732 | 52.6857 | 24.6719 | 3.4413 | 26.3419 | 32.7391 | 5.9609 | 22.998 | 11.4428 | 24.9346 | 21.9243 | 10.1565 | 48.0345 | 20.3643 | 570.5084
27 | 7.5889 | 44.8192 | 30.834 | 7.6504 | 32.3798 | 46.4259 | 18.9126 | 8.4224 | 18.531 | 13.6746 | 11.7603 | 26.2381 | 52.9201 | 18.3396 | 3.0743 | 14.8016 | 23.7657 | 3.7307 | 20.4692 | 12.3095 | 19.2303 | 14.0217 | 6.6967 | 58.7549 | 15.2952 | 530.6468
28 | 5.9551 | 47.9774 | 25.6972 | 6.85 | 39.5641 | 45.7386 | 36.9465 | 10.3408 | 14.0419 | 12.2962 | 15.3276 | 23.6991 | 42.8202 | 23.0853 | 3.8242 | 21.7095 | 37.6836 | 5.8771 | 22.0267 | 10.0886 | 16.8793 | 16.4854 | 11.8549 | 47.276 | 15.9172 | 559.9623
29 | 6.4742 | 43.5892 | 25.7596 | 5.6473 | 32.8453 | 35.0234 | 29.378 | 10.3936 | 19.8919 | 12.623 | 19.5773 | 26.889 | 41.2858 | 15.7295 | 2.4179 | 26.0232 | 32.3229 | 5.4355 | 27.8578 | 11.7741 | 19.0368 | 15.1148 | 8.6728 | 46.4462 | 18.8532 | 539.0619
30 | 6.8885 | 36.924 | 26.6152 | 8.5276 | 34.7117 | 49.2163 | 34.3137 | 6.9348 | 17.4378 | 12.3956 | 18.6406 | 26.3305 | 54.6855 | 23.6719 | 3.2472 | 22.9179 | 29.4328 | 5.0323 | 27.829 | 12.9687 | 18.3996 | 17.176 | 9.9052 | 54.1688 | 15.9363 | 574.3072
31 | 6.1446 | 44.739 | 32.4935 | 5.7983 | 28.5248 | 39.7295 | 30.7164 | 11.2942 | 17.7393 | 8.9386 | 19.378 | 21.1123 | 35.4524 | 24.0229 | 2.2235 | 24.4687 | 32.4541 | 5.691 | 29.4027 | 9.4783 | 14.4109 | 21.9024 | 11.8413 | 48.7326 | 17.1273 | 543.8165
32 | 5.016 | 35.833 | 27.6809 | 6.9892 | 21.5316 | 40.7624 | 38.0934 | 10.789 | 12.2126 | 14.5878 | 18.9876 | 26.4634 | 32.5074 | 24.7211 | 3.5528 | 21.7922 | 34.7454 | 3.6663 | 32.7297 | 13.4031 | 19.2945 | 19.1738 | 9.3673 | 36.54 | 20.7235 | 531.1641
33 | 3.1958 | 37.6769 | 19.9482 | 8.4343 | 25.8704 | 50.085 | 22.6479 | 10.3641 | 15.4703 | 12.6586 | 16.248 | 25.5538 | 54.7538 | 25.574 | 2.8201 | 25.7497 | 33.105 | 4.0627 | 24.0925 | 13.3331 | 23.6574 | 16.736 | 9.4173 | 51.9393 | 20.0813 | 553.4755
34 | 5.5042 | 46.0828 | 24.7436 | 6.9724 | 33.3293 | 49.933 | 28.102 | 11.2169 | 19.4311 | 16.5101 | 18.2661 | 26.0894 | 50.9142 | 22.9728 | 3.5996 | 22.9478 | 30.4178 | 4.4243 | 26.2762 | 11.5832 | 18.8615 | 13.7236 | 11.027 | 53.2864 | 14.8623 | 571.0777
35 | 5.9155 | 43.5478 | 27.248 | 7.6694 | 27.8379 | 42.3916 | 37.7175 | 7.971 | 16.4441 | 15.8873 | 14.6841 | 25.053 | 43.6356 | 25.1692 | 3.741 | 21.4696 | 32.4172 | 4.2082 | 29.956 | 12.5598 | 18.3986 | 15.4861 | 12.2139 | 45.5833 | 19.0136 | 556.2193
36 | 6.5646 | 45.3359 | 17.4039 | 7.1213 | 37.6408 | 47.6862 | 38.6058 | 11.2092 | 18.5018 | 8.3122 | 20.3772 | 20.5254 | 37.08 | 20.3903 | 3.534 | 15.7771 | 35.8053 | 4.586 | 30.1286 | 9.5862 | 19.5184 | 17.4022 | 11.8349 | 37.0565 | 21.1244 | 543.1081
37 | 5.722 | 30.6341 | 22.3538 | 6.036 | 35.2087 | 51.1191 | 36.7178 | 11.6656 | 17.9277 | 15.223 | 22.0317 | 23.6989 | 52.7403 | 20.0064 | 3.4547 | 22.4524 | 25.2573 | 5.8441 | 24.7024 | 11.738 | 19.2767 | 13.7385 | 11.1997 | 45.7579 | 15.2615 | 549.7682
38 | 7.685 | 41.6956 | 28.9795 | 6.9039 | 23.2426 | 48.003 | 23.6654 | 11.3631 | 18.214 | 16.0676 | 17.9958 | 17.3427 | 43.5593 | 14.2216 | 3.8615 | 18.4952 | 22.4476 | 5.0395 | 32.2554 | 12.5403 | 13.3621 | 13.3258 | 12.0439 | 57.3174 | 21.6052 | 531.2329
39 | 8.0719 | 47.0347 | 24.6216 | 7.1149 | 29.9065 | 40.6287 | 27.9615 | 9.5 | 19.7575 | 14.3892 | 16.1612 | 19.1398 | 55.9146 | 24.3082 | 2.5694 | 26.7295 | 27.7757 | 5.5302 | 32.6197 | 11.1203 | 21.8112 | 16.7738 | 9.5856 | 42.757 | 16.6965 | 558.479
40 | 5.447 | 36.931 | 30.2896 | 7.0138 | 24.6351 | 31.1853 | 22.7396 | 9.8869 | 16.2671 | 13.2791 | 16.789 | 27.6663 | 46.7514 | 20.4767 | 2.7175 | 14.1721 | 24.4036 | 4.2729 | 23.5196 | 11.4614 | 21.3564 | 21.8661 | 10.4428 | 53.9646 | 22.1963 | 519.7311
41 | 7.0779 | 45.6164 | 32.5497 | 8.5801 | 34.2153 | 39.1944 | 27.6482 | 8.5631 | 17.3324 | 13.712 | 20.9949 | 23.0817 | 40.0608 | 19.9414 | 3.9991 | 26.4556 | 28.6962 | 5.6593 | 20.6948 | 12.9927 | 13.7328 | 18.8052 | 7.4454 | 47.4534 | 21.3844 | 545.8871
42 | 4.7818 | 44.1699 | 31.3149 | 8.6372 | 37.4634 | 35.2033 | 26.2292 | 9.2771 | 17.5624 | 14.4684 | 14.8189 | 22.8301 | 52.6551 | 16.1843 | 3.7266 | 19.8012 | 28.0997 | 5.1008 | 26.4378 | 11.9818 | 22.5022 | 19.099 | 10.0173 | 37.7584 | 12.7072 | 532.828
43 | 4.9614 | 42.2503 | 31.5294 | 4.8431 | 31.7548 | 41.2734 | 28.9392 | 8.9525 | 17.2158 | 11.258 | 19.6871 | 23.6837 | 31.0963 | 25.7937 | 2.6265 | 25.6914 | 36.4323 | 5.3764 | 27.1925 | 11.1936 | 20.6175 | 14.783 | 7.9391 | 57.7807 | 16.7021 | 549.5737
44 | 4.101 | 41.4216 | 25.761 | 8.1123 | 25.0584 | 38.2394 | 29.71 | 8.0728 | 18.951 | 10.3536 | 14.9369 | 10.8454 | 28.6257 | 21.9433 | 2.981 | 26.8215 | 26.0888 | 5.5257 | 25.0803 | 13.7784 | 24.4721 | 21.6609 | 9.7324 | 58.5411 | 17.2916 | 518.1064
45 | 7.2855 | 41.9552 | 21.7968 | 8.5012 | 25.5542 | 49.3387 | 31.7526 | 9.7688 | 19.6609 | 13.2878 | 17.5773 | 24.4483 | 49.2726 | 15.9762 | 3.6275 | 27.2508 | 26.7103 | 5.3364 | 24.7479 | 12.8989 | 26.4512 | 13.5133 | 10.089 | 44.0026 | 17.9535 | 548.7576
46 | 7.4471 | 33.7851 | 20.6254 | 8.4651 | 23.3168 | 38.2026 | 34.1924 | 8.283 | 15.7662 | 14.868 | 19.4746 | 25.3941 | 51.2891 | 18.5537 | 3.7803 | 25.1747 | 34.3874 | 4.8668 | 21.3627 | 8.676 | 21.7946 | 21.8094 | 10.6989 | 38.7949 | 17.4032 | 528.412
47 | 7.7967 | 39.1379 | 22.3259 | 6.1386 | 35.6202 | 47.4767 | 32.9939 | 7.8784 | 19.9379 | 13.5973 | 21.9593 | 26.4838 | 52.5378 | 20.5312 | 3.9826 | 21.0499 | 34.7959 | 5.5929 | 21.835 | 13.5293 | 20.9119 | 19.8364 | 9.4917 | 42.1092 | 16.1008 | 563.651
48 | 8.0852 | 31.1359 | 31.3304 | 7.691 | 34.7587 | 32.4314 | 34.8275 | 11.8695 | 13.6586 | 12.2217 | 18.3369 | 20.0348 | 47.6666 | 24.7202 | 3.9973 | 23.9239 | 35.533 | 4.9247 | 23.7622 | 12.3665 | 19.9121 | 21.2149 | 10.5469 | 42.8787 | 18.0768 | 545.9053
49 | 8.2322 | 43.6928 | 26.3117 | 8.6918 | 13.8327 | 48.5202 | 37.073 | 7.3534 | 17.4474 | 11.5668 | 17.5285 | 21.6135 | 35.577 | 23.7347 | 2.4564 | 22.15 | 38.3221 | 3.7598 | 31.2973 | 7.3884 | 24.7415 | 16.6823 | 11.749 | 49.3285 | 18.4365 | 547.4877
50 | 4.6911 | 36.0702 | 33.5364 | 5.9631 | 36.2926 | 32.5482 | 17.503 | 8.585 | 17.7898 | 14.6168 | 20.9284 | 27.4348 | 22.8552 | 20.5474 | 3.9295 | 22.1183 | 29.7849 | 5.4339 | 23.9741 | 13.7431 | 20.6105 | 15.9182 | 11.3421 | 55.1502 | 21.8207 | 523.1876
51 | 5.1463 | 32.2322 | 30.2215 | 8.1768 | 31.5394 | 49.7336 | 19.4076 | 10.7121 | 17.9851 | 15.0211 | 15.9798 | 24.0582 | 33.1254 | 20.4344 | 3.244 | 20.2081 | 24.4585 | 3.5696 | 31.6382 | 12.7788 | 22.9089 | 17.6087 | 8.1368 | 44.0299 | 17.8715 | 520.227
52 | 6.032 | 37.3834 | 23.215 | 6.9424 | 32.7978 | 51.1352 | 19.819 | 10.136 | 10.6606 | 15.4461 | 16.728 | 26.2597 | 30.876 | 22.743 | 3.9355 | 26.039 | 27.0735 | 5.2273 | 24.1031 | 9.8095 | 26.3866 | 19.322 | 9.9163 | 51.8714 | 18.9042 | 532.7626
53 | 8.3899 | 27.8237 | 31.2573 | 6.7724 | 37.3306 | 41.6669 | 35.2289 | 8.7351 | 17.1206 | 9.9882 | 21.2999 | 12.6782 | 46.051 | 23.793 | 2.5635 | 15.939 | 35.8377 | 5.0573 | 25.493 | 11.4549 | 19.0981 | 14.9225 | 8.2817 | 52.0904 | 17.9925 | 536.8661
54 | 7.9819 | 41.1755 | 32.3748 | 7.1769 | 29.159 | 51.0855 | 35.851 | 7.2822 | 12.5117 | 12.837 | 17.5192 | 16.2855 | 38.3607 | 22.154 | 3.7687 | 26.5721 | 37.3011 | 5.5449 | 28.5532 | 13.8123 | 20.0303 | 18.9032 | 8.5878 | 41.1384 | 19.8456 | 555.8125
55 | 6.26 | 27.0125 | 27.2586 | 8.1534 | 34.4483 | 51.5465 | 37.2739 | 10.9473 | 17.5363 | 12.1217 | 16.8834 | 21.8451 | 53.6769 | 25.0268 | 3.9942 | 15.1683 | 34.368 | 4.1961 | 30.0947 | 12.5628 | 20.4918 | 20.2215 | 7.1997 | 58.5243 | 21.7366 | 578.5486
56 | 7.5906 | 38.3673 | 28.014 | 6.181 | 26.4249 | 41.0028 | 30.5277 | 7.7138 | 15.4487 | 16.5353 | 19.3292 | 26.888 | 45.0539 | 20.9011 | 3.5102 | 20.3867 | 20.6367 | 5.1611 | 22.3935 | 13.8764 | 19.7024 | 13.4576 | 9.3103 | 55.5989 | 20.5052 | 534.5174
57 | 7.2791 | 44.5588 | 19.6514 | 8.617 | 29.4274 | 45.1323 | 19.4391 | 8.8117 | 16.0159 | 12.0536 | 19.3018 | 26.7043 | 32.6356 | 21.7439 | 3.1511 | 23.3118 | 32.917 | 5.8218 | 23.0101 | 13.7916 | 20.1942 | 18.666 | 11.2225 | 55.459 | 20.2265 | 539.1436
58 | 7.095 | 47.4447 | 28.3029 | 7.4813 | 32.5922 | 32.5749 | 28.8536 | 11.0686 | 19.5523 | 12.0526 | 19.5282 | 22.8689 | 48.3881 | 23.654 | 3.8365 | 17.9976 | 27.2128 | 5.5738 | 32.9632 | 13.9872 | 24.0331 | 19.7593 | 6.0201 | 39.5888 | 18.0524 | 550.4821
59 | 6.4335 | 39.9015 | 22.7201 | 5.5499 | 29.9806 | 39.2358 | 21.3471 | 11.0733 | 17.4262 | 11.7884 | 13.913 | 25.1628 | 33.2885 | 16.133 | 3.9346 | 21.959 | 34.0725 | 5.7541 | 29.2489 | 13.1827 | 18.6372 | 15.0884 | 11.1986 | 43.401 | 20.4085 | 510.8391
60 | 7.102 | 39.7525 | 28.0857 | 7.7973 | 38.9631 | 45.846 | 35.6418 | 11.2155 | 18.4787 | 13.7597 | 18.5493 | 17.7171 | 40.1775 | 21.5513 | 2.7233 | 20.6569 | 32.4019 | 5.8386 | 28.2959 | 13.6384 | 22.4468 | 19.2878 | 10.3501 | 38.7847 | 17.5602 | 556.6221
61 | 7.8289 | 40.4069 | 29.5547 | 8.4256 | 35.9741 | 42.6627 | 35.1845 | 8.7407 | 17.7672 | 15.0691 | 21.7201 | 21.5705 | 38.5778 | 22.9715 | 3.6197 | 22.2621 | 23.9232 | 5.7741 | 31.6269 | 8.2786 | 11.3155 | 21.0265 | 11.2922 | 55.2327 | 19.2988 | 560.1047
62 | 4.8417 | 43.2905 | 18.5077 | 8.6301 | 35.9816 | 41.3566 | 37.1461 | 6.7656 | 18.1158 | 14.4869 | 14.824 | 25.4164 | 52.5018 | 16.2377 | 2.6689 | 23.3066 | 32.1116 | 5.9028 | 30.6458 | 13.3099 | 15.2226 | 15.6134 | 9.8991 | 56.0045 | 11.3226 | 554.1104
63 | 6.3971 | 34.0141 | 24.2106 | 8.7366 | 31.21 | 40.5319 | 36.0234 | 9.0511 | 15.6889 | 15.3182 | 14.1743 | 27.9361 | 49.6988 | 25.8824 | 3.1593 | 21.1721 | 30.895 | 4.8798 | 30.4744 | 13.8398 | 18.5675 | 20.7099 | 8.4704 | 49.1768 | 17.1869 | 557.4052
64 | 7.7366 | 27.1937 | 32.2955 | 5.8926 | 30.1511 | 41.8395 | 28.9036 | 9.3628 | 15.4587 | 15.8886 | 19.9583 | 22.6993 | 45.953 | 24.6755 | 3.719 | 20.2232 | 28.7662 | 5.1632 | 26.4198 | 13.889 | 24.175 | 14.4985 | 11.7576 | 46.4103 | 16.5504 | 539.5809
65 | 7.7937 | 42.2132 | 30.232 | 6.17 | 39.3351 | 35.5352 | 32.648 | 11.2172 | 18.4369 | 16.011 | 18.3353 | 28.6839 | 36.5692 | 25.39 | 3.7805 | 27.6984 | 29.3027 | 5.8216 | 26.5741 | 9.3487 | 22.4694 | 21.9561 | 9.8822 | 50.4255 | 19.6701 | 575.5002
66 | 7.8342 | 35.3646 | 28.8919 | 7.4303 | 16.4781 | 38.1556 | 26.1842 | 7.2454 | 19.2443 | 9.0044 | 16.3901 | 20.4487 | 35.7335 | 25.1844 | 3.7197 | 20.9022 | 30.7816 | 5.6026 | 21.9003 | 10.1779 | 23.5136 | 16.8911 | 11.4896 | 55.7461 | 17.6658 | 511.9804
67 | 6.7738 | 34.9172 | 23.6397 | 7.9749 | 27.5899 | 45.123 | 30.5386 | 9.5343 | 14.4724 | 10.9457 | 13.9752 | 16.5161 | 49.7917 | 25.9844 | 2.7174 | 24.0922 | 35.9634 | 5.4447 | 26.7742 | 13.0803 | 18.9542 | 15.2925 | 9.3472 | 40.1907 | 21.823 | 531.4565
68 | 6.5302 | 39.9228 | 25.0083 | 6.5094 | 27.5452 | 42.3451 | 36.7701 | 10.2495 | 18.993 | 12.2661 | 19.4629 | 27.2418 | 51.4376 | 24.5235 | 3.2491 | 24.2382 | 33.965 | 5.9533 | 29.8433 | 8.1638 | 22.6157 | 17.3358 | 10.4534 | 46.7898 | 21.8929 | 573.3057
69 | 7.2566 | 41.899 | 24.5945 | 5.7959 | 34.5263 | 50.8561 | 35.0181 | 10.6898 | 17.8155 | 10.1897 | 19.2658 | 20.4076 | 27.5832 | 22.0593 | 3.9816 | 20.8276 | 26.4642 | 5.9182 | 27.0865 | 12.6103 | 24.0565 | 17.3422 | 10.3449 | 48.4506 | 20.4838 | 545.5237
70 | 6.4486 | 33.785 | 32.4537 | 4.9818 | 31.3032 | 46.189 | 36.0755 | 9.8501 | 19.3808 | 14.033 | 16.3548 | 23.2606 | 46.0403 | 14.2285 | 3.3725 | 24.5822 | 24.7744 | 4.4793 | 25.7228 | 9.7207 | 17.5484 | 19.1187 | 10.063 | 41.411 | 17.5217 | 532.6997
71 | 5.4272 | 38.5188 | 31.5674 | 7.7998 | 38.4915 | 51.8897 | 32.2057 | 11.08 | 15.2588 | 14.6153 | 19.4286 | 28.2912 | 51.4584 | 21.5758 | 2.5766 | 24.498 | 35.312 | 5.6439 | 26.3314 | 13.7746 | 17.5208 | 20.5569 | 11.7682 | 49.3054 | 19.0281 | 593.9241
72 | 6.5162 | 39.9085 | 30.3925 | 4.5214 | 36.6968 | 36.5441 | 22.0223 | 9.7351 | 18.7432 | 8.2428 | 15.3131 | 14.2457 | 46.2287 | 18.2946 | 3.658 | 18.1246 | 37.2704 | 5.2868 | 32.4063 | 10.53 | 21.6265 | 17.5906 | 11.2095 | 41.2705 | 16.3741 | 522.7523
73 | 5.7051 | 42.2088 | 29.8647 | 5.9667 | 38.7098 | 47.1984 | 31.3685 | 8.9072 | 18.3807 | 13.0127 | 21.2619 | 26.0391 | 47.2345 | 22.2226 | 3.7012 | 20.9102 | 30.5122 | 5.89 | 32.3999 | 7.8822 | 15.2417 | 12.9353 | 6.1469 | 54.3967 | 15.059 | 563.1557
74 | 8.0469 | 48.1009 | 25.9516 | 5.0113 | 30.3435 | 32.5981 | 23.5253 | 7.6682 | 16.6036 | 10.4355 | 18.3793 | 28.288 | 49.514 | 21.3225 | 3.7143 | 23.54 | 32.5032 | 4.9944 | 29.2636 | 11.0203 | 24.5722 | 21.4368 | 10.7062 | 41.0877 | 12.0641 | 540.6913
75 | 6.7916 | 44.5005 | 24.2339 | 8.6761 | 36.9943 | 50.6631 | 25.0428 | 9.9205 | 16.8545 | 15.3217 | 19.3421 | 17.4041 | 28.5813 | 25.1203 | 2.3463 | 19.3384 | 36.6227 | 5.925 | 25.1706 | 13.729 | 23.3593 | 16.6078 | 11.6699 | 50.9121 | 20.8642 | 555.9919
76 | 6.7957 | 34.0672 | 28.8159 | 7.3407 | 37.5122 | 43.8483 | 36.9498 | 9.2913 | 12.3059 | 8.1047 | 18.1333 | 21.2899 | 40.3775 | 19.0029 | 3.057 | 22.9166 | 34.2632 | 3.4311 | 28.7457 | 12.078 | 25.3167 | 19.1781 | 8.8347 | 54.8009 | 19.0619 | 555.5192
77 | 4.9931 | 45.8933 | 18.393 | 8.0931 | 34.045 | 50.7792 | 32.9413 | 11.0034 | 12.8707 | 14.9476 | 16.4564 | 22.7441 | 45.6348 | 20.795 | 2.98 | 20.966 | 29.915 | 5.1582 | 32.5014 | 10.5499 | 25.0413 | 16.9009 | 11.2876 | 54.2666 | 20.5787 | 569.7355
78 | 7.0678 | 36.5882 | 25.4535 | 8.5675 | 38.8583 | 43.7376 | 25.4556 | 7.1812 | 18.6784 | 14.1767 | 17.1105 | 16.3053 | 47.497 | 17.6645 | 3.5538 | 21.9827 | 30.6932 | 4.3057 | 27.3759 | 7.6076 | 25.2507 | 14.492 | 11.0782 | 38.761 | 13.3061 | 522.749
79 | 6.4015 | 34.462 | 17.9533 | 5.69 | 28.3156 | 39.9168 | 30.8263 | 6.9459 | 18.0949 | 9.5415 | 15.7185 | 20.8752 | 40.5583 | 21.1501 | 3.8184 | 21.5754 | 25.1261 | 5.0795 | 28.3172 | 13.9748 | 13.6135 | 17.2491 | 12.2325 | 54.5836 | 16.3983 | 508.4183
80 | 8.0362 | 42.2892 | 23.8984 | 5.4443 | 33.6934 | 40.728 | 27.5937 | 7.696 | 18.0739 | 15.6786 | 18.0637 | 25.7688 | 48.9255 | 25.5312 | 3.2997 | 20.0878 | 26.7708 | 5.119 | 32.9116 | 11.7621 | 21.5428 | 21.8336 | 12.2958 | 51.2099 | 17.8032 | 566.0573
81 | 6.9586 | 45.2104 | 22.2495 | 8.156 | 29.3021 | 47.8892 | 35.0962 | 10.563 | 19.6918 | 13.1857 | 20.4113 | 26.8956 | 49.3325 | 25.2138 | 3.9032 | 24.4459 | 36.0703 | 4.8792 | 32.5172 | 13.9232 | 19.0673 | 12.0199 | 10.8298 | 48.7131 | 14.8957 | 581.4205
82 | 6.827 | 41.3348 | 28.4824 | 7.4279 | 29.6799 | 39.8535 | 24.458 | 11.2698 | 12.2067 | 13.6746 | 21.2507 | 24.2159 | 52.239 | 19.9851 | 2.2964 | 16.9428 | 24.381 | 5.8642 | 26.0889 | 13.7338 | 19.997 | 21.3172 | 9.1688 | 30.451 | 21.4371 | 524.5837
83 | 8.2455 | 44.6999 | 25.5131 | 8.2813 | 20.2531 | 48.616 | 30.8311 | 5.9928 | 16.4052 | 16.1759 | 18.9062 | 28.0368 | 52.1613 | 23.4786 | 2.3288 | 25.4003 | 27.878 | 4.0086 | 26.8553 | 12.1107 | 21.6722 | 19.5816 | 6.8297 | 57.8766 | 16.315 | 568.4535
84 | 7.1138 | 47.3264 | 25.9346 | 7.6284 | 34.5891 | 50.7409 | 28.2447 | 6.5742 | 16.9635 | 9.5138 | 19.9349 | 18.882 | 52.0697 | 24.1146 | 2.7379 | 23.5476 | 34.2389 | 4.0377 | 26.5754 | 13.8216 | 21.6787 | 19.3941 | 12.2698 | 40.0567 | 16.2495 | 564.2385
85 | 7.779 | 38.2292 | 30.0541 | 5.8225 | 38.7484 | 36.7087 | 33.7738 | 10.5181 | 15.7437 | 14.792 | 18.3007 | 26.8469 | 41.0345 | 21.5179 | 3.8139 | 24.2317 | 33.4238 | 5.3156 | 25.8731 | 9.2989 | 12.2593 | 15.9508 | 10.8792 | 45.1771 | 21.3616 | 547.4544
86 | 4.374 | 36.2552 | 30.93 | 5.6227 | 33.0451 | 42.6053 | 34.5318 | 10.7138 | 12.8587 | 12.0697 | 18.4704 | 25.7072 | 51.4385 | 25.7932 | 2.5266 | 21.4792 | 23.099 | 5.0545 | 30.1047 | 11.9453 | 17.4918 | 19.7749 | 10.7754 | 38.3921 | 15.9571 | 541.0163
87 | 7.0182 | 42.3017 | 25.224 | 7.0644 | 29.1534 | 30.5471 | 31.038 | 8.7805 | 16.2084 | 15.9531 | 16.3052 | 21.9855 | 33.5532 | 22.5461 | 2.5951 | 19.1133 | 35.2842 | 4.8359 | 32.612 | 10.9519 | 22.0843 | 20.8496 | 9.4208 | 48.9466 | 18.7754 | 533.1478
88 | 6.8727 | 34.602 | 33.3599 | 5.636 | 29.1915 | 50.7607 | 25.444 | 5.3983 | 18.8692 | 14.4914 | 17.3641 | 15.8466 | 37.7745 | 25.909 | 2.5183 | 24.3875 | 33.9176 | 4.7967 | 29.842 | 12.3334 | 23.7324 | 14.6101 | 12.077 | 54.5364 | 18.8461 | 553.1177
89 | 7.4366 | 43.5121 | 24.8625 | 8.4895 | 26.3874 | 45.7468 | 30.7542 | 7.5368 | 16.2076 | 15.1631 | 13.3216 | 26.7625 | 42.3498 | 25.2145 | 3.0278 | 23.3919 | 28.2697 | 5.0466 | 19.3935 | 10.4175 | 25.0769 | 14.7348 | 7.7068 | 43.2412 | 21.0766 | 535.1281
90 | 7.7203 | 41.2098 | 32.4173 | 6.7871 | 30.1613 | 30.123 | 34.1972 | 9.856 | 15.9652 | 12.716 | 21.4943 | 25.8112 | 39.3452 | 15.8431 | 3.1939 | 26.3817 | 38.5428 | 5.6982 | 23.4588 | 12.6281 | 16.2196 | 18.7459 | 9.6009 | 40.6942 | 21.5061 | 540.3172
91 | 5.9842 | 33.6023 | 31.9733 | 8.3285 | 37.5009 | 50.1527 | 26.7934 | 9.8464 | 15.3092 | 13.5748 | 18.7516 | 21.5958 | 34.3166 | 25.1267 | 3.9273 | 18.1171 | 21.8716 | 5.1211 | 31.7341 | 10.8693 | 22.6906 | 19.5745 | 8.9338 | 33.1355 | 20.5293 | 529.3606
92 | 7.9246 | 34.6285 | 31.2015 | 6.3721 | 30.5718 | 47.8532 | 38.5309 | 5.2773 | 17.3888 | 13.7772 | 19.9694 | 23.6869 | 46.6363 | 22.7525 | 3.8856 | 22.8643 | 36.1721 | 5.4508 | 32.856 | 10.7921 | 17.6322 | 17.8332 | 8.2114 | 56.9816 | 14.4968 | 573.7471
93 | 7.0081 | 42.0441 | 32.2375 | 7.2071 | 21.5107 | 44.1685 | 28.6785 | 10.0369 | 12.0599 | 16.6265 | 21.767 | 23.9028 | 53.7033 | 22.5499 | 3.1727 | 21.8502 | 30.741 | 5.2808 | 30.3911 | 11.8456 | 21.5078 | 20.8621 | 11.7312 | 39.9282 | 16.9723 | 557.7836
94 | 6.6331 | 47.0474 | 23.8463 | 7.7316 | 29.9395 | 42.9683 | 30.9751 | 10.9993 | 19.3398 | 14.9396 | 20.0067 | 26.4706 | 35.0311 | 23.1864 | 3.7805 | 24.4205 | 23.984 | 4.3447 | 30.9595 | 11.1429 | 20.1257 | 21.1002 | 8.3654 | 45.9631 | 18.0236 | 551.3246
95 | 6.9827 | 44.6463 | 30.1476 | 5.5249 | 34.4057 | 47.6084 | 19.4152 | 9.859 | 19.4227 | 9.5855 | 20.1123 | 24.6979 | 36.125 | 19.545 | 3.7641 | 26.1709 | 29.8335 | 5.3963 | 23.0709 | 13.1119 | 23.5022 | 19.9755 | 6.5863 | 48.5238 | 10.1072 | 538.1207
96 | 6.5616 | 40.075 | 15.0404 | 5.5779 | 30.2267 | 31.4422 | 32.7862 | 7.8951 | 15.2755 | 14.2251 | 22.2892 | 19.0915 | 38.7782 | 24.2916 | 3.9297 | 16.434 | 38.2126 | 5.2484 | 25.64 | 12.8588 | 26.0495 | 14.623 | 11.3877 | 43.1958 | 19.3836 | 520.5191
97 | 7.5754 | 39.8905 | 19.6115 | 5.9798 | 27.8101 | 48.1008 | 31.8022 | 10.5746 | 15.9475 | 12.6009 | 18.4604 | 20.7185 | 51.0953 | 24.0717 | 3.8255 | 25.4142 | 22.9852 | 5.628 | 24.0143 | 10.7059 | 25.9318 | 13.9133 | 11.0671 | 43.9924 | 15.9467 | 537.6638
98 | 8.1952 | 30.9191 | 24.2371 | 8.343 | 33.6053 | 23.205 | 24.5193 | 8.6388 | 14.2284 | 16.7389 | 13.6436 | 15.8418 | 32.5431 | 22.3473 | 2.707 | 18.2426 | 28.122 | 5.7336 | 20.6398 | 13.563 | 20.1688 | 15.4393 | 9.5392 | 45.4727 | 16.5902 | 473.2242
99 | 7.1415 | 34.7479 | 28.8712 | 5.836 | 31.6116 | 51.4831 | 28.1353 | 9.7665 | 19.2006 | 14.5496 | 20.6216 | 25.8239 | 50.8497 | 23.5025 | 3.1004 | 17.1164 | 23.7313 | 5.9249 | 29.5594 | 8.3177 | 25.9878 | 13.6144 | 12.0421 | 36.9411 | 13.2588 | 541.7355
100 | 7.9257 | 36.8082 | 29.5858 | 6.1671 | 38.3971 | 44.7788 | 35.5113 | 9.7061 | 19.2713 | 12.2662 | 17.6465 | 25.7312 | 41.7181 | 22.1184 | 3.4839 | 24.5928 | 34.012 | 5.555 | 26.8288 | 8.8325 | 21.1311 | 17.1426 | 11.6642 | 39.0722 | 22.2116 | 562.1585
101 | 7.8154 | 46.3064 | 32.6619 | 5.8537 | 24.1884 | 51.869 | 32.2925 | 10.172 | 19.4127 | 12.8854 | 19.9772 | 21.4484 | 51.6884 | 23.0529 | 2.8246 | 24.2882 | 26.6118 | 5.1465 | 27.486 | 7.5346 | 21.1869 | 13.804 | 10.2418 | 41.6231 | 9.7585 | 550.1304
102 | 6.0531 | 44.3068 | 20.3193 | 7.9703 | 29.1311 | 51.5467 | 36.8505 | 5.7387 | 19.7256 | 12.7907 | 14.8041 | 25.3572 | 44.7247 | 25.1544 | 2.9656 | 23.6163 | 30.2409 | 5.6478 | 32.0091 | 13.8686 | 23.0434 | 18.412 | 10.8722 | 34.9937 | 21.742 | 561.885
103 | 5.5572 | 32.5314 | 25.9097 | 8.6196 | 23.3793 | 39.5793 | 31.3965 | 7.35 | 17.6462 | 14.7363 | 15.4085 | 18.8726 | 42.7864 | 25.6171 | 3.7916 | 26.0481 | 30.3191 | 5.1831 | 31.957 | 9.2327 | 22.308 | 21.6798 | 10.3593 | 27.4634 | 14.4738 | 512.206
104 | 7.0432 | 33.7804 | 31.5751 | 6.5739 | 36.62 | 45.0007 | 37.2966 | 9.9237 | 13.6977 | 12.4767 | 21.5983 | 22.4236 | 54.3512 | 19.5632 | 3.1893 | 26.114 | 28.0927 | 4.1197 | 19.3817 | 9.6968 | 10.4942 | 21.873 | 7.6043 | 43.2645 | 15.9851 | 541.7397
105 | 7.6042 | 44.3665 | 17.4001 | 8.4112 | 29.8409 | 45.7066 | 32.9402 | 11.4888 | 19.8249 | 10.5822 | 18.7042 | 26.6199 | 44.1238 | 14.3453 | 3.2341 | 14.4736 | 28.8788 | 4.9841 | 27.5826 | 12.9821 | 24.5881 | 21.3044 | 12.0774 | 40.9195 | 17.5559 | 540.5393
106 | 7.6653 | 43.1307 | 21.5486 | 8.6965 | 35.413 | 39.591 | 37.4573 | 7.5225 | 19.9806 | 13.0959 | 22.0692 | 19.4251 | 48.6121 | 19.4 | 3.4739 | 11.3937 | 36.2164 | 4.4712 | 25.307 | 12.5775 | 22.5376 | 18.9359 | 10.9587 | 56.9951 | 16.2499 | 562.7245
107 | 4.3923 | 27.2985 | 29.4347 | 8.3937 | 22.7162 | 47.9727 | 25.6425 | 9.1703 | 18.5013 | 12.6011 | 22.243 | 21.4778 | 26.8182 | 21.6575 | 3.4671 | 23.2959 | 25.8791 | 5.3132 | 28.4639 | 9.3358 | 20.9909 | 18.3874 | 10.7919 | 43.0678 | 18.6492 | 505.9621
108 | 7.0352 | 29.0475 | 29.9571 | 8.1293 | 25.3206 | 51.219 | 38.082 | 11.0415 | 17.4997 | 16.7814 | 16.3194 | 26.2264 | 41.8182 | 21.6738 | 3.1661 | 16.3935 | 34.8465 | 5.9651 | 20.349 | 10.9488 | 16.4761 | 13.8604 | 10.6563 | 36.9526 | 20.9331 | 530.6988
109 | 4.1428 | 40.0865 | 29.2159 | 4.9883 | 31.4645 | 43.1069 | 28.4147 | 10.7846 | 14.9686 | 10.0985 | 18.008 | 17.8476 | 35.5095 | 22.0748 | 3.87 | 15.7195 | 31.7847 | 5.1628 | 30.4769 | 13.1316 | 18.1246 | 11.8155 | 8.2524 | 50.2072 | 20.0735 | 519.3299
110 | 6.4094 | 38.4749 | 19.9893 | 6.9609 | 22.3522 | 39.6032 | 22.8845 | 10.8001 | 14.8597 | 11.1414 | 15.3491 | 23.3021 | 47.3886 | 15.784 | 2.091 | 25.386 | 32.7449 | 5.6445 | 23.1152 | 12.8752 | 16.088 | 19.5706 | 9.7652 | 51.0688 | 18.1929 | 511.8418
111 | 6.8308 | 43.3797 | 27.4982 | 8.3367 | 35.9764 | 38.9961 | 36.9014 | 10.9708 | 18.4685 | 15.6791 | 18.7414 | 18.8194 | 53.1641 | 24.9618 | 3.1686 | 22.4092 | 29.268 | 5.7223 | 16.3729 | 13.4563 | 21.2549 | 19.3786 | 10.2893 | 44.0583 | 18.1646 | 562.2673
112 | 7.8046 | 39.5249 | 20.5632 | 6.1475 | 27.8398 | 36.1153 | 33.4239 | 5.8637 | 16.1943 | 11.6031 | 17.5905 | 25.413 | 51.1524 | 24.8974 | 3.502 | 26.941 | 34.201 | 5.063 | 21.0582 | 12.9744 | 19.393 | 18.3102 | 8.3485 | 52.5 | 15.9355 | 542.3604
113 | 6.6226 | 49.0529 | 28.87 | 5.73 | 37.0491 | 38.9801 | 34.9498 | 9.1511 | 17.7938 | 16.4502 | 17.4304 | 25.6697 | 49.2047 | 22.9121 | 3.3091 | 22.4642 | 28.8101 | 5.3191 | 23.7686 | 13.3616 | 16.8841 | 19.5818 | 8.1797 | 54.3152 | 21.4228 | 577.2828
114 | 8.1959 | 24.625 | 24.9662 | 5.3293 | 19.8486 | 46.8422 | 17.7559 | 10.3521 | 12.8068 | 10.0609 | 17.5383 | 25.4903 | 44.9621 | 25.7453 | 3.3919 | 14.0422 | 29.2886 | 4.1848 | 27.7114 | 12.688 | 23.2604 | 18.3924 | 8.8832 | 46.2309 | 19.4678 | 502.0606
115 | 7.1428 | 26.3023 | 31.1332 | 7.7288 | 26.2916 | 46.2256 | 36.3661 | 10.8405 | 16.3541 | 13.3988 | 22.4355 | 28.4358 | 49.8447 | 25.3016 | 3.8759 | 19.3505 | 31.6287 | 3.85 | 28.9978 | 12.9457 | 17.8217 | 14.5013 | 10.6519 | 37.6143 | 17.573 | 546.6122
116 | 5.8076 | 43.4573 | 33.2631 | 5.4493 | 29.8265 | 46.7418 | 29.2861 | 9.8471 | 12.7466 | 15.7204 | 19.9774 | 21.7933 | 53.7891 | 20.9742 | 3.5838 | 23.0369 | 27.4424 | 4.9801 | 26.0125 | 11.3182 | 18.8504 | 21.6859 | 10.056 | 27.6123 | 18.5643 | 541.8226
117 | 7.8567 | 39.0725 | 27.7383 | 5.0169 | 31.6646 | 53.2222 | 24.4313 | 10.5246 | 14.4138 | 12.362 | 14.7975 | 18.0157 | 51.1748 | 25.1449 | 3.6362 | 25.2238 | 28.7104 | 5.1899 | 29.0264 | 9.9661 | 18.0214 | 20.791 | 11.9843 | 58.2053 | 9.6393 | 555.83
118 | 7.6779 | 44.4158 | 27.5065 | 4.7388 | 27.0058 | 53.4045 | 16.2492 | 11.0784 | 18.4435 | 15.142 | 11.8172 | 18.8056 | 51.1071 | 18.7561 | 3.2593 | 22.5479 | 35.3593 | 5.0875 | 26.5399 | 13.3692 | 22.5751 | 21.1803 | 12.0088 | 51.3506 | 22.1624 | 561.5886
119 | 6.7673 | 43.2122 | 25.4224 | 6.3359 | 35.9642 | 51.5715 | 18.0647 | 11.1318 | 18.348 | 15.5818 | 21.9036 | 14.5846 | 49.9664 | 20.0298 | 3.5472 | 19.7913 | 20.4768 | 5.6147 | 24.901 | 13.644 | 25.1975 | 21.078 | 6.7809 | 50.4433 | 16.1646 | 546.5235
120 | 7.9117 | 30.1316 | 30.2394 | 5.8058 | 25.531 | 47.6237 | 34.4138 | 8.2421 | 16.276 | 14.9859 | 19.2656 | 27.4154 | 43.8537 | 25.6019 | 3.3582 | 18.6495 | 24.3347 | 3.7364 | 27.1401 | 10.8958 | 26.0785 | 19.4328 | 11.8753 | 53.1056 | 10.8731 | 546.7778
121 | 7.4329 | 37.607 | 28.7889 | 7.7249 | 26.9155 | 42.864 | 29.0217 | 9.171 | 18.3397 | 10.6185 | 17.4057 | 24.5237 | 53.9252 | 22.6863 | 2.8617 | 18.8265 | 26.7719 | 4.2675 | 28.0548 | 8.2751 | 24.1651 | 19.8253 | 9.9215 | 48.735 | 17.142 | 545.8713
122 | 6.7906 | 36.0051 | 25.9148 | 4.6232 | 28.659 | 45.9947 | 21.4602 | 9.7716 | 15.4613 | 16.5207 | 16.5106 | 27.0239 | 46.3903 | 25.6355 | 3.3131 | 24.0154 | 29.8928 | 3.1739 | 32.2399 | 12.8137 | 16.5023 | 20.2027 | 8.6059 | 33.5641 | 15.5969 | 526.6821
123 | 8.111 | 44.9203 | 28.6349 | 5.8243 | 28.0821 | 34.3079 | 36.3871 | 8.3118 | 18.5357 | 13.7288 | 13.2777 | 23.7987 | 44.5931 | 17.4775 | 2.5449 | 19.0907 | 23.0213 | 4.7654 | 17.5579 | 10.685 | 17.7008 | 20.2575 | 9.8308 | 52.0749 | 13.3638 | 516.8841
124 | 7.9362 | 39.6323 | 32.1937 | 4.6096 | 29.7865 | 48.0597 | 27.7523 | 8.5701 | 18.7327 | 13.8754 | 13.8265 | 25.4799 | 30.4104 | 23.5299 | 3.8016 | 26.4346 | 29.0426 | 5.7974 | 22.7839 | 10.2593 | 17.8932 | 17.0904 | 9.1617 | 44.168 | 18.7188 | 529.5468
125 | 8.0323 | 27.9098 | 18.3597 | 6.0274 | 30.1728 | 43.832 | 29.2337 | 11.2233 | 13.2647 | 15.481 | 11.6778 | 23.1071 | 27.9366 | 21.8483 | 2.7893 | 21.6771 | 38.1357 | 5.4178 | 28.7856 | 13.2296 | 11.9717 | 21.9973 | 7.1947 | 57.0385 | 18.1043 | 514.4482
126 | 5.0653 | 44.8229 | 28.5006 | 7.3689 | 30.3767 | 49.1949 | 34.8993 | 11.533 | 10.6158 | 10.3385 | 18.2823 | 27.2277 | 55.3915 | 19.4844 | 3.2516 | 23.3768 | 36.7842 | 4.1867 | 24.001 | 12.2396 | 22.5287 | 15.0957 | 9.4029 | 36.8453 | 20.8633 | 561.6775
127 | 8.2063 | 40.7775 | 30.3943 | 8.3966 | 26.8164 | 43.1324 | 24.5835 | 9.7369 | 16.557 | 15.765 | 22.0628 | 18.6911 | 54.242 | 25.623 | 3.6183 | 18.1596 | 24.343 | 5.3324 | 26.0759 | 13.6398 | 21.521 | 17.0905 | 9.1302 | 48.1641 | 16.6116 | 548.6713
128 | 6.177 | 34.6972 | 16.2769 | 6.3638 | 19.1222 | 47.9083 | 36.5508 | 8.7201 | 18.3341 | 11.4153 | 17.5523 | 27.2261 | 34.7908 | 20.0317 | 3.1678 | 22.7869 | 34.5089 | 4.0644 | 31.4054 | 13.8807 | 15.747 | 17.2517 | 9.7953 | 49.6523 | 21.2569 | 528.6841
129 | 5.773 | 28.7646 | 22.5474 | 6.8627 | 34.0174 | 38.0398 | 27.5894 | 7.3427 | 12.6187 | 11.8061 | 18.285 | 22.1977 | 33.1054 | 22.6164 | 3.7625 | 23.1811 | 28.2195 | 4.2407 | 22.8988 | 8.9699 | 23.2061 | 16.7506 | 8.2812 | 56.5821 | 18.5389 | 506.1975
130 | 6.3508 | 34.4231 | 30.3612 | 7.8781 | 21.1884 | 52.4099 | 37.8612 | 9.4285 | 11.3761 | 7.9084 | 12.4162 | 20.3767 | 51.3344 | 18.2057 | 3.8148 | 26.6357 | 35.3214 | 5.8821 | 19.7009 | 10.0605 | 23.1561 | 20.7488 | 9.4643 | 26.8556 | 17.8138 | 520.9726
131 | 7.8487 | 38.0726 | 32.4702 | 4.3532 | 26.5884 | 47.0295 | 17.1169 | 11.853 | 18.7003 | 14.2511 | 19.9539 | 25.8152 | 28.3962 | 22.7777 | 3.6551 | 26.6353 | 33.5199 | 5.0803 | 28.296 | 11.9774 | 23.1831 | 21.7428 | 9.719 | 51.9098 | 15.1124 | 546.0579
132 | 5.7229 | 43.0283 | 24.9116 | 7.5235 | 20.772 | 37.4366 | 29.8298 | 11.0763 | 15.9838 | 14.0292 | 21.3792 | 25.7769 | 44.4755 | 23.6288 | 2.5065 | 26.2721 | 25.7875 | 5.5217 | 30.1276 | 13.7751 | 21.529 | 18.9318 | 12.3949 | 28.4133 | 17.7783 | 528.6121
133 | 6.7337 | 38.0313 | 28.1186 | 4.8795 | 27.9993 | 33.1936 | 36.1447 | 10.8025 | 16.9118 | 12.546 | 15.9467 | 24.4527 | 38.3271 | 22.9908 | 3.417 | 21.0071 | 35.5216 | 5.4657 | 24.4967 | 13.4539 | 14.0131 | 18.3027 | 10.6965 | 54.9309 | 19.4888 | 537.8723
134 | 7.4607 | 46.0245 | 24.1816 | 5.3749 | 33.1201 | 39.6275 | 33.5086 | 11.7898 | 16.4132 | 16.7485 | 21.8414 | 22.6576 | 50.6352 | 21.4728 | 3.5863 | 27.5831 | 30.7812 | 4.3248 | 24.073 | 11.1309 | 20.9756 | 20.9385 | 6.1012 | 50.1936 | 17.6168 | 568.1612
135 | 6.2389 | 45.4169 | 31.7054 | 7.0505 | 30.4235 | 44.1421 | 34.108 | 10.6325 | 13.9955 | 13.6028 | 22.0143 | 26.2716 | 50.0435 | 21.2571 | 3.819 | 23.4312 | 32.2999 | 4.6398 | 32.0535 | 9.9877 | 24.8149 | 21.073 | 10.7158 | 47.5928 | 17.7807 | 585.1106
136 | 7.0927 | 42.8019 | 25.385 | 7.8764 | 38.1351 | 48.2809 | 29.1374 | 10.8988 | 17.9062 | 14.0444 | 17.6533 | 22.1002 | 34.7651 | 16.7273 | 3.5895 | 22.5249 | 31.2792 | 5.618 | 30.2877 | 13.5308 | 15.4663 | 19.7554 | 11.7859 | 43.3939 | 15.185 | 545.2214
137 | 6.9213 | 44.4096 | 31.4961 | 7.281 | 38.3005 | 47.8643 | 37.0794 | 11.1513 | 19.6827 | 13.9405 | 13.5838 | 21.4638 | 25.8716 | 24.8256 | 3.8712 | 21.2044 | 33.6566 | 4.9881 | 29.9853 | 11.7144 | 10.3623 | 19.6359 | 12.1041 | 48.593 | 19.6233 | 559.6104
138 | 4.6965 | 45.9701 | 23.6244 | 6.1353 | 25.2527 | 47.2551 | 38.8492 | 8.062 | 19.1651 | 13.3971 | 18.1139 | 23.1283 | 45.7519 | 20.6309 | 2.2835 | 23.666 | 37.3577 | 5.9969 | 31.461 | 8.0208 | 20.2616 | 20.8521 | 11.2688 | 47.7694 | 21.9528 | 570.9233
139 | 6.1727 | 31.7433 | 28.8762 | 5.5775 | 34.1861 | 38.4755 | 35.4065 | 7.8737 | 11.5992 | 13.2219 | 17.9169 | 26.7902 | 53.9588 | 18.4262 | 3.6722 | 17.4659 | 34.7493 | 5.8256 | 24.2018 | 12.6424 | 16.462 | 18.3764 | 7.8636 | 52.5121 | 19.6405 | 543.6363
140 | 6.5006 | 40.7365 | 31.9048 | 6.0703 | 39.2952 | 52.9567 | 32.4406 | 11.4913 | 15.3497 | 13.5416 | 14.4821 | 10.5118 | 30.8348 | 22.9422 | 3.4977 | 23.0411 | 33.3899 | 5.2507 | 25.709 | 13.3253 | 13.8327 | 21.472 | 11.522 | 49.5462 | 15.3912 | 545.0358
141 | 5.6941 | 30.8176 | 28.6878 | 7.2077 | 33.5275 | 47.7238 | 36.7377 | 9.5397 | 19.1199 | 9.0843 | 18.8591 | 18.3105 | 44.0932 | 24.5025 | 3.0022 | 23.8201 | 34.4625 | 5.9411 | 24.6683 | 11.5377 | 19.0708 | 17.6034 | 10.0733 | 53.6704 | 12.0345 | 549.7896
142 | 7.0398 | 35.6318 | 22.3637 | 5.8847 | 24.0366 | 28.5824 | 28.7326 | 7.6748 | 13.5943 | 14.5608 | 20.5181 | 18.0487 | 51.0612 | 22.7191 | 3.3601 | 19.179 | 22.1938 | 4.9555 | 27.9706 | 12.0226 | 21.1033 | 14.8566 | 12.2937 | 46.8886 | 17.8379 | 503.1102
143 | 6.9295 | 43.7056 | 30.1049 | 6.2286 | 34.8505 | 48.5503 | 33.2799 | 8.9475 | 16.4825 | 15.8087 | 11.5832 | 17.1713 | 35.8881 | 25.3458 | 3.1523 | 16.9621 | 21.4891 | 5.8678 | 25.4416 | 13.8499 | 21.7047 | 20.2005 | 12.4077 | 47.3399 | 20.2753 | 543.5674
144 | 5.7318 | 44.9622 | 16.6008 | 6.4438 | 21.522 | 37.6378 | 21.1171 | 11.1626 | 15.8779 | 10.7329 | 15.0121 | 21.6969 | 35.4318 | 15.7283 | 3.7776 | 18.7903 | 23.0488 | 5.8577 | 27.1646 | 11.9559 | 14.8851 | 19.4501 | 6.5527 | 47.0889 | 15.0765 | 473.3062
145 | 4.8004 | 35.6873 | 32.2338 | 5.889 | 35.3781 | 45.8269 | 38.1042 | 8.8535 | 18.7556 | 11.7353 | 17.9334 | 24.3987 | 51.8124 | 24.2463 | 2.2408 | 20.5699 | 26.0436 | 4.8619 | 31.2148 | 13.0324 | 20.6787 | 21.0933 | 9.1063 | 50.7549 | 12.2126 | 567.4641
146 | 7.2399 | 44.1529 | 27.3752 | 7.1461 | 36.4772 | 44.8873 | 36.5319 | 11.5642 | 17.1693 | 15.525 | 20.0682 | 21.9628 | 52.1657 | 20.9218 | 3.8251 | 26.5052 | 32.2309 | 5.791 | 18.2693 | 11.1781 | 22.3193 | 18.7217 | 8.7541 | 52.4314 | 19.3057 | 582.5194
147 | 5.6425 | 46.8343 | 26.2585 | 7.7078 | 33.3575 | 48.4574 | 33.4204 | 9.27 | 19.7385 | 13.3059 | 17.55 | 15.0219 | 43.0351 | 25.8978 | 3.8265 | 22.7196 | 32.8319 | 5.0023 | 25.0921 | 7.4088 | 15.7811 | 13.6899 | 12.1109 | 51.1866 | 18.7645 | 553.9113
148 | 7.5015 | 40.259 | 30.4974 | 7.9162 | 30.2821 | 36.1909 | 36.7226 | 8.4892 | 16.9134 | 11.2 | 19.9002 | 15.0761 | 42.1172 | 25.5824 | 3.8221 | 15.939 | 38.254 | 5.7355 | 24.4189 | 12.2737 | 15.8307 | 18.6043 | 7.6099 | 50.3319 | 21.1838 | 542.652
149 | 7.2985 | 48.9009 | 28.966 | 6.9716 | 29.288 | 39.7048 | 33.0536 | 10.3708 | 17.6634 | 15.7743 | 17.6519 | 23.2811 | 49.6157 | 15.7255 | 2.8123 | 19.4469 | 32.6587 | 5.4077 | 22.7908 | 13.2211 | 18.8173 | 13.0413 | 11.8537 | 47.3132 | 21.7782 | 553.4071
150 | 6.6706 | 39.6556 | 26.9089 | 6.2654 | 34.7558 | 42.8479 | 30.1093 | 6.6103 | 17.2807 | 15.6236 | 21.2504 | 21.712 | 44.45 | 24.9437 | 2.8709 | 21.2631 | 36.8985 | 4.7663 | 20.4657 | 13.7706 | 21.911 | 20.1722 | 9.447 | 38.5485 | 15.01 | 544.2079
151 | 6.4702 | 45.228 | 18.4881 | 8.7349 | 33.3695 | 48.9582 | 22.279 | 11.2334 | 12.8889 | 14.9742 | 16.9391 | 13.8016 | 36.5288 | 25.0851 | 3.0937 | 21.6077 | 37.79 | 3.5952 | 30.9356 | 12.0998 | 19.9852 | 17.5361 | 10.1805 | 47.8774 | 16.9168 | 536.597
152 | 7.7372 | 43.1952 | 16.5167 | 4.8997 | 36.3857 | 40.2241 | 33.2904 | 5.5808 | 14.4351 | 14.8507 | 20.4388 | 24.431 | 46.6184 | 25.9496 | 2.8251 | 20.99 | 29.246 | 5.5108 | 31.735 | 13.1112 | 18.9741 | 21.917 | 7.4333 | 53.5738 | 16.6246 | 556.4945
153 | 6.6007 | 41.0678 | 21.2565 | 7.9781 | 38.3456 | 50.6275 | 38.1025 | 8.5315 | 13.1727 | 10.7937 | 18.7494 | 28.4567 | 42.5625 | 23.6385 | 3.449 | 22.2075 | 30.7416 | 5.2166 | 24.4375 | 13.375 | 23.1769 | 16.4874 | 9.6963 | 58.0562 | 11.3884 | 568.1161
154 | 6.5971 | 47.3499 | 30.1469 | 7.353 | 33.3831 | 32.8195 | 32.4191 | 8.9623 | 17.018 | 13.8555 | 15.9977 | 17.9712 | 51.3527 | 21.3085 | 3.6325 | 22.9099 | 33.2656 | 5.4884 | 30.5532 | 8.8451 | 21.6378 | 13.4055 | 11.6792 | 56.1606 | 20.398 | 564.5102
155 | 3.8283 | 36.8231 | 30.9287 | 7.8725 | 39.1448 | 47.0118 | 31.2211 | 6.8947 | 19.317 | 13.8164 | 16.8822 | 22.4455 | 32.4709 | 21.3102 | 3.2824 | 16.9981 | 34.7639 | 5.8147 | 29.0896 | 13.6606 | 22.637 | 16.9243 | 10.7282 | 38.504 | 20.9182 | 543.2882
156 | 6.1929 | 43.4447 | 32.3398 | 7.8749 | 19.0979 | 49.9427 | 28.06 | 8.2806 | 19.547 | 13.9292 | 12.7164 | 23.4651 | 36.7039 | 20.5433 | 3.5403 | 26.8645 | 33.4585 | 4.6627 | 32.8412 | 10.8518 | 24.5572 | 18.1428 | 11.0586 | 44.3559 | 15.9065 | 548.3784
157 | 8.1605 | 28.9414 | 27.4318 | 5.8603 | 27.5731 | 29.9258 | 30.5355 | 8.5463 | 13.1073 | 13.2451 | 15.9218 | 27.1459 | 47.5391 | 25.4985 | 3.5994 | 27.6151 | 25.6797 | 5.3683 | 31.8822 | 13.7723 | 18.2988 | 16.3841 | 8.6116 | 35.3153 | 21.9914 | 517.9502
158 | 6.4546 | 43.595 | 26.1976 | 7.2692 | 22.1939 | 47.8663 | 22.5549 | 6.9079 | 15.6939 | 12.9008 | 20.3269 | 28.0305 | 36.4029 | 23.1363 | 2.5481 | 26.7966 | 35.904 | 5.6265 | 21.8241 | 10.9815 | 24.2299 | 13.407 | 10.4006 | 42.2563 | 21.6718 | 535.1772
159 | 7.2088 | 24.3425 | 29.103 | 7.5582 | 18.9725 | 38.8656 | 33.0682 | 10.4241 | 12.924 | 10.5066 | 19.4974 | 25.1971 | 48.6361 | 25.5655 | 3.6327 | 18.952 | 38.7485 | 5.506 | 24.1642 | 12.6732 | 19.786 | 19.5282 | 12.0375 | 53.2536 | 11.9114 | 532.0627
160 | 6.0548 | 31.8516 | 30.3503 | 5.6735 | 31.7332 | 49.2624 | 34.0045 | 8.5829 | 14.601 | 10.9552 | 16.7757 | 28.7628 | 49.3634 | 25.5237 | 3.0897 | 25.4615 | 24.1738 | 5.3091 | 25.592 | 13.1245 | 23.8305 | 21.1101 | 9.0078 | 47.5634 | 19.5684 | 561.3258
161 | 6.7003 | 41.8686 | 17.7525 | 7.7366 | 31.2853 | 35.1585 | 39.0363 | 7.0286 | 16.4224 | 12.276 | 20.5668 | 28.4527 | 40.9956 | 16.6395 | 3.802 | 23.4581 | 30.9644 | 5.2061 | 23.8332 | 13.501 | 17.2089 | 18.4707 | 12.0331 | 49.3597 | 19.5149 | 539.2714
162 | 8.0255 | 36.9433 | 31.9769 | 8.1307 | 30.277 | 35.6223 | 24.8483 | 7.7734 | 18.3493 | 15.5229 | 20.0138 | 21.6346 | 51.7816 | 24.1014 | 3.228 | 21.1277 | 26.9266 | 3.8056 | 23.7936 | 12.5751 | 26.2616 | 20.9725 | 10.7325 | 48.3316 | 20.915 | 553.6706
163 | 7.3551 | 44.0346 | 21.2345 | 8.5628 | 33.305 | 50.63 | 32.7264 | 8.9293 | 18.3495 | 13.3318 | 13.3567 | 21.7843 | 47.6683 | 23.1893 | 3.563 | 12.0173 | 32.7779 | 3.6268 | 28.7663 | 13.3589 | 12.1017 | 20.6611 | 10.7027 | 28.343 | 13.6569 | 524.0332
164 | 4.5163 | 42.8304 | 27.8657 | 7.8201 | 30.2503 | 34.8378 | 28.0841 | 11.1973 | 19.0213 | 15.828 | 21.5794 | 22.9066 | 42.7322 | 23.7669 | 2.3621 | 26.3495 | 27.0162 | 5.9937 | 28.2721 | 7.2406 | 8.6435 | 19.9968 | 11.1676 | 58.5824 | 21.0102 | 549.8714
165 | 4.1818 | 34.5424 | 30.4223 | 8.5568 | 31.3096 | 41.3293 | 35.3502 | 8.6724 | 15.8683 | 14.2652 | 22.1459 | 24.267 | 34.7622 | 23.2363 | 2.5241 | 22.3943 | 27.0471 | 4.84 | 27.6818 | 9.9143 | 19.4624 | 12.9558 | 6.4163 | 50.6977 | 17.1161 | 529.9594
166 | 5.0306 | 27.6648 | 30.1645 | 6.5666 | 27.415 | 43.671 | 28.0353 | 8.1842 | 17.0692 | 10.5672 | 12.895 | 22.5433 | 51.5814 | 18.966 | 3.24 | 19.0247 | 35.1926 | 4.395 | 23.7708 | 13.5213 | 21.4039 | 19.8916 | 7.7029 | 36.1634 | 18.802 | 513.4625
167 | 6.3917 | 35.1969 | 19.916 | 7.1608 | 19.0123 | 48.7982 | 25.6373 | 9.6685 | 15.4943 | 10.4476 | 14.8841 | 24.4683 | 51.6164 | 23.8627 | 2.6523 | 22.24 | 38.1923 | 5.9998 | 31.5501 | 7.9236 | 16.5835 | 21.799 | 11.4474 | 42.009 | 18.037 | 530.9892
168 | 5.2857 | 38.9875 | 26.0706 | 7.7318 | 38.7202 | 44.1984 | 26.9102 | 8.3841 | 18.7639 | 12.8348 | 21.4619 | 20.6709 | 53.2451 | 21.0367 | 2.6736 | 25.6553 | 21.5367 | 5.5069 | 25.7971 | 11.0365 | 23.4473 | 20.0468 | 9.7353 | 44.4131 | 22.1707 | 556.321
169 | 7.4366 | 35.6807 | 31.7581 | 8.2959 | 35.9937 | 51.8802 | 31.5143 | 11.4047 | 17.8754 | 13.5841 | 12.3544 | 20.6129 | 40.413 | 18.3619 | 3.5352 | 21.3586 | 19.3538 | 4.9902 | 16.8663 | 13.9252 | 13.6264 | 16.9307 | 12.0892 | 45.0145 | 17.199 | 522.0549
170 | 8.0971 | 33.252 | 22.7184 | 8.4585 | 37.0047 | 29.8481 | 29.7416 | 7.1512 | 17.2638 | 11.3635 | 14.6695 | 20.4875 | 27.0222 | 18.5356 | 3.1751 | 17.7626 | 22.466 | 3.5726 | 28.6916 | 11.1593 | 23.3133 | 18.7788 | 8.5591 | 51.8045 | 15.281 | 490.1777
171 | 7.4727 | 40.2975 | 31.5179 | 6.7535 | 15.3401 | 44.8494 | 29.1028 | 9.5988 | 16.8645 | 10.9261 | 16.1684 | 21.8673 | 44.0404 | 16.9278 | 3.5425 | 25.412 | 25.7254 | 5.3684 | 18.965 | 12.3504 | 17.1674 | 20.3696 | 9.4985 | 35.8367 | 17.4969 | 503.4602
172 | 7.0252 | 46.0215 | 26.2185 | 7.1064 | 32.9418 | 49.3484 | 27.6091 | 10.1706 | 17.3069 | 15.2257 | 11.067 | 20.1379 | 33.9301 | 25.3893 | 3.4185 | 18.7595 | 24.6629 | 4.1722 | 32.1133 | 13.0213 | 21.405 | 18.1095 | 12.3282 | 36.6024 | 21.5864 | 535.6775
173 | 8.1356 | 32.1726 | 27.966 | 8.0196 | 30.0587 | 34.358 | 22.2683 | 9.1361 | 17.8424 | 12.2985 | 18.7145 | 12.8892 | 40.6324 | 17.8603 | 3.5266 | 24.8628 | 29.0281 | 4.5592 | 29.2463 | 13.4692 | 25.115 | 19.8031 | 9.699 | 55.785 | 18.9806 | 526.4269
174 | 8.171 | 27.0837 | 29.1325 | 8.673 | 28.2077 | 45.1832 | 32.955 | 8.4072 | 16.7964 | 16.4914 | 20.4647 | 22.59 | 28.6802 | 23.8314 | 3.9261 | 21.4966 | 38.3766 | 3.4273 | 30.3708 | 11.6955 | 23.951 | 16.6519 | 10.8858 | 28.5236 | 17.0477 | 523.0201
175 | 5.0051 | 48.1242 | 31.7402 | 8.1867 | 27.6168 | 49.0869 | 32.9723 | 10.0183 | 18.8179 | 13.0757 | 12.4253 | 25.7746 | 41.5663 | 21.4921 | 3.7256 | 23.3212 | 27.1575 | 3.8657 | 24.1667 | 9.708 | 21.4191 | 20.6081 | 11.2427 | 54.1768 | 20.8105 | 566.1045
176 | 6.429 | 39.1449 | 26.8657 | 7.4529 | 38.6252 | 33.2964 | 27.9742 | 10.7033 | 15.8068 | 11.4661 | 17.2243 | 19.4815 | 50.7773 | 24.3653 | 3.6506 | 17.3432 | 39.0043 | 4.5454 | 22.9258 | 12.7544 | 18.4797 | 20.067 | 5.6461 | 56.3014 | 14.6705 | 545.0013
177 | 6.9145 | 41.7729 | 26.7692 | 8.6636 | 31.8429 | 45.2918 | 34.6606 | 11.0851 | 19.2694 | 11.8555 | 20.8201 | 19.9482 | 45.1406 | 25.5643 | 3.6865 | 26.1511 | 38.2524 | 5.1207 | 25.3119 | 12.7736 | 13.5947 | 17.3509 | 11.8753 | 51.7731 | 18.23 | 573.7189
178 | 5.718 | 29.0087 | 23.3445 | 6.7104 | 32.3487 | 41.4926 | 31.0772 | 10.78 | 12.6454 | 13.8718 | 21.0579 | 26.3957 | 46.1951 | 21.4083 | 3.7246 | 23.4252 | 34.7223 | 4.943 | 28.8951 | 13.1783 | 24.0134 | 18.5799 | 9.4443 | 55.1407 | 15.987 | 554.1084
179 | 7.6489 | 36.7382 | 31.335 | 7.7171 | 30.854 | 45.423 | 25.0804 | 10.1724 | 14.6334 | 12.9929 | 15.3263 | 21.6473 | 49.4643 | 23.4581 | 2.5289 | 14.1393 | 35.9977 | 5.4441 | 22.7583 | 12.7593 | 16.6654 | 21.4893 | 11.9366 | 50.4411 | 15.9968 | 542.6479
180 | 6.3469 | 42.3386 | 30.9847 | 8.1177 | 36.7123 | 49.1113 | 29.6114 | 8.6884 | 16.9158 | 13.8458 | 16.0383 | 16.6208 | 31.4692 | 24.7152 | 3.3309 | 24.998 | 34.8885 | 5.5277 | 20.7626 | 12.0382 | 24.0082 | 11.6568 | 9.2667 | 52.9071 | 16.1983 | 547.0993
181 | 8.2458 | 31.2536 | 18.6925 | 5.8465 | 32.6592 | 50.3253 | 39.0171 | 8.779 | 13.7008 | 14.8998 | 21.7864 | 26.7921 | 44.5721 | 25.6694 | 3.7712 | 27.2882 | 23.184 | 5.444 | 18.7936 | 13.8502 | 15.7847 | 17.5533 | 11.8532 | 58.1658 | 18.7569 | 556.6847
182 | 7.3281 | 35.1903 | 19.9955 | 8.1531 | 38.5482 | 51.8594 | 25.1654 | 9.0611 | 17.5066 | 13.4861 | 15.8856 | 20.2931 | 53.6302 | 25.9982 | 3.4618 | 23.9698 | 26.2687 | 3.3754 | 29.1952 | 13.1814 | 23.4499 | 18.6755 | 11.7586 | 46.7653 | 16.5493 | 558.7519
183 | 7.1796 | 39.7351 | 29.444 | 5.5851 | 37.6987 | 45.5452 | 26.8587 | 10.8098 | 16.9558 | 14.3376 | 21.1526 | 23.4093 | 33.0656 | 20.2037 | 3.807 | 21.3057 | 20.0332 | 5.9399 | 21.912 | 13.0343 | 20.6386 | 20.5621 | 9.1585 | 50.4248 | 17.0818 | 535.8787
184 | 8.1424 | 36.2364 | 30.3595 | 6.0505 | 34.7124 | 43.8747 | 34.1828 | 8.8672 | 18.3997 | 13.8766 | 17.775 | 18.5029 | 50.6458 | 17.9597 | 3.4517 | 16.5562 | 25.7546 | 5.6731 | 26.7192 | 13.8031 | 18.5787 | 21.3248 | 12.4016 | 50.4412 | 20.7399 | 555.0296
185 | 7.6254 | 29.0993 | 26.1255 | 6.4865 | 30.0884 | 34.1499 | 21.0708 | 8.5809 | 19.3247 | 12.1123 | 20.3059 | 20.9206 | 47.7222 | 24.9614 | 3.9641 | 25.5244 | 36.4513 | 5.0233 | 31.1743 | 10.1227 | 15.5935 | 19.0202 | 9.9378 | 50.3519 | 11.4903 | 527.2276
186 | 8.2452 | 46.9668 | 25.1459 | 7.1797 | 17.6041 | 49.5271 | 26.0511 | 7.9783 | 14.5798 | 9.7334 | 20.325 | 21.3644 | 39.0297 | 18.2644 | 3.9736 | 15.8288 | 25.8766 | 5.5348 | 31.6165 | 12.6048 | 19.5258 | 18.5865 | 7.0623 | 57.8504 | 20.6917 | 531.1468
187 | 6.6308 | 35.1479 | 30.5688 | 5.2775 | 37.9125 | 37.7992 | 22.1584 | 5.8802 | 17.7934 | 14.0962 | 17.4212 | 22.4891 | 54.3556 | 23.3102 | 2.8985 | 24.2522 | 36.1099 | 5.7271 | 25.1339 | 11.3549 | 19.4967 | 20.143 | 8.9405 | 52.0252 | 14.579 | 551.502
188 | 7.859 | 38.3292 | 24.0941 | 6.1073 | 27.3486 | 41.3211 | 28.6074 | 8.8999 | 18.9318 | 10.2213 | 20.212 | 25.8203 | 46.6915 | 24.8831 | 2.2237 | 26.459 | 36.4563 | 4.6517 | 32.295 | 13.1904 | 20.572 | 16.236 | 10.3008 | 55.3389 | 8.6444 | 555.6944
189 | 5.4098 | 33.8536 | 32.8599 | 6.6752 | 33.3863 | 28.9048 | 38.2819 | 11.9845 | 16.6723 | 14.3695 | 20.335 | 26.5709 | 38.5016 | 18.9877 | 3.7423 | 22.3823 | 36.4555 | 5.8678 | 32.2145 | 11.5232 | 21.6177 | 19.4343 | 8.447 | 54.2331 | 18.9987 | 561.7093
190 | 6.7843 | 34.2877 | 22.4143 | 7.7461 | 31.6459 | 47.5964 | 28.588 | 8.4631 | 17.5063 | 14.2873 | 18.5753 | 21.7222 | 36.581 | 22.271 | 2.8866 | 19.1075 | 38.5717 | 5.8926 | 30.2992 | 12.2762 | 15.3885 | 16.614 | 10.3799 | 46.2979 | 14.7242 | 530.9072
191 | 6.1669 | 47.0731 | 18.2878 | 8.749 | 38.0684 | 46.2779 | 37.34 | 9.922 | 17.2443 | 14.4795 | 20.8931 | 19.1124 | 46.5638 | 22.7992 | 3.2356 | 11.1142 | 33.2361 | 4.9891 | 26.541 | 13.1087 | 24.5705 | 21.0997 | 11.4275 | 44.2276 | 12.7867 | 559.314
192 | 6.2854 | 30.483 | 30.6368 | 6.7205 | 38.8241 | 43.4743 | 38.0126 | 11.4174 | 13.7244 | 11.0214 | 20.8962 | 25.71 | 52.3369 | 14.7294 | 3.8119 | 24.4908 | 35.1786 | 5.5893 | 28.8219 | 9.5716 | 23.0581 | 20.055 | 10.8017 | 44.5074 | 21.1239 | 571.2824
193 | 8.2351 | 34.0673 | 24.6817 | 6.3763 | 29.6651 | 51.0959 | 25.8692 | 11.2778 | 15.5174 | 12.8604 | 21.0197 | 22.9068 | 39.2609 | 13.9914 | 3.159 | 24.0227 | 38.7936 | 5.3993 | 26.3898 | 12.9475 | 21.2663 | 15.8631 | 12.0938 | 47.9636 | 20.5343 | 545.258
194 | 6.3831 | 43.891 | 25.3499 | 7.0904 | 28.588 | 43.7809 | 31.7193 | 8.0938 | 17.3882 | 12.5189 | 15.7919 | 23.0009 | 40.5832 | 25.1137 | 3.9234 | 24.5021 | 34.4573 | 5.7222 | 29.3957 | 11.7589 | 22.6996 | 11.8481 | 5.5739 | 45.0945 | 18.6216 | 542.8908
195 | 4.1092 | 45.6839 | 28.4286 | 8.1319 | 30.0179 | 45.7918 | 21.9447 | 10.7977 | 19.5254 | 13.307 | 14.088 | 25.7895 | 50.4204 | 23.8788 | 3.9731 | 17.3999 | 21.1016 | 3.7658 | 31.6954 | 11.8216 | 13.0798 | 16.4268 | 11.828 | 47.8826 | 18.8623 | 539.7517
196 | 4.2178 | 36.7336 | 21.6568 | 8.5827 | 30.2156 | 44.0184 | 33.4346 | 7.2966 | 14.1763 | 13.9647 | 21.5029 | 20.6011 | 47.667 | 22.9228 | 3.6864 | 26.628 | 30.2666 | 5.4297 | 26.0122 | 13.294 | 16.4976 | 15.0696 | 10.6671 | 57.745 | 18.3583 | 550.6453
197 | 6.0504 | 37.5281 | 31.6821 | 6.0691 | 22.0892 | 49.617 | 20.3477 | 8.159 | 17.8183 | 15.4519 | 20.67 | 18.028 | 28.711 | 22.5989 | 3.4385 | 21.8072 | 31.6138 | 4.3851 | 21.7145 | 13.683 | 21.6973 | 20.8079 | 10.864 | 26.1909 | 19.8396 | 500.8625
198 | 7.5168 | 46.0422 | 24.1534 | 5.0667 | 34.4756 | 49.7034 | 37.0726 | 5.3789 | 13.3055 | 11.7041 | 19.7035 | 25.6237 | 38.9323 | 22.6858 | 3.1559 | 24.7901 | 32.3083 | 5.5288 | 21.2513 | 11.3635 | 26.0647 | 20.8508 | 8.452 | 57.0669 | 21.6427 | 573.8393
199 | 6.7937 | 40.2595 | 25.8176 | 5.4351 | 35.2411 | 35.1011 | 36.2509 | 9.7774 | 19.532 | 15.7297 | 17.0362 | 15.8802 | 36.5666 | 21.1346 | 3.3739 | 27.4067 | 30.5412 | 5.6275 | 31.8202 | 12.2877 | 21.2732 | 21.7952 | 12.014 | 31.6351 | 20.5568 | 538.8873
200 | 7.2903 | 39.1112 | 30.1621 | 5.6135 | 38.7746 | 42.1281 | 29.6719 | 8.9626 | 19.5098 | 13.0564 | 14.5587 | 23.1635 | 50.6675 | 24.8159 | 2.6061 | 15.4458 | 33.352 | 5.6851 | 32.9132 | 12.4068 | 19.2642 | 20.9422 | 12.2244 | 56.4362 | 15.3256 | 574.0878
201 | 8.0023 | 29.7907 | 30.1165 | 7.3242 | 37.3825 | 48.5948 | 30.5022 | 9.8758 | 14.1492 | 11.594 | 18.7599 | 23.1319 | 42.0069 | 24.7903 | 2.996 | 14.3011 | 32.0696 | 4.791 | 22.3857 | 12.2407 | 21.9075 | 12.3605 | 9.6921 | 52.5385 | 20.0186 | 541.3226
202 | 6.385 | 44.904 | 21.922 | 5.5998 | 29.2226 | 45.1269 | 36.6056 | 11.7275 | 19.7709 | 16.0437 | 18.3336 | 20.7939 | 35.8493 | 18.9587 | 3.7044 | 19.0919 | 33.2137 | 4.8488 | 26.0635 | 11.9621 | 18.296 | 21.0339 | 9.3784 | 41.1521 | 21.3857 | 541.3738
203 | 7.527 | 36.7686 | 24.2842 | 7.3085 | 32.7968 | 43.6863 | 34.6468 | 8.8125 | 19.7517 | 13.1564 | 18.5893 | 20.7321 | 47.8023 | 17.3328 | 3.0271 | 19.0958 | 33.7739 | 3.795 | 28.6657 | 10.5237 | 22.3195 | 14.9373 | 11.8064 | 55.2316 | 15.5846 | 551.9558
204 | 6.4282 | 39.3483 | 30.1639 | 6.6071 | 37.2482 | 50.1566 | 32.998 | 10.2707 | 19.3696 | 12.538 | 20.1527 | 24.9426 | 45.6306 | 23.7167 | 3.9894 | 17.1584 | 38.303 | 4.9395 | 27.9554 | 13.9176 | 22.727 | 19.8409 | 7.8964 | 49.486 | 20.9623 | 586.7471
205 | 6.2918 | 38.3728 | 31.9651 | 6.0095 | 36.7454 | 44.8929 | 26.6795 | 7.7391 | 18.6527 | 14.2635 | 15.1816 | 13.3771 | 47.8289 | 22.2247 | 3.9826 | 20.2268 | 29.2206 | 4.0213 | 23.0691 | 7.5704 | 15.3661 | 19.4533 | 11.4395 | 47.4882 | 18.9129 | 530.9753
206 | 6.913 | 44.2316 | 30.7139 | 8.4606 | 36.6807 | 49.308 | 26.7183 | 6.5318 | 12.9465 | 14.8672 | 16.3783 | 21.9269 | 40.196 | 19.3284 | 3.1149 | 19.1192 | 21.1757 | 5.4642 | 22.7819 | 10.8938 | 25.9574 | 19.8174 | 8.6117 | 45.4456 | 18.2887 | 535.8719
207 | 7.5095 | 42.7682 | 20.1829 | 6.5662 | 34.9246 | 43.7944 | 33.8785 | 10.8183 | 17.5873 | 13.4852 | 21.132 | 17.0102 | 43.9003 | 25.5167 | 3.8627 | 23.819 | 20.4405 | 5.6323 | 23.3249 | 12.5035 | 21.7977 | 19.1 | 11.9161 | 36.2146 | 17.0081 | 534.6935
208 | 7.7514 | 47.6939 | 19.7757 | 8.6797 | 37.2792 | 43.3328 | 28.8517 | 8.1028 | 17.4061 | 12.971 | 18.5454 | 17.883 | 50.3139 | 25.6468 | 3.7883 | 24.2429 | 30.4776 | 5.7099 | 22.2438 | 13.1125 | 13.9457 | 11.866 | 10.8138 | 54.2555 | 18.2922 | 552.9814
209 | 7.2119 | 41.3803 | 28.0081 | 6.7439 | 30.2816 | 49.5854 | 31.7857 | 11.0893 | 19.492 | 13.3415 | 21.4914 | 24.1913 | 42.0952 | 23.1102 | 3.8106 | 19.41 | 38.8083 | 5.6258 | 27.0003 | 11.0259 | 21.3357 | 15.3075 | 11.8229 | 33.5477 | 21.697 | 559.1997
210 | 5.3758 | 37.8148 | 22.197 | 7.5014 | 31.6322 | 47.9599 | 35.8937 | 8.5922 | 18.877 | 16.2155 | 12.1224 | 25.1985 | 48.8797 | 25.4685 | 3.4822 | 17.7919 | 32.6893 | 4.7407 | 22.4748 | 10.9053 | 17.7677 | 14.2006 | 10.8857 | 37.6185 | 12.8729 | 529.158
211 | 8.2702 | 42.9156 | 22.0877 | 8.5918 | 33.0664 | 34.611 | 31.2581 | 9.7408 | 17.6529 | 16.3551 | 19.9678 | 21.5293 | 32.8489 | 24.7701 | 3.0568 | 21.9263 | 34.3278 | 4.6261 | 24.5357 | 12.3084 | 22.3309 | 17.7464 | 8.51 | 57.8882 | 17.8818 | 548.8041
212 | 7.126 | 36.4964 | 27.8044 | 6.0613 | 34.2734 | 52.5394 | 24.7178 | 8.3861 | 13.3949 | 14.5474 | 16.6518 | 19.9964 | 37.4331 | 21.2322 | 3.4728 | 24.2822 | 32.212 | 5.8729 | 27.0412 | 13.4756 | 23.0487 | 16.4857 | 8.1792 | 57.6217 | 16.4146 | 548.7672
213 | 7.5622 | 39.7061 | 26.4261 | 5.9507 | 38.6345 | 46.8299 | 35.7922 | 9.9778 | 13.1918 | 10.8002 | 14.3941 | 24.9772 | 41.8658 | 21.8218 | 2.6274 | 25.2143 | 26.0834 | 5.4982 | 31.1481 | 13.1497 | 19.805 | 19.3551 | 10.3263 | 50.3455 | 17.0107 | 558.4943
214 | 4.8346 | 28.8409 | 17.4383 | 6.4353 | 28.1216 | 33.2131 | 32.5825 | 9.8479 | 14.6664 | 12.3869 | 14.7123 | 21.4359 | 50.7812 | 15.5136 | 3.3472 | 23.0983 | 23.5503 | 4.8235 | 27.4903 | 10.9437 | 16.7726 | 19.7384 | 9.1965 | 32.6688 | 20.6092 | 483.0494
215 | 5.6759 | 40.2181 | 30.8596 | 8.7271 | 39.0854 | 32.7917 | 34.7186 | 7.0646 | 13.7351 | 12.0965 | 22.4197 | 23.0353 | 41.7983 | 20.735 | 2.7605 | 24.8733 | 26.2255 | 4.5198 | 32.5659 | 10.8561 | 24.3364 | 15.5191 | 9.5652 | 38.8691 | 14.678 | 537.7299
216 | 7.3279 | 25.587 | 31.5995 | 6.8953 | 33.3368 | 47.4506 | 31.8851 | 8.4986 | 18.2302 | 15.193 | 20.6884 | 15.4715 | 40.9676 | 17.4834 | 3.5883 | 27.608 | 28.19 | 4.0468 | 26.7944 | 12.5561 | 22.7784 | 18.0109 | 8.6501 | 50.5018 | 14.712 | 538.0519
217 | 8.2036 | 34.3546 | 26.8368 | 6.8958 | 36.1991 | 43.6837 | 26.5886 | 10.8279 | 15.5102 | 9.6496 | 11.1141 | 20.8911 | 41.1637 | 23.479 | 2.8539 | 25.1944 | 25.6647 | 5.4071 | 21.892 | 9.7963 | 18.9425 | 17.7405 | 12.2478 | 44.2297 | 11.6504 | 511.0171
218 | 7.5384 | 45.4173 | 25.6113 | 6.215 | 29.0554 | 46.1877 | 35.662 | 11.724 | 11.9954 | 16.6526 | 14.2134 | 15.0589 | 46.358 | 24.8527 | 3.5649 | 24.1955 | 32.2799 | 3.9929 | 25.7272 | 9.8446 | 16.2485 | 21.4172 | 9.5369 | 49.9694 | 18.5415 | 551.8606
219 | 4.6694 | 46.8434 | 19.8742 | 8.2357 | 36.5695 | 44.8582 | 35.3708 | 9.1616 | 12.1226 | 15.7086 | 22.3243 | 21.8249 | 54.9285 | 23.8698 | 3.6229 | 27.2609 | 29.6846 | 4.7779 | 27.7362 | 13.4849 | 22.1687 | 21.8493 | 11.9564 | 48.1174 | 12.5596 | 579.5802
220 | 3.9366 | 39.9359 | 21.4199 | 4.7255 | 27.8734 | 44.9911 | 34.7531 | 10.2447 | 16.623 | 12.7313 | 17.2352 | 24.2606 | 51.2755 | 24.0823 | 3.6377 | 22.3005 | 38.7362 | 5.0698 | 27.0984 | 8.8451 | 18.9911 | 16.9137 | 6.7302 | 54.5045 | 16.0923 | 553.0077
221 | 7.1434 | 36.5345 | 22.7607 | 8.654 | 35.7174 | 46.264 | 30.4436 | 10.3644 | 18.9805 | 11.3204 | 20.8515 | 23.208 | 40.0722 | 25.019 | 3.5531 | 25.5787 | 27.6116 | 5.999 | 31.774 | 13.782 | 22.2782 | 16.227 | 8.051 | 48.7937 | 15.7412 | 556.7231
222 | 6.4303 | 28.3089 | 25.6842 | 8.4702 | 22.0171 | 49.6611 | 17.1822 | 10.2141 | 19.6163 | 16.1268 | 19.1206 | 19.0717 | 50.446 | 25.3999 | 3.9235 | 19.7701 | 27.2442 | 4.7723 | 19.5486 | 11.7939 | 23.4052 | 19.9813 | 11.4091 | 47.6384 | 10.9846 | 518.2208
223 | 7.4691 | 38.9614 | 20.7372 | 7.6695 | 33.6821 | 34.0664 | 27.9621 | 9.6268 | 15.7753 | 14.506 | 21.4032 | 12.621 | 41.9496 | 24.533 | 2.7912 | 22.7913 | 27.138 | 4.7141 | 27.4632 | 13.7164 | 24.6093 | 19.9139 | 11.122 | 53.6535 | 19.3636 | 538.2393
224 | 5.9772 | 28.5622 | 19.4668 | 7.141 | 27.1106 | 37.1841 | 36.3286 | 10.8925 | 13.3181 | 12.6003 | 17.5561 | 23.0344 | 46.2121 | 20.3519 | 3.5987 | 25.7503 | 35.247 | 4.5599 | 28.9429 | 11.8659 | 21.1298 | 20.746 | 10.5191 | 37.1563 | 18.766 | 524.0179
225 | 6.1084 | 41.584 | 30.0381 | 7.0817 | 37.6057 | 45.8719 | 24.8686 | 7.9676 | 17.4407 | 15.3856 | 18.8142 | 21.7614 | 28.6296 | 22.7573 | 3.5446 | 23.6182 | 24.7444 | 5.8082 | 30.0326 | 10.5405 | 21.3966 | 21.3607 | 6.9061 | 41.8721 | 22.138 | 537.8767
226 | 7.4305 | 29.5983 | 24.2995 | 7.266 | 35.199 | 46.6449 | 32.5913 | 9.3876 | 18.6348 | 13.4599 | 18.9276 | 25.8761 | 34.0142 | 19.9634 | 3.844 | 18.1005 | 30.2679 | 5.2913 | 32.4499 | 13.8688 | 16.8621 | 21.7839 | 11.5764 | 50.2255 | 19.0505 | 546.614
227 | 7.7916 | 37.1671 | 21.826 | 7.0772 | 35.1564 | 40.9704 | 33.9079 | 5.9099 | 12.1382 | 12.8216 | 14.779 | 27.329 | 53.1456 | 20.5266 | 2.6168 | 19.0528 | 32.3223 | 5.2578 | 26.0361 | 7.7821 | 19.7175 | 19.8629 | 7.9292 | 40.7534 | 19.5814 | 531.4588
228 | 7.6919 | 46.6789 | 30.28 | 4.6566 | 33.1318 | 51.8483 | 33.3246 | 11.6013 | 14.9924 | 8.8526 | 14.7758 | 20.3619 | 47.8049 | 24.9228 | 3.8802 | 23.3673 | 34.3375 | 4.7132 | 32.3054 | 12.5943 | 15.6455 | 21.4542 | 11.6687 | 46.4709 | 20.6933 | 578.0544
229 | 5.9465 | 41.5066 | 33.5105 | 7.8695 | 27.6044 | 45.2421 | 29.0945 | 9.0478 | 17.0144 | 14.7036 | 21.2635 | 17.1677 | 46.5032 | 23.3362 | 3.8761 | 22.571 | 37.3951 | 5.4777 | 30.1931 | 13.638 | 25.6925 | 18.4956 | 11.0694 | 46.2076 | 18.8175 | 573.2441
230 | 5.857 | 33.5463 | 25.2219 | 8.6856 | 31.8261 | 35.6277 | 27.4097 | 11.8826 | 17.5479 | 16.3309 | 17.4184 | 27.9508 | 39.854 | 24.6974 | 3.0013 | 26.3906 | 34.6117 | 5.8921 | 31.8372 | 13.4982 | 23.6338 | 18.7851 | 12.2441 | 48.1779 | 15.5689 | 557.4972
231 | 5.5017 | 39.7927 | 24.7655 | 7.7105 | 25.0995 | 33.3867 | 31.3521 | 11.2455 | 16.562 | 15.8922 | 15.3975 | 18.4496 | 38.3325 | 17.8484 | 2.919 | 25.8623 | 26.5559 | 5.1518 | 24.0752 | 10.8251 | 21.9461 | 19.9206 | 11.5204 | 34.3809 | 16.9093 | 501.4032
232 | 7.0983 | 47.9775 | 30.5482 | 5.1091 | 37.5438 | 46.007 | 32.3517 | 7.0668 | 19.9594 | 14.6563 | 21.9232 | 24.9312 | 43.2789 | 25.7359 | 3.8727 | 14.5586 | 31.2412 | 4.9107 | 28.7511 | 12.3005 | 25.4828 | 15.7249 | 11.6569 | 51.1771 | 18.7064 | 582.5701
233 | 6.311 | 30.7957 | 24.8577 | 8.5777 | 32.4724 | 50.1484 | 27.7695 | 11.6679 | 19.0049 | 16.4811 | 20.4181 | 25.8447 | 41.0717 | 21.5952 | 2.3309 | 16.2146 | 37.9147 | 5.9244 | 29.1227 | 12.1363 | 23.6393 | 20.2221 | 8.8294 | 58.055 | 17.1522 | 568.5577
234 | 7.1373 | 30.5927 | 18.8929 | 6.3287 | 25.3731 | 27.0117 | 31.6874 | 9.8616 | 18.5125 | 15.6524 | 11.5843 | 22.6629 | 43.439 | 14.9064 | 3.0953 | 23.31 | 36.9936 | 5.2689 | 29.0145 | 8.5187 | 17.5844 | 13.9192 | 9.2291 | 57.6564 | 18.3134 | 506.5463
235 | 7.5871 | 43.4789 | 20.3589 | 6.8285 | 36.7557 | 30.3554 | 31.1778 | 7.9227 | 16.9791 | 11.1209 | 19.5406 | 26.2262 | 45.8488 | 23.5215 | 2.5891 | 12.993 | 32.8636 | 5.8985 | 17.8761 | 13.6054 | 23.2825 | 19.8621 | 11.3873 | 46.5444 | 20.4636 | 535.0678
236 | 7.8447 | 39.6648 | 30.483 | 7.6246 | 28.668 | 45.8708 | 31.7011 | 11.1263 | 16.5686 | 14.8308 | 19.4188 | 21.9745 | 43.7186 | 17.8881 | 3.6382 | 18.0147 | 36.9398 | 4.0339 | 17.5532 | 7.4276 | 23.172 | 13.0092 | 9.9225 | 41.501 | 19.46 | 532.0548
237 | 6.1165 | 47.2413 | 27.0289 | 4.5913 | 30.3916 | 39.392 | 26.1245 | 8.5184 | 19.8476 | 12.8701 | 15.7548 | 21.4186 | 51.7512 | 14.7027 | 3.3455 | 17.2001 | 38.7027 | 4.5546 | 28.6376 | 9.3855 | 16.0378 | 18.9672 | 9.4944 | 31.977 | 12.5567 | 516.6087
238 | 6.326 | 33.017 | 26.3388 | 7.7447 | 31.4606 | 47.9705 | 36.5885 | 10.5093 | 19.3772 | 14.8619 | 18.661 | 9.99 | 52.7444 | 19.9542 | 2.9682 | 22.2316 | 35.9945 | 5.6368 | 31.5778 | 12.0808 | 23.231 | 19.8775 | 8.3804 | 58.3429 | 15.9457 | 571.8112
239 | 7.5695 | 30.3214 | 32.3932 | 6.7956 | 37.4658 | 43.1374 | 24.7127 | 7.6063 | 13.4103 | 16.1659 | 22.3857 | 17.0684 | 34.7378 | 24.502 | 2.6655 | 22.2666 | 26.1273 | 5.5721 | 28.2441 | 11.8961 | 23.6779 | 20.199 | 11.149 | 48.4761 | 17.718 | 536.2638
240 | 4.9433 | 32.5642 | 14.2707 | 6.9945 | 27.9907 | 40.6143 | 31.6481 | 11.171 | 18.289 | 13.9866 | 14.8518 | 23.002 | 43.5475 | 18.6221 | 3.4341 | 19.2633 | 34.8221 | 3.4757 | 21.3492 | 13.9861 | 22.4074 | 17.6871 | 11.1649 | 57.2225 | 21.5747 | 528.8828
241 | 4.5862 | 45.0605 | 26.9479 | 7.2931 | 25.5288 | 43.8298 | 33.3634 | 8.8286 | 18.1508 | 10.5774 | 12.8107 | 25.4644 | 50.133 | 19.3381 | 2.9965 | 21.7875 | 30.9073 | 4.8914 | 31.111 | 12.8515 | 25.4068 | 19.3204 | 8.9231 | 52.0058 | 14.1904 | 556.3044
242 | 7.6957 | 44.0837 | 31.7702 | 6.8981 | 27.1543 | 42.4815 | 27.1231 | 10.4494 | 13.8578 | 12.3246 | 16.2381 | 26.8709 | 32.5342 | 17.5896 | 3.8185 | 25.127 | 32.4547 | 5.1664 | 25.8781 | 10.9535 | 25.7082 | 19.5841 | 12.2508 | 50.8195 | 16.0629 | 544.8948
243 | 5.8106 | 26.8007 | 32.2758 | 7.1153 | 32.8061 | 45.7157 | 26.849 | 9.3424 | 19.7132 | 14.7648 | 17.3063 | 23.4446 | 40.8426 | 25.4681 | 3.8971 | 22.5247 | 30.5852 | 4.6385 | 30.7125 | 11.0523 | 22.6421 | 17.1067 | 11.1537 | 37.7409 | 14.6939 | 535.0027
244 | 5.1215 | 41.9264 | 28.8812 | 6.2763 | 23.083 | 41.8322 | 26.4092 | 11.7178 | 16.1088 | 12.9496 | 17.0411 | 23.6913 | 53.0812 | 23.7117 | 3.2782 | 24.4091 | 27.5555 | 5.4937 | 29.6318 | 13.3519 | 26.0762 | 19.5835 | 10.4497 | 55.9941 | 15.8977 | 563.5524
245 | 7.3898 | 41.4316 | 33.5069 | 7.7632 | 27.1285 | 34.1216 | 21.7809 | 5.7147 | 14.2086 | 8.2083 | 12.7861 | 21.6054 | 38.4834 | 24.9292 | 3.642 | 22.5444 | 36.819 | 5.9948 | 20.7434 | 12.5825 | 20.7408 | 13.6906 | 7.7098 | 43.1709 | 10.9979 | 497.6943
246 | 8.3943 | 29.2966 | 29.1545 | 7.3744 | 20.0217 | 39.8205 | 38.5717 | 7.443 | 18.2081 | 13.0746 | 20.8911 | 18.3047 | 33.5474 | 19.9178 | 3.3489 | 16.1496 | 25.8632 | 4.3907 | 28.7373 | 13.5 | 20.4831 | 19.1845 | 11.6551 | 46.0409 | 21.0547 | 514.4283
247 | 5.0211 | 37.1788 | 28.703 | 6.9376 | 34.1663 | 41.662 | 29.552 | 10.2598 | 17.9904 | 16.4176 | 13.7263 | 20.2484 | 40.5192 | 19.1299 | 3.4729 | 25.7355 | 28.0614 | 4.9284 | 25.5246 | 13.6145 | 22.3824 | 21.1509 | 8.2597 | 44.8573 | 18.2046 | 537.7049
248 | 7.6554 | 26.8775 | 28.8966 | 8.288 | 33.4464 | 37.7425 | 38.3591 | 8.7743 | 19.8698 | 12.4786 | 19.1451 | 28.052 | 35.2693 | 25.0368 | 3.7274 | 16.9309 | 38.176 | 5.7937 | 30.4707 | 12.1321 | 22.5684 | 21.7797 | 9.8859 | 44.7825 | 19.6456 | 555.7844
249 | 5.2544 | 48.8145 | 31.3173 | 7.1983 | 32.9474 | 30.6402 | 29.6983 | 6.6753 | 14.8841 | 12.8231 | 17.5148 | 25.395 | 43.1124 | 23.4367 | 3.2706 | 22.1402 | 36.4388 | 3.7617 | 24.2524 | 12.6177 | 22.9711 | 21.7092 | 9.2664 | 46.1888 | 16.6043 | 548.9332
250 | 8.1793 | 34.9764 | 27.4208 | 5.9006 | 21.6169 | 37.4917 | 30.7791 | 9.3886 | 14.8196 | 15.3527 | 20.6535 | 27.2442 | 29.475 | 25.7484 | 2.7518 | 21.7028 | 32.3374 | 4.4382 | 29.5612 | 12.5515 | 22.0628 | 21.5376 | 7.7236 | 33.7482 | 21.7679 | 519.2302
251 | 4.3271 | 41.7995 | 30.4277 | 6.1089 | 30.0951 | 52.2281 | 19.0147 | 10.6597 | 17.8258 | 12.196 | 12.5923 | 13.2952 | 40.3803 | 22.4246 | 3.4158 | 23.5373 | 24.7783 | 4.988 | 30.8602 | 12.118 | 24.1363 | 19.9317 | 12.2846 | 54.0701 | 18.269 | 541.7644
252 | 7.1532 | 35.3066 | 24.4458 | 7.0114 | 32.7446 | 34.6495 | 17.1579 | 9.902 | 18.5371 | 10.8534 | 19.9937 | 24.5867 | 27.8064 | 24.0624 | 2.9767 | 25.7559 | 25.7925 | 4.3009 | 21.7473 | 9.7481 | 19.8799 | 17.3368 | 11.8554 | 40.4559 | 19.3638 | 493.4239
253 | 7.4392 | 39.3719 | 33.272 | 6.2171 | 28.346 | 48.7024 | 35.1584 | 10.8667 | 18.0237 | 14.3487 | 17.3374 | 28.1154 | 39.6762 | 15.3085 | 3.0587 | 27.2785 | 28.5972 | 4.7297 | 28.8471 | 13.1223 | 12.3381 | 21.4046 | 11.7346 | 53.1565 | 21.6464 | 568.0973
254 | 6.8695 | 39.4074 | 28.8117 | 7.8001 | 27.3805 | 28.8126 | 38.1294 | 6.1569 | 12.7723 | 15.4494 | 17.6954 | 26.562 | 43.7137 | 22.1476 | 2.2492 | 16.6888 | 34.1192 | 4.4943 | 28.8763 | 13.0086 | 18.8382 | 21.6351 | 9.6111 | 49.1878 | 19.6943 | 540.1113
255 | 8.057 | 31.7861 | 23.071 | 8.0915 | 30.3962 | 44.7499 | 36.8104 | 9.3041 | 17.0355 | 14.2478 | 14.9006 | 25.8718 | 35.8993 | 18.6901 | 3.5547 | 27.1772 | 35.8348 | 5.5323 | 26.578 | 11.2803 | 20.5831 | 17.7951 | 10.3548 | 46.4552 | 15.0322 | 539.0891
256 | 6.4365 | 30.4373 | 32.5925 | 7.6803 | 36.3523 | 45.1873 | 35.9058 | 9.3702 | 18.7498 | 11.3497 | 13.4899 | 23.7749 | 35.7364 | 21.7521 | 2.9054 | 25.1178 | 25.8526 | 5.679 | 29.451 | 12.2078 | 22.3265 | 18.1887 | 7.1865 | 41.6984 | 21.909 | 541.3379
257 | 7.5686 | 32.6478 | 25.7165 | 7.271 | 37.1856 | 46.0006 | 37.8462 | 9.9157 | 17.8737 | 7.3215 | 15.1513 | 23.6808 | 51.4193 | 19.9534 | 2.2776 | 13.7882 | 25.0654 | 5.8536 | 24.3196 | 11.7017 | 25.3514 | 19.9494 | 11.8666 | 57.3963 | 19.4491 | 556.571
258 | 6.3267 | 30.5873 | 23.5296 | 8.4691 | 33.4782 | 37.567 | 33.6785 | 8.4779 | 16.8774 | 13.2134 | 15.8152 | 26.5704 | 41.6758 | 16.6437 | 2.7272 | 17.8628 | 38.6724 | 5.0967 | 31.6495 | 11.0686 | 15.7977 | 20.2361 | 12.3026 | 39.1157 | 17.0854 | 524.525
259 | 6.3561 | 34.4748 | 24.6479 | 8.2137 | 29.7534 | 39.2797 | 25.1852 | 9.9839 | 19.8323 | 14.8743 | 19.2793 | 23.6237 | 35.5789 | 25.5695 | 3.6521 | 24.1064 | 39.1779 | 4.6955 | 28.5662 | 9.5179 | 18.1514 | 15.4326 | 8.5624 | 33.8177 | 18.3384 | 520.6712
260 | 6.625 | 46.9841 | 18.417 | 5.3972 | 30.5939 | 42.2066 | 37.0222 | 11.4941 | 19.5411 | 12.4111 | 19.7085 | 13.2884 | 41.4481 | 17.3835 | 2.6629 | 24.0151 | 33.9296 | 5.4547 | 19.5342 | 13.8154 | 25.1431 | 11.8482 | 10.1627 | 33.3896 | 19.8549 | 522.3312
261 | 5.7427 | 39.6626 | 30.0065 | 5.5346 | 23.5261 | 50.7764 | 32.9347 | 8.1301 | 17.2827 | 14.4942 | 16.7364 | 25.4917 | 39.3994 | 24.0994 | 3.3833 | 24.1854 | 32.4777 | 4.9603 | 23.2539 | 13.2023 | 22.0658 | 20.3848 | 10.5623 | 50.98 | 14.6961 | 553.9695
262 | 6.4704 | 44.4822 | 16.4406 | 5.607 | 37.7431 | 48.9485 | 29.6348 | 9.6697 | 13.9063 | 12.9338 | 19.2145 | 23.0304 | 49.4905 | 22.9974 | 2.3419 | 27.4993 | 32.5989 | 5.0806 | 31.0025 | 13.0745 | 21.2662 | 17.9551 | 9.6968 | 50.1176 | 21.1399 | 572.3426
263 | 3.7874 | 36.1898 | 22.695 | 8.4458 | 24.5117 | 39.8914 | 27.4531 | 7.6543 | 18.8487 | 14.2996 | 18.8878 | 25.2836 | 40.5105 | 15.7483 | 3.3606 | 13.187 | 37.5476 | 3.6744 | 25.7147 | 7.5356 | 21.1956 | 14.7668 | 11.9279 | 53.6061 | 19.9627 | 516.6859
264 | 5.9769 | 42.6526 | 29.9019 | 5.3218 | 27.8023 | 50.3815 | 31.6218 | 9.5872 | 17.9127 | 12.8329 | 16.9242 | 22.3908 | 51.7419 | 23.938 | 3.7932 | 25.3716 | 25.8739 | 5.4263 | 27.8394 | 10.0981 | 24.2878 | 21.7634 | 8.0548 | 54.8924 | 21.2262 | 577.6138
265 | 7.8255 | 42.2458 | 17.3022 | 8.3162 | 31.4124 | 49.4901 | 32.0577 | 10.118 | 16.5589 | 14.1448 | 19.4298 | 21.336 | 45.2483 | 25.8507 | 3.8367 | 22.0411 | 34.6472 | 5.265 | 19.8711 | 12.0432 | 24.7028 | 21.4893 | 7.7418 | 48.833 | 9.9588 | 551.7665
266 | 6.2609 | 39.2698 | 27.2464 | 8.1547 | 25.6658 | 46.0624 | 22.012 | 10.3062 | 14.5207 | 15.656 | 18.5919 | 28.0094 | 49.8801 | 24.7353 | 3.8792 | 19.7005 | 32.6532 | 4.8395 | 18.02 | 10.583 | 19.4433 | 19.3798 | 11.5307 | 50.5393 | 19.0708 | 546.011
267 | 8.0257 | 42.6594 | 25.0733 | 5.8193 | 27.1892 | 41.2009 | 26.8949 | 7.5329 | 19.3008 | 8.8686 | 18.0729 | 19.9358 | 43.8531 | 14.7628 | 2.9295 | 16.9933 | 20.5285 | 4.9659 | 27.0365 | 13.9298 | 19.1679 | 17.0601 | 8.8326 | 33.059 | 21.2495 | 494.9423
268 | 4.9178 | 34.0458 | 27.6438 | 5.9251 | 33.3041 | 43.8746 | 32.9155 | 9.3108 | 19.1727 | 11.727 | 15.256 | 13.6258 | 44.605 | 22.3369 | 3.7145 | 18.3228 | 33.7793 | 5.6185 | 31.0594 | 11.4223 | 24.995 | 15.3412 | 7.9167 | 56.794 | 14.7513 | 542.3759
269 | 6.4931 | 36.9237 | 27.711 | 6.9667 | 31.2027 | 40.2715 | 24.0817 | 9.325 | 14.4565 | 12.1471 | 16.8433 | 27.0341 | 39.1608 | 25.6043 | 2.281 | 22.1701 | 28.3153 | 5.4387 | 24.943 | 10.1066 | 25.6841 | 16.2312 | 10.855 | 56.3455 | 21.8723 | 542.4641
270 | 5.7881 | 37.0413 | 29.1412 | 6.9282 | 24.3832 | 42.9074 | 33.5372 | 8.1713 | 17.575 | 10.2372 | 19.0481 | 27.5399 | 41.3037 | 17.5746 | 3.6736 | 26.9082 | 29.7115 | 5.8137 | 32.0868 | 9.4082 | 19.3254 | 21.4725 | 9.8459 | 35.4059 | 18.9194 | 533.7476
271 | 6.8584 | 26.1957 | 24.4558 | 6.9237 | 33.8935 | 42.1337 | 36.5292 | 8.8178 | 17.7154 | 15.1053 | 20.7983 | 22.105 | 49.5868 | 22.2885 | 2.6492 | 24.1363 | 27.856 | 4.4101 | 24.7729 | 13.556 | 14.586 | 19.7274 | 7.8389 | 54.9663 | 14.4852 | 542.3914
272 | 7.2881 | 31.0002 | 28.6232 | 6.5918 | 22.4095 | 39.3664 | 29.0862 | 11.1265 | 18.6574 | 13.8708 | 19.0702 | 24.0166 | 41.8841 | 25.995 | 2.0806 | 24.47 | 26.4014 | 5.4413 | 19.7411 | 10.7717 | 23.3648 | 21.486 | 9.9252 | 49.0549 | 21.7123 | 533.4353
273 | 6.4672 | 42.0228 | 27.4062 | 6.7159 | 31.9835 | 42.0927 | 36.5164 | 8.7076 | 19.4818 | 8.6153 | 14.1868 | 24.5725 | 46.7096 | 22.0238 | 3.7287 | 18.2894 | 29.1749 | 4.4666 | 22.9541 | 13.9221 | 17.0864 | 14.57 | 8.028 | 54.107 | 18.462 | 542.2915
274 | 5.3201 | 42.8333 | 22.978 | 8.442 | 38.2635 | 48.8417 | 22.1925 | 10.0365 | 18.9426 | 10.9018 | 22.0797 | 21.2652 | 37.3127 | 24.7694 | 3.6812 | 24.8611 | 30.6866 | 5.6497 | 25.2542 | 11.2656 | 24.3404 | 17.1915 | 9.9651 | 59.3825 | 13.5842 | 560.0409
275 | 6.7621 | 28.8702 | 31.6676 | 4.8778 | 39.0596 | 44.3259 | 34.2567 | 8.9917 | 14.9291 | 10.388 | 19.8957 | 15.1528 | 52.2432 | 21.3816 | 3.6906 | 23.156 | 34.8209 | 5.7797 | 29.0994 | 10.9455 | 16.3034 | 12.9447 | 10.9579 | 48.9768 | 20.8522 | 550.3293
276 | 7.6539 | 25.0354 | 31.1878 | 6.0337 | 30.4071 | 40.0357 | 32.547 | 10.9576 | 16.0736 | 16.2434 | 21.1114 | 19.6996 | 29.2909 | 23.8414 | 3.7147 | 22.7644 | 27.6707 | 5.8561 | 26.0607 | 11.1432 | 24.002 | 15.0208 | 10.1517 | 44.2121 | 21.7865 | 522.5013
277 | 4.2159 | 39.5741 | 30.5961 | 8.1701 | 26.6276 | 36.8148 | 30.3833 | 5.962 | 16.7332 | 12.4525 | 17.9039 | 14.8804 | 51.2976 | 21.588 | 3.6399 | 21.0286 | 33.4937 | 3.5295 | 17.8934 | 13.2761 | 14.759 | 19.2837 | 8.4479 | 52.0926 | 14.4036 | 519.0475
278 | 7.7192 | 46.2881 | 15.5779 | 7.7913 | 29.5864 | 46.7337 | 23.9175 | 10.4256 | 18.1421 | 14.7146 | 14.5668 | 25.8104 | 45.303 | 17.2622 | 3.072 | 25.5117 | 34.8816 | 5.5303 | 17.9311 | 11.1595 | 18.2798 | 20.405 | 9.6141 | 55.793 | 22.3163 | 548.3332
279 | 4.4358 | 48.9117 | 26.8383 | 4.7694 | 27.1544 | 46.7838 | 38.0057 | 9.8289 | 18.4218 | 14.7239 | 18.338 | 22.0849 | 25.8041 | 22.3758 | 2.5873 | 15.5761 | 35.721 | 5.8423 | 26.3409 | 11.4561 | 18.2346 | 20.9709 | 11.7895 | 54.3912 | 19.7773 | 551.1637
280 | 8.37 | 42.3139 | 15.8597 | 7.1716 | 24.4823 | 51.262 | 36.9684 | 10.7331 | 16.7652 | 11.7057 | 21.7674 | 16.3106 | 35.2228 | 25.4153 | 3.6557 | 24.7379 | 22.4048 | 5.7063 | 30.9682 | 12.1601 | 23.7442 | 21.2162 | 9.936 | 45.6931 | 13.7579 | 538.3284
281 | 5.9764 | 41.336 | 24.461 | 7.5042 | 32.7862 | 42.7776 | 35.474 | 8.6134 | 16.3713 | 14.2165 | 18.4137 | 16.8681 | 34.5194 | 25.634 | 3.4752 | 19.2413 | 25.7689 | 4.8859 | 27.5213 | 8.9908 | 23.5074 | 15.5972 | 9.4845 | 35.3992 | 18.4224 | 517.246
282 | 7.4309 | 29.295 | 26.0106 | 7.1336 | 25.0164 | 40.7241 | 33.767 | 11.7158 | 13.8645 | 14.3115 | 18.8531 | 23.332 | 29.4367 | 22.33 | 3.76 | 20.9911 | 27.3458 | 4.6248 | 23.2052 | 13.7574 | 21.1524 | 21.5262 | 10.6228 | 27.9181 | 21.1327 | 499.2579
283 | 7.5534 | 42.5025 | 22.6419 | 8.5091 | 29.458 | 50.8315 | 34.6678 | 10.8482 | 19.5493 | 10.7137 | 15.0553 | 24.2054 | 33.9283 | 23.4337 | 3.3009 | 17.5101 | 35.1292 | 4.4422 | 21.6837 | 13.783 | 22.6695 | 20.1567 | 8.7473 | 54.8531 | 19.0666 | 555.2406
284 | 7.2381 | 42.9938 | 24.1897 | 5.4902 | 27.2477 | 45.1818 | 26.9799 | 9.1861 | 15.1967 | 13.5394 | 10.2839 | 28.4175 | 42.0895 | 25.7565 | 3.5059 | 20.7898 | 35.7406 | 5.1022 | 29.6388 | 10.8256 | 25.7493 | 12.9454 | 10.2546 | 57.3086 | 20.429 | 556.0806
285 | 8.0152 | 43.776 | 32.9092 | 8.3564 | 30.0781 | 45.3607 | 35.9093 | 8.2215 | 16.2057 | 15.5728 | 13.3048 | 21.0613 | 51.0983 | 22.4826 | 3.83 | 20.6524 | 24.3957 | 3.6592 | 29.5764 | 13.3065 | 17.8438 | 21.8381 | 10.7699 | 48.1558 | 16.8835 | 563.2632
286 | 7.1603 | 40.7809 | 31.0527 | 8.4337 | 36.6844 | 52.244 | 29.3706 | 7.1683 | 17.3471 | 15.5225 | 16.9086 | 17.0376 | 51.0381 | 19.5416 | 3.6408 | 18.4204 | 34.1871 | 4.4542 | 28.6049 | 11.9012 | 21.7985 | 19.1484 | 11.4478 | 34.5911 | 13.7537 | 552.2384
287 | 7.009 | 32.0973 | 29.694 | 7.68 | 34.6461 | 31.7741 | 32.7669 | 6.5109 | 19.0829 | 13.7151 | 15.2917 | 26.6493 | 48.5334 | 22.3094 | 3.2517 | 20.553 | 31.8463 | 5.7942 | 24.63 | 13.9788 | 25.3768 | 20.551 | 9.4004 | 48.9576 | 20.6092 | 552.7089
288 | 7.5446 | 30.857 | 24.0791 | 4.6665 | 19.3461 | 42.2639 | 28.8031 | 9.5059 | 17.0728 | 14.1344 | 20.5794 | 22.5684 | 35.1326 | 18.7901 | 2.9367 | 17.2414 | 29.2804 | 4.5843 | 29.2266 | 13.768 | 15.255 | 20.3606 | 10.8233 | 41.4671 | 14.7773 | 495.0645
289 | 6.2896 | 39.5265 | 30.1205 | 7.0418 | 31.6572 | 41.6224 | 37.6213 | 9.0472 | 15.5435 | 14.1959 | 17.2991 | 28.3374 | 43.7652 | 25.383 | 2.8491 | 21.4433 | 32.0867 | 5.065 | 30.3257 | 10.2656 | 22.6736 | 21.9263 | 10.5318 | 40.6269 | 16.2412 | 561.4857
290 | 7.9583 | 35.5928 | 22.182 | 6.8426 | 34.5202 | 38.7786 | 33.3144 | 10.4317 | 19.0599 | 10.851 | 18.483 | 24.7954 | 46.7622 | 23.9147 | 3.5842 | 18.4543 | 30.6336 | 4.8693 | 27.961 | 13.5775 | 21.7533 | 14.7578 | 8.6505 | 44.5617 | 19.4756 | 541.7655
291 | 7.1385 | 42.7107 | 30.724 | 7.6375 | 33.6345 | 44.5142 | 27.1637 | 10.0502 | 13.8096 | 12.4335 | 11.0561 | 26.9146 | 31.6471 | 25.3713 | 3.7866 | 25.5793 | 38.4497 | 5.9309 | 27.282 | 13.9816 | 23.8912 | 16.8093 | 7.5916 | 49.1912 | 17.1593 | 554.4583
292 | 8.2015 | 36.1453 | 32.3137 | 8.6487 | 23.6651 | 49.9264 | 35.6342 | 10.1915 | 18.7266 | 15.7382 | 14.6308 | 22.4025 | 38.3386 | 23.247 | 3.7207 | 22.7217 | 22.2248 | 5.7436 | 32.0141 | 12.344 | 25.1558 | 18.7207 | 11.709 | 38.3525 | 21.7564 | 552.2732
293 | 6.3391 | 30.1742 | 23.2943 | 6.4087 | 32.0144 | 38.1581 | 37.2287 | 8.6711 | 13.8092 | 10.5214 | 20.277 | 17.7154 | 42.1108 | 24.6624 | 3.7271 | 26.4805 | 36.1453 | 5.1904 | 32.5919 | 11.4656 | 13.2018 | 19.4719 | 6.9791 | 30.7542 | 19.0894 | 516.4818
294 | 5.9125 | 47.7865 | 17.9047 | 8.3279 | 34.5601 | 43.6504 | 24.6718 | 4.1959 | 14.3804 | 14.2283 | 18.8091 | 24.648 | 53.7312 | 16.7129 | 3.7587 | 26.7822 | 38.8237 | 5.478 | 29.6453 | 10.4783 | 25.7194 | 21.2786 | 9.9613 | 57.1725 | 15.8998 | 574.5175
295 | 6.7775 | 41.2845 | 29.0027 | 8.028 | 23.1492 | 50.1754 | 33.1394 | 9.3609 | 14.6747 | 8.8797 | 19.0676 | 19.056 | 38.5067 | 24.6676 | 3.9591 | 27.5144 | 28.7749 | 5.9021 | 28.5361 | 8.9296 | 24.4628 | 20.3332 | 11.5735 | 31.2362 | 21.1839 | 538.1756
296 | 5.9263 | 46.2149 | 23.8315 | 5.2912 | 33.4284 | 42.4647 | 32.3681 | 11.174 | 12.3643 | 14.4585 | 16.4471 | 23.8972 | 35.3666 | 22.8979 | 3.9935 | 25.1739 | 34.6201 | 5.9495 | 27.0907 | 11.1926 | 17.1946 | 20.8558 | 9.5406 | 46.6144 | 18.0446 | 546.401
297 | 8.2553 | 39.9843 | 22.0118 | 7.5527 | 29.7904 | 47.7933 | 31.9403 | 11.0094 | 18.5164 | 15.6918 | 13.9407 | 26.0165 | 50.7955 | 23.4269 | 3.3677 | 17.53 | 24.2558 | 5.9313 | 28.7039 | 13.2953 | 24.5502 | 16.6914 | 10.6538 | 54.6452 | 19.7992 | 566.149
298 | 7.5254 | 40.2442 | 32.8927 | 7.182 | 32.8245 | 51.5629 | 34.8472 | 10.7913 | 19.0129 | 10.7687 | 17.2992 | 24.9268 | 53.117 | 20.168 | 3.6267 | 18.9839 | 33.9189 | 3.4766 | 26.3856 | 10.9315 | 23.7165 | 17.4289 | 11.2691 | 43.8091 | 16.5468 | 573.2566
299 | 8.0368 | 23.7863 | 32.1621 | 7.6698 | 35.3614 | 51.1684 | 28.9259 | 7.0651 | 11.7826 | 16.3635 | 19.3832 | 27.6796 | 25.6606 | 24.1874 | 3.148 | 27.7906 | 36.1175 | 4.5547 | 32.1989 | 11.4858 | 25.0825 | 14.64 | 10.8151 | 52.7145 | 21.6866 | 559.4669
300 | 6.22 | 47.7041 | 29.1794 | 7.2949 | 27.1186 | 50.5248 | 26.4413 | 10.235 | 15.3336 | 10.454 | 18.6164 | 23.0402 | 40.5229 | 16.3687 | 3.7015 | 21.8565 | 34.0795 | 3.203 | 27.0884 | 13.8799 | 19.4168 | 15.9548 | 8.529 | 47.4931 | 12.3531 | 536.6096
301 | 7.0673 | 27.3449 | 29.5453 | 5.9838 | 37.4315 | 35.4471 | 32.6351 | 8.6508 | 15.8763 | 9.6539 | 14.9971 | 22.9123 | 39.5412 | 23.2249 | 3.6943 | 22.1448 | 36.6565 | 5.7821 | 23.865 | 13.3421 | 20.3271 | 20.2738 | 7.5158 | 50.0392 | 19.8717 | 533.8239
302 | 5.8927 | 41.2832 | 30.2972 | 7.026 | 25.362 | 24.9907 | 32.6387 | 8.4534 | 18.0689 | 12.1845 | 15.7936 | 26.5431 | 42.5035 | 25.351 | 3.8555 | 17.4334 | 32.9329 | 5.5579 | 24.7318 | 13.7425 | 16.7967 | 16.6519 | 8.7446 | 45.005 | 19.1965 | 521.0372
303 | 4.6926 | 35.7664 | 25.3292 | 7.8627 | 32.4428 | 49.0028 | 28.0848 | 9.5807 | 11.9815 | 13.663 | 16.5292 | 23.5353 | 50.2032 | 23.2492 | 3.4885 | 24.3512 | 37.9428 | 4.5129 | 30.3644 | 13.9342 | 20.8518 | 19.4338 | 10.7447 | 53.1125 | 13.2051 | 563.8651
304 | 6.9979 | 38.907 | 17.3053 | 8.3345 | 29.5844 | 43.0042 | 31.7129 | 9.0188 | 17.5012 | 15.3451 | 21.4518 | 22.6934 | 35.0917 | 19.2137 | 3.382 | 20.0853 | 33.7225 | 5.1757 | 20.6587 | 13.8334 | 21.7217 | 16.0969 | 10.2787 | 37.4857 | 15.6539 | 514.2564
305 | 6.9494 | 46.5854 | 26.0832 | 7.5715 | 24.7215 | 48.7592 | 34.2421 | 9.5261 | 18.0359 | 10.1802 | 16.2061 | 20.9025 | 42.3013 | 25.5664 | 3.6633 | 27.5151 | 31.9242 | 5.3124 | 19.616 | 12.8305 | 17.0768 | 20.0545 | 12.4627 | 35.2985 | 13.2029 | 536.588
306 | 6.1358 | 35.5535 | 30.5362 | 8.1711 | 31.1271 | 50.512 | 28.5884 | 9.7521 | 11.8145 | 15.4699 | 18.7893 | 23.3332 | 55.1832 | 17.3739 | 2.3171 | 24.2994 | 37.2603 | 4.0288 | 22.1988 | 11.274 | 18.6637 | 17.1997 | 11.097 | 50.6163 | 15.9864 | 557.2819
307 | 5.4984 | 34.0454 | 17.5883 | 5.8428 | 27.7003 | 47.988 | 22.665 | 10.5118 | 14.5436 | 15.4198 | 20.5282 | 24.2176 | 33.666 | 24.5729 | 2.5008 | 16.2286 | 37.5153 | 3.5593 | 22.9037 | 11.4314 | 22.7707 | 21.8712 | 11.1935 | 40.7278 | 14.9041 | 510.3944
308 | 7.6422 | 33.3034 | 25.7097 | 8.1931 | 30.852 | 52.1529 | 17.4958 | 9.7921 | 17.1165 | 10.4887 | 22.3602 | 20.5077 | 51.4771 | 25.2178 | 3.0754 | 17.4869 | 32.4589 | 5.8963 | 30.9507 | 12.3348 | 19.2966 | 17.6168 | 10.5305 | 49.4596 | 15.9713 | 547.3871
309 | 6.6165 | 42.4285 | 29.5849 | 7.1953 | 36.929 | 35.9978 | 24.8942 | 9.1897 | 19.5792 | 13.2901 | 18.8509 | 23.2913 | 48.4542 | 15.3882 | 3.597 | 20.4718 | 25.2546 | 4.6786 | 31.5653 | 12.2063 | 21.6908 | 20.943 | 7.8974 | 32.7806 | 19.1728 | 531.948
310 | 8.0532 | 44.0052 | 32.8382 | 8.5919 | 31.4715 | 39.0346 | 25.9978 | 8.7467 | 17.9021 | 9.4035 | 18.5966 | 28.3604 | 42.7758 | 23.9074 | 2.2562 | 18.8795 | 31.4322 | 3.7349 | 32.7353 | 12.077 | 18.4333 | 21.4381 | 11.2593 | 48.9608 | 20.6995 | 561.591
311 | 4.0123 | 43.7405 | 29.6055 | 6.8042 | 29.0566 | 49.4584 | 39.0428 | 9.5594 | 16.3565 | 15.5337 | 18.5075 | 18.0254 | 46.369 | 25.4251 | 3.982 | 20.0179 | 37.1233 | 3.6757 | 31.3882 | 12.8438 | 24.4774 | 14.5828 | 9.3729 | 44.9964 | 21.6536 | 575.6112
312 | 5.89 | 45.1305 | 33.5871 | 8.473 | 28.1747 | 44.6903 | 28.0722 | 8.8721 | 19.2749 | 14.4497 | 21.0391 | 19.4424 | 46.9197 | 21.8685 | 2.9211 | 24.1521 | 22.0487 | 5.4492 | 25.3817 | 8.6066 | 17.1664 | 19.3901 | 11.9299 | 48.5153 | 14.7642 | 546.2096
313 | 6.0448 | 38.5715 | 26.2005 | 7.9401 | 30.5211 | 52.1505 | 36.9235 | 11.5207 | 15.4315 | 16.1918 | 15.5129 | 25.4775 | 43.8139 | 22.8692 | 2.6822 | 18.0262 | 26.8482 | 5.5654 | 29.9078 | 13.4357 | 25.7245 | 20.7058 | 11.4287 | 53.1876 | 17.3304 | 574.0119
314 | 7.1235 | 48.7526 | 23.3863 | 6.7936 | 32.089 | 46.3718 | 25.2665 | 9.886 | 19.9708 | 15.1753 | 21.0392 | 26.712 | 36.63 | 16.3947 | 3.6054 | 27.071 | 35.0607 | 5.4382 | 23.0399 | 12.9004 | 25.8636 | 21.4614 | 10.8002 | 42.458 | 14.416 | 557.7063
315 | 6.1928 | 31.1732 | 27.8937 | 7.8034 | 18.3096 | 36.0535 | 37.5648 | 9.4051 | 19.953 | 12.0708 | 18.2496 | 21.9647 | 47.0188 | 17.5477 | 3.187 | 25.9637 | 32.1363 | 4.7498 | 32.5935 | 12.9934 | 24.1134 | 19.4058 | 12.3123 | 48.3404 | 21.6435 | 548.6399
316 | 5.9991 | 43.1985 | 33.3105 | 7.4072 | 22.0823 | 50.8046 | 34.8466 | 8.2969 | 19.0664 | 15.857 | 15.8576 | 27.7542 | 33.1672 | 20.1768 | 3.9119 | 16.7537 | 28.6187 | 4.5334 | 26.2549 | 13.5792 | 24.8357 | 18.4941 | 8.3326 | 45.279 | 13.857 | 542.2752
317 | 6.0291 | 48.3449 | 29.1965 | 6.3948 | 23.5926 | 32.6026 | 31.6161 | 7.0382 | 19.7738 | 11.6869 | 15.2894 | 20.8838 | 54.1462 | 20.1523 | 3.5684 | 20.9926 | 33.2114 | 3.7027 | 29.9233 | 12.7047 | 23.5187 | 17.5591 | 10.5824 | 47.4864 | 14.2192 | 544.2163
318 | 8.2358 | 44.9984 | 24.7683 | 7.7887 | 18.9134 | 49.5913 | 33.5496 | 10.1374 | 15.3736 | 13.1248 | 18.0515 | 27.0773 | 37.6255 | 25.0046 | 3.7143 | 25.3577 | 33.5527 | 4.5816 | 30.059 | 11.9782 | 22.7588 | 18.6816 | 12.3228 | 56.5406 | 21.9456 | 575.733
319 | 5.8364 | 46.9161 | 28.108 | 5.5135 | 26.1999 | 39.5042 | 26.659 | 9.6572 | 13.729 | 10.9028 | 20.8093 | 27.6353 | 40.0947 | 16.4938 | 3.0332 | 17.0865 | 38.3105 | 5.3382 | 28.4119 | 12.8055 | 26.4691 | 20.5185 | 12.1863 | 56.6753 | 18.4393 | 557.3336
320 | 8.2582 | 31.4424 | 28.0249 | 8.3979 | 34.8593 | 49.7264 | 36.0703 | 7.5498 | 18.2423 | 13.8901 | 13.2099 | 19.8126 | 51.8192 | 24.8065 | 3.6633 | 19.164 | 36.0096 | 4.5564 | 28.5195 | 12.4067 | 21.4981 | 18.8892 | 11.7457 | 46.2143 | 17.5917 | 566.3682
321 | 4.6436 | 35.3884 | 33.3254 | 8.2391 | 22.4138 | 45.9933 | 35.3546 | 9.5668 | 17.5096 | 14.14 | 15.7706 | 19.6341 | 38.1016 | 22.4855 | 3.5829 | 16.3611 | 34.113 | 4.8137 | 32.3406 | 10.5791 | 25.7238 | 21.5359 | 12.2711 | 29.2563 | 18.619 | 531.7627
322 | 6.048 | 32.6092 | 17.2854 | 8.6825 | 38.4208 | 41.5424 | 32.5166 | 9.6544 | 19.7793 | 14.5022 | 18.8304 | 19.8403 | 45.0689 | 22.4843 | 3.2586 | 24.4841 | 28.6089 | 4.4365 | 32.2634 | 12.126 | 20.0802 | 20.633 | 9.0608 | 55.5725 | 17.6404 | 555.4293
323 | 6.9027 | 43.0257 | 26.7584 | 5.6539 | 32.0579 | 37.9081 | 24.7151 | 11.1664 | 17.4991 | 11.6956 | 20.004 | 25.6887 | 53.0392 | 24.1018 | 3.7577 | 22.2942 | 35.0135 | 5.8799 | 22.7451 | 9.4153 | 26.5872 | 14.069 | 9.8995 | 56.0262 | 13.3783 | 559.2825
324 | 7.9311 | 47.9464 | 26.1777 | 8.5882 | 35.9123 | 36.099 | 31.7038 | 6.1118 | 14.8743 | 13.9253 | 11.6233 | 24.2993 | 29.071 | 19.7114 | 3.5249 | 25.8935 | 36.06 | 4.7715 | 27.284 | 9.8542 | 13.1438 | 21.5155 | 9.3004 | 40.4507 | 18.6969 | 524.4703
325 | 7.6055 | 29.7238 | 30.6515 | 7.8089 | 27.752 | 40.2915 | 34.3289 | 7.7964 | 18.621 | 14.9682 | 21.1384 | 23.3241 | 45.3663 | 23.3204 | 3.3671 | 24.7667 | 27.2478 | 5.796 | 31.0432 | 10.6007 | 18.9675 | 20.8301 | 8.4602 | 38.8126 | 17.3737 | 539.9624
326 | 5.0666 | 47.3428 | 21.8668 | 6.1864 | 38.3371 | 48.4499 | 31.0267 | 8.991 | 19.3831 | 11.9211 | 19.9145 | 28.4599 | 41.3786 | 15.0706 | 3.7263 | 22.952 | 30.18 | 5.9639 | 27.9346 | 9.3919 | 19.3499 | 14.9225 | 10.2923 | 36.3261 | 15.8219 | 540.2567
327 | 4.1319 | 43.2443 | 33.2096 | 8.781 | 33.6894 | 25.4242 | 38.6904 | 10.242 | 12.9242 | 16.0565 | 13.3344 | 21.2135 | 48.858 | 22.7121 | 3.5359 | 15.3161 | 36.7647 | 4.8616 | 32.9474 | 11.6768 | 19.9182 | 14.3527 | 11.0391 | 29.6016 | 21.3262 | 533.8518
328 | 7.2482 | 42.5318 | 25.9542 | 5.7084 | 35.7898 | 47.9347 | 24.3614 | 6.5593 | 19.4655 | 14.7232 | 18.5697 | 17.1956 | 33.5494 | 18.4937 | 3.1662 | 18.2997 | 29.0252 | 5.5456 | 23.5607 | 7.8005 | 19.5767 | 21.8449 | 8.2013 | 43.4047 | 13.0821 | 511.5922
329 | 5.9321 | 39.186 | 25.2244 | 5.8943 | 33.1654 | 36.1389 | 29.049 | 9.2928 | 18.3133 | 16.3504 | 22.2827 | 18.3186 | 39.172 | 24.1645 | 3.205 | 20.7167 | 33.6194 | 4.8348 | 24.0994 | 12.8115 | 23.4593 | 16.7405 | 9.7706 | 52.3364 | 14.4782 | 538.5561
330 | 6.3583 | 33.87 | 24.0066 | 7.7254 | 36.3106 | 49.4908 | 31.7952 | 9.2432 | 16.2198 | 15.05 | 9.9422 | 17.8595 | 47.1929 | 24.5637 | 2.8023 | 24.2283 | 38.1716 | 5.0481 | 29.8665 | 12.9053 | 20.5563 | 16.4554 | 7.1033 | 47.7642 | 13.4824 | 548.0115
331 | 6.8731 | 32.6289 | 31.4205 | 8.5018 | 38.4874 | 39.825 | 32.6246 | 9.2776 | 14.9842 | 16.6237 | 15.1914 | 20.5051 | 42.0963 | 18.6894 | 3.3312 | 27.0433 | 25.135 | 5.961 | 27.3252 | 13.3758 | 21.1781 | 19.3698 | 10.6678 | 38.5597 | 19.265 | 538.9405
332 | 7.7568 | 35.6373 | 31.9047 | 8.5733 | 27.8159 | 29.5845 | 36.5123 | 9.6796 | 17.107 | 13.7103 | 20.8086 | 26.6978 | 43.8277 | 24.1301 | 2.5447 | 19.9235 | 34.5519 | 5.5786 | 26.2427 | 13.4525 | 18.2567 | 20.3559 | 8.8048 | 56.8473 | 17.4917 | 557.7962
333 | 8.0732 | 21.3761 | 27.0763 | 6.355 | 31.829 | 47.0239 | 20.071 | 11.8317 | 16.2885 | 15.0004 | 14.4851 | 23.7676 | 49.9607 | 24.3731 | 3.2582 | 18.7381 | 33.3733 | 3.95 | 32.1039 | 13.7482 | 21.2892 | 12.5568 | 8.2849 | 26.2159 | 18.3634 | 509.3936
334 | 6.4305 | 32.5946 | 22.5873 | 6.0059 | 23.8246 | 51.1054 | 33.463 | 8.4438 | 18.1846 | 14.6816 | 11.6787 | 26.6496 | 46.8651 | 24.569 | 3.167 | 25.1376 | 26.6391 | 5.667 | 32.8898 | 8.7421 | 22.7113 | 16.9541 | 9.0375 | 40.524 | 11.0514 | 529.6047
335 | 6.444 | 45.0762 | 29.7413 | 7.485 | 28.4737 | 44.9443 | 27.9437 | 9.2685 | 19.7511 | 16.4406 | 17.8661 | 26.4183 | 34.7576 | 24.6376 | 2.721 | 21.6841 | 38.3406 | 4.2193 | 28.9479 | 9.2981 | 20.6674 | 20.0381 | 11.7756 | 37.5519 | 20.8954 | 555.3875
336 | 6.8951 | 37.1541 | 23.344 | 8.1836 | 39.3423 | 37.9484 | 35.535 | 11.381 | 19.2571 | 12.8132 | 16.1021 | 27.8219 | 50.9322 | 24.1941 | 2.493 | 14.0095 | 25.8411 | 5.8749 | 20.6886 | 9.5636 | 22.1833 | 17.1513 | 10.8237 | 40.27 | 17.6334 | 537.4364
337 | 8.0117 | 37.6857 | 29.9143 | 6.4183 | 38.3447 | 33.977 | 30.2883 | 9.004 | 13.4367 | 9.6424 | 18.7325 | 25.44 | 43.9871 | 23.9339 | 3.363 | 21.1444 | 25.9253 | 5.5403 | 26.8803 | 11.3336 | 13.8821 | 21.4599 | 9.8812 | 45.7166 | 15.3727 | 529.3162
338 | 7.3977 | 31.6052 | 32.0707 | 7.023 | 33.709 | 47.8517 | 33.5667 | 11.2001 | 14.249 | 10.5663 | 11.9688 | 15.2619 | 45.687 | 13.395 | 2.972 | 26.7613 | 35.1547 | 4.9832 | 20.7918 | 12.0255 | 25.123 | 19.285 | 6.9289 | 42.4078 | 20.2099 | 532.1951
339 | 6.2043 | 33.4285 | 31.9154 | 6.9971 | 37.586 | 43.5692 | 36.9594 | 11.7548 | 15.6567 | 15.1117 | 20.6712 | 24.6192 | 43.786 | 22.9595 | 3.7816 | 20.1116 | 33.8408 | 5.721 | 26.5826 | 7.6021 | 23.3862 | 20.7203 | 12.1247 | 33.4103 | 14.41 | 552.9102
340 | 7.4558 | 37.5739 | 28.945 | 7.1869 | 30.7872 | 45.6461 | 35.0757 | 11.0887 | 16.5863 | 12.008 | 17.727 | 13.0102 | 48.5522 | 21.9971 | 2.3968 | 15.3815 | 23.9914 | 5.1013 | 31.862 | 11.0646 | 19.0583 | 21.0586 | 7.7186 | 58.4856 | 18.6076 | 548.3666
341 | 6.481 | 38.1752 | 24.0017 | 8.606 | 36.4861 | 39.8611 | 29.8006 | 7.5427 | 10.3706 | 16.7534 | 20.4448 | 23.6162 | 28.3902 | 18.8141 | 2.7657 | 24.243 | 32.0521 | 5.8799 | 21.8288 | 10.9428 | 19.537 | 18.2454 | 12.0682 | 52.7898 | 18.6411 | 528.3374
342 | 5.8087 | 38.1633 | 23.4746 | 7.9487 | 26.0855 | 34.79 | 33.0966 | 7.7829 | 10.6523 | 11.992 | 18.5332 | 24.9382 | 50.9882 | 20.0432 | 3.6923 | 25.1503 | 32.9177 | 4.3258 | 18.6225 | 13.8402 | 19.8957 | 18.7455 | 7.5211 | 53.6448 | 21.7477 | 534.401
343 | 5.0215 | 23.2609 | 28.8309 | 4.6743 | 34.9909 | 43.7065 | 34.2466 | 7.9479 | 17.1107 | 10.7642 | 20.6237 | 24.7045 | 48.5528 | 22.554 | 3.9278 | 22.9167 | 25.7425 | 4.8494 | 26.0526 | 11.6875 | 17.6756 | 14.747 | 9.8254 | 49.9934 | 21.389 | 535.7964
344 | 7.5099 | 48.3343 | 27.7703 | 8.357 | 35.2123 | 46.246 | 31.9979 | 9.6015 | 13.5485 | 16.3006 | 22.2225 | 28.0615 | 47.4119 | 25.9407 | 2.6514 | 19.9949 | 31.6899 | 5.0664 | 25.7252 | 11.5607 | 20.7848 | 16.8145 | 10.722 | 43.5932 | 21.4482 | 578.566
345 | 6.6531 | 46.8911 | 17.0021 | 8.1082 | 31.7829 | 46.3038 | 37.3933 | 9.3829 | 15.9435 | 10.8022 | 22.4648 | 23.6752 | 22.032 | 22.041 | 2.7784 | 13.6933 | 23.7667 | 3.8967 | 32.3448 | 10.7368 | 21.0811 | 18.9716 | 6.909 | 54.372 | 14.065 | 523.0914
346 | 6.9373 | 32.5653 | 33.1908 | 6.4895 | 36.1851 | 42.6884 | 29.0211 | 9.3409 | 16.2273 | 15.347 | 20.4276 | 21.3697 | 29.5606 | 21.3032 | 3.6284 | 19.2909 | 31.1986 | 4.3047 | 31.6102 | 11.4685 | 25.3553 | 21.1983 | 8.6346 | 45.6482 | 19.5346 | 542.526
347 | 6.9588 | 46.1156 | 21.7783 | 7.2659 | 25.3597 | 31.1162 | 35.9735 | 6.9545 | 16.4517 | 7.8692 | 12.3743 | 21.2382 | 51.3998 | 23.2929 | 3.7156 | 27.9368 | 31.1474 | 5.7033 | 31.1812 | 12.1978 | 18.6161 | 14.6405 | 10.4808 | 50.6373 | 17.3453 | 537.7504
348 | 5.5904 | 30.2523 | 27.0106 | 7.8311 | 27.5076 | 30.2936 | 37.4868 | 7.3656 | 14.0901 | 12.4373 | 20.8673 | 17.2198 | 47.3645 | 15.0559 | 3.5399 | 26.538 | 33.8756 | 4.0823 | 25.9627 | 9.7067 | 13.4501 | 21.9889 | 12.0549 | 41.3803 | 16.5676 | 509.5199
349 | 6.6178 | 36.3531 | 23.0789 | 7.9406 | 37.1822 | 33.9389 | 18.078 | 9.4642 | 17.0758 | 15.9102 | 19.2545 | 26.5372 | 45.7635 | 24.5476 | 3.2315 | 19.6456 | 28.0907 | 5.84 | 29.5162 | 9.3301 | 26.5702 | 20.5227 | 11.3391 | 57.2951 | 16.1699 | 549.2935
350 | 6.1233 | 38.3111 | 25.7606 | 6.7513 | 35.0469 | 46.6076 | 27.8477 | 11.3856 | 15.5585 | 14.1984 | 18.6614 | 18.5856 | 53.0943 | 17.9407 | 3.8861 | 24.1917 | 32.4609 | 5.9972 | 32.8562 | 11.0713 | 23.2544 | 21.4044 | 8.5361 | 53.5835 | 11.0104 | 564.1251
351 | 5.7785 | 30.5352 | 26.299 | 8.2202 | 38.0477 | 45.2663 | 26.296 | 8.0042 | 17.885 | 13.0066 | 17.3242 | 20.0404 | 24.7238 | 19.4277 | 2.6771 | 19.8717 | 35.2522 | 4.7892 | 30.6372 | 13.9194 | 17.3806 | 17.0728 | 10.6756 | 42.5258 | 19.5886 | 515.2452
352 | 7.6095 | 47.1245 | 27.3728 | 5.5241 | 23.3851 | 46.883 | 28.4415 | 8.8283 | 19.2038 | 12.8374 | 13.9811 | 23.1105 | 49.1425 | 23.3774 | 3.9391 | 16.6976 | 34.0914 | 5.2012 | 32.8775 | 12.3413 | 21.6634 | 18.0742 | 8.5767 | 55.6579 | 20.7016 | 566.6436
353 | 6.9853 | 30.5576 | 30.7908 | 7.7406 | 36.0332 | 45.9206 | 28.617 | 11.7305 | 18.8246 | 8.437 | 16.0285 | 22.9747 | 51.2912 | 18.6275 | 3.1322 | 25.7906 | 38.034 | 3.2767 | 26.4359 | 12.4118 | 23.2341 | 20.5675 | 11.4259 | 52.2716 | 13.3056 | 564.4448
354 | 8.1743 | 47.7182 | 24.7873 | 7.8761 | 28.0065 | 37.8732 | 24.1686 | 10.9943 | 16.3062 | 13.6211 | 20.8391 | 22.3469 | 42.5079 | 18.2721 | 3.5661 | 24.6843 | 30.3755 | 5.6704 | 29.5291 | 11.6504 | 23.9864 | 12.9463 | 6.2196 | 57.1339 | 15.6991 | 544.9529
355 | 6.8548 | 45.9048 | 19.4927 | 8.1464 | 32.0185 | 40.1178 | 25.3519 | 11.495 | 19.7658 | 16.4654 | 17.6766 | 21.0174 | 41.6105 | 21.304 | 3.9242 | 22.9116 | 37.9094 | 5.7287 | 30.9323 | 13.464 | 23.7068 | 16.5038 | 10.4395 | 37.011 | 17.5883 | 547.3411
356 | 6.5688 | 28.8482 | 29.2409 | 6.1303 | 24.3499 | 43.1053 | 22.8659 | 6.08 | 19.3636 | 16.6341 | 15.7115 | 26.8238 | 48.2659 | 22.032 | 3.6316 | 19.6021 | 33.8301 | 4.0025 | 28.2943 | 10.6345 | 22.989 | 21.7127 | 8.2454 | 57.9128 | 17.3072 | 544.1824
357 | 7.3077 | 45.1104 | 31.0771 | 5.9971 | 24.6438 | 49.9755 | 38.807 | 8.0864 | 15.8095 | 16.2171 | 21.6038 | 25.0322 | 33.1931 | 20.2298 | 3.6576 | 22.9202 | 33.7843 | 3.9728 | 22.7799 | 10.4695 | 25.6045 | 12.755 | 9.3375 | 39.0561 | 21.3792 | 548.807
358 | 7.0111 | 38.6103 | 30.8899 | 8.2318 | 34.0744 | 40.4146 | 23.7628 | 10.8094 | 16.8991 | 11.171 | 15.3249 | 18.3207 | 42.6408 | 23.3056 | 3.6435 | 21.7633 | 23.3267 | 5.8339 | 19.2516 | 11.1692 | 21.5692 | 16.868 | 11.4331 | 44.4748 | 16.9892 | 517.7889
359 | 5.8207 | 44.6486 | 22.3161 | 7.9875 | 39.114 | 36.2823 | 25.9827 | 7.8608 | 19.085 | 11.737 | 22.4392 | 21.2174 | 38.504 | 24.987 | 3.162 | 19.6665 | 32.4627 | 5.9892 | 31.788 | 12.5311 | 16.3224 | 18.823 | 11.9208 | 52.3522 | 21.2271 | 554.2274
360 | 5.5872 | 37.373 | 26.2006 | 8.236 | 24.6674 | 49.5131 | 26.3055 | 9.9937 | 14.237 | 13.4596 | 15.3925 | 27.67 | 52.0702 | 24.5369 | 3.7476 | 24.1836 | 32.4896 | 5.5285 | 28.4439 | 12.2365 | 25.8773 | 15.379 | 10.3256 | 37.4682 | 19.3649 | 550.2873
361 | 7.861 | 30.9841 | 19.7145 | 8.5254 | 37.6408 | 51.8652 | 34.1303 | 11.4497 | 11.9282 | 15.4627 | 16.8701 | 25.2255 | 45.2594 | 21.731 | 3.9237 | 26.8845 | 36.8292 | 5.2807 | 26.5023 | 12.2181 | 19.5565 | 14.6258 | 8.7386 | 52.0054 | 13.773 | 558.9858
362 | 8.2927 | 32.1435 | 20.8156 | 7.8792 | 16.9421 | 35.779 | 25.8168 | 9.0301 | 19.2111 | 13.0124 | 21.4957 | 15.2846 | 49.1686 | 24.6518 | 3.9698 | 18.4926 | 35.636 | 5.5233 | 32.3685 | 12.4828 | 21.2475 | 13.5102 | 6.6112 | 50.7811 | 16.2766 | 516.4227
363 | 6.0197 | 28.0831 | 25.6833 | 6.4484 | 25.5173 | 43.6568 | 38.629 | 11.2586 | 12.1886 | 10.9319 | 12.6434 | 16.3462 | 37.793 | 25.0553 | 2.8555 | 18.5819 | 25.3716 | 5.3972 | 29.4061 | 10.2621 | 19.6352 | 20.6764 | 10.0525 | 56.8257 | 19.6434 | 518.9625
364 | 6.9891 | 48.3432 | 28.702 | 7.7535 | 33.2422 | 40.9033 | 35.3048 | 6.1748 | 16.9771 | 12.8277 | 15.2964 | 20.1857 | 36.3861 | 20.203 | 3.7633 | 21.8281 | 34.3411 | 4.5303 | 26.9118 | 11.2294 | 19.7764 | 18.3043 | 10.2104 | 44.6906 | 16.2583 | 541.133
365 | 7.9196 | 35.1152 | 26.927 | 6.2913 | 26.1263 | 50.1313 | 26.5209 | 6.4668 | 14.0101 | 13.5654 | 14.4418 | 20.4879 | 50.0413 | 23.247 | 2.7746 | 20.8349 | 37.975 | 3.2379 | 20.7117 | 13.8403 | 14.3108 | 20.594 | 9.8899 | 48.7604 | 19.8468 | 534.068
366 | 6.4676 | 42.1666 | 30.577 | 6.0094 | 32.0613 | 52.9228 | 36.8 | 10.0975 | 19.6784 | 12.1528 | 11.8918 | 24.5647 | 45.3677 | 23.805 | 2.2717 | 23.0316 | 32.4567 | 3.9776 | 29.1007 | 12.8325 | 19.1969 | 15.1122 | 9.8648 | 51.9854 | 15.8747 | 570.2675
367 | 5.9004 | 41.0061 | 32.2051 | 6.5672 | 34.328 | 35.0531 | 32.3359 | 8.773 | 15.8025 | 11.6903 | 18.9858 | 14.7238 | 43.9051 | 17.3602 | 3.8504 | 26.8131 | 36.313 | 5.0665 | 31.7686 | 10.9608 | 18.8767 | 21.095 | 11.9879 | 33.0485 | 21.8742 | 540.2912
368 | 7.0685 | 41.718 | 29.9382 | 8.1231 | 37.8525 | 46.3707 | 32.15 | 9.2639 | 19.1879 | 11.5098 | 12.5521 | 25.2629 | 41.24 | 24.4859 | 3.0612 | 17.224 | 34.3631 | 5.6503 | 30.5863 | 10.1695 | 25.4959 | 21.4927 | 10.8373 | 52.8798 | 18.6775 | 577.1613
369 | 5.5174 | 38.3169 | 26.5967 | 8.6909 | 37.2907 | 49.1716 | 32.4186 | 9.2932 | 13.1009 | 10.2921 | 13.0665 | 26.5625 | 48.0396 | 20.3613 | 3.7763 | 23.128 | 30.2947 | 4.075 | 26.7414 | 12.3397 | 15.7137 | 12.8859 | 10.492 | 47.9552 | 10.6276 | 536.7482
370 | 6.576 | 48.0141 | 30.1572 | 5.0185 | 38.3051 | 39.2184 | 16.8577 | 9.3468 | 19.3213 | 14.2493 | 15.5927 | 22.0126 | 49.2537 | 20.375 | 2.2833 | 25.5092 | 38.2215 | 5.2171 | 26.6684 | 12.7914 | 20.486 | 18.9719 | 7.0809 | 48.5919 | 11.2407 | 551.3604
371 | 3.4996 | 37.757 | 31.684 | 5.8358 | 33.4988 | 49.0921 | 33.3237 | 10.1761 | 12.6249 | 11.7997 | 18.5944 | 26.422 | 31.3088 | 16.707 | 3.6878 | 22.9478 | 29.4622 | 5.7545 | 29.5912 | 11.7073 | 23.467 | 21.8073 | 10.9634 | 41.8523 | 17.3088 | 540.8734
372 | 6.5737 | 40.2947 | 25.8174 | 5.5274 | 27.5918 | 51.5484 | 37.8331 | 9.7746 | 19.274 | 16.4368 | 17.4845 | 28.1967 | 47.9104 | 23.5724 | 3.8301 | 11.1842 | 28.2802 | 5.3837 | 30.3256 | 11.1737 | 22.368 | 21.4482 | 9.6876 | 44.7394 | 18.5249 | 564.7813
373 | 6.9954 | 44.3727 | 22.7659 | 6.3242 | 27.3654 | 43.4733 | 37.8783 | 8.3942 | 10.8898 | 13.235 | 21.0707 | 22.4289 | 28.6527 | 20.9311 | 3.4648 | 26.572 | 36.8508 | 5.5712 | 28.6935 | 13.4802 | 19.6404 | 19.1998 | 7.7118 | 50.3891 | 22.0785 | 548.4297
374 | 5.432 | 39.1 | 29.8448 | 6.5136 | 36.5169 | 47.0171 | 33.7503 | 7.0005 | 19.1078 | 16.3804 | 19.1063 | 24.4949 | 41.9488 | 21.2775 | 3.0315 | 19.8804 | 34.5161 | 5.8697 | 24.098 | 7.4958 | 25.5516 | 18.603 | 11.4405 | 51.9838 | 20.9254 | 570.8866
375 | 7.7984 | 49.6032 | 33.2041 | 6.0679 | 30.2041 | 30.9791 | 28.8717 | 10.5844 | 15.0361 | 15.084 | 12.7721 | 27.7245 | 28.6211 | 15.5432 | 3.9631 | 18.9376 | 30.596 | 5.6499 | 32.6771 | 13.5951 | 19.3233 | 18.769 | 9.7965 | 48.88 | 15.9531 | 530.2345
376 | 7.2749 | 27.693 | 28.4761 | 4.8144 | 28.7351 | 44.6714 | 31.4079 | 8.5659 | 13.9064 | 9.1857 | 20.7262 | 26.1069 | 50.9494 | 19.651 | 3.2984 | 21.7545 | 37.4966 | 5.8221 | 26.0834 | 12.7657 | 21.061 | 21.8943 | 8.6811 | 51.969 | 16.4868 | 549.477
377 | 6.7207 | 39.9988 | 20.7675 | 5.7293 | 34.8733 | 36.6676 | 34.7067 | 7.7495 | 13.4844 | 11.1902 | 16.0576 | 27.2832 | 44.5926 | 24.8777 | 2.5984 | 20.4272 | 23.7185 | 5.0068 | 24.3675 | 10.4943 | 24.8697 | 14.8783 | 10.6292 | 41.0057 | 19.1355 | 521.8303
378 | 4.3805 | 47.0943 | 21.0152 | 8.2846 | 31.7127 | 47.3426 | 30.5759 | 11.9001 | 12.208 | 14.2574 | 16.7444 | 23.5413 | 48.5935 | 25.3285 | 3.3528 | 19.0357 | 16.9922 | 5.7025 | 32.8373 | 9.6845 | 23.4879 | 21.5069 | 8.9936 | 40.9986 | 18.2808 | 543.8517
379 | 6.4205 | 41.1353 | 33.0759 | 7.0302 | 33.9811 | 45.0272 | 21.9466 | 11.6738 | 12.9675 | 11.5646 | 18.3253 | 26.2431 | 43.731 | 19.0513 | 3.2856 | 17.4095 | 31.147 | 4.3489 | 31.0813 | 12.6948 | 22.7172 | 21.7896 | 10.5806 | 56.3344 | 12.2029 | 555.7651
380 | 4.2023 | 30.498 | 23.0641 | 8.0948 | 34.4414 | 45.2032 | 34.4269 | 6.2251 | 19.2944 | 15.6553 | 20.9823 | 15.7037 | 43.1533 | 23.3744 | 3.524 | 23.4769 | 31.9034 | 5.0582 | 32.4157 | 9.9523 | 20.9768 | 17.4245 | 11.31 | 50.5787 | 17.9837 | 548.9231
381 | 5.2231 | 32.1295 | 21.7937 | 8.7081 | 26.0641 | 50.7796 | 35.874 | 11.5895 | 17.6487 | 15.1382 | 21.6509 | 25.3911 | 36.7215 | 20.5558 | 3.9391 | 24.3983 | 19.148 | 3.7352 | 28.0822 | 9.9098 | 25.0783 | 20.5201 | 12.2038 | 57.9772 | 21.8334 | 556.0931
382 | 4.4867 | 23.6213 | 28.8215 | 6.9154 | 25.1776 | 46.1894 | 23.8843 | 10.0386 | 19.9404 | 15.0594 | 16.8393 | 25.7395 | 51.4246 | 22.1146 | 3.9004 | 18.096 | 26.4293 | 5.9459 | 24.0262 | 10.7211 | 26.2205 | 19.4009 | 11.9373 | 58.8238 | 20.0742 | 545.8283
383 | 5.1459 | 44.1768 | 23.2872 | 8.5343 | 26.2741 | 46.9459 | 36.0229 | 8.1481 | 12.99 | 10.8283 | 12.7113 | 19.4637 | 40.9715 | 24.3229 | 2.9953 | 22.7309 | 38.6848 | 4.2547 | 21.3399 | 11.1831 | 18.5254 | 20.9323 | 10.9501 | 38.5999 | 18.765 | 528.7843
384 | 6.6084 | 35.7366 | 24.3251 | 7.0647 | 33.1058 | 38.498 | 30.5716 | 5.0013 | 18.9316 | 12.8478 | 22.4672 | 25.473 | 50.9481 | 20.2573 | 3.5627 | 21.1013 | 34.0943 | 3.3586 | 25.1325 | 13.4848 | 15.1743 | 20.9886 | 9.0932 | 43.842 | 20.6028 | 542.2716
385 | 4.8585 | 33.227 | 30.5392 | 8.0898 | 34.3533 | 36.2083 | 31.1859 | 8.359 | 11.8943 | 14.9246 | 11.815 | 25.3977 | 28.8684 | 20.448 | 3.2122 | 25.2949 | 33.3425 | 4.4004 | 17.1237 | 13.9954 | 22.531 | 17.3076 | 9.9056 | 44.1076 | 14.2243 | 505.6141
386 | 6.9777 | 39.0302 | 26.6116 | 8.36 | 33.9691 | 44.8918 | 32.3693 | 11.095 | 18.6986 | 13.3154 | 22.427 | 20.7884 | 53.4885 | 20.608 | 3.9203 | 17.8866 | 28.0838 | 5.6169 | 23.986 | 13.0471 | 23.2647 | 14.9312 | 11.2337 | 49.8125 | 14.4458 | 558.8593
387 | 7.458 | 23.9043 | 27.7741 | 8.0069 | 19.2642 | 41.7113 | 35.7588 | 10.275 | 17.9011 | 12.9747 | 17.3998 | 20.362 | 35.4577 | 17.0905 | 2.7622 | 22.9861 | 25.8297 | 5.9838 | 23.1052 | 13.512 | 25.3955 | 19.0535 | 10.5146 | 47.9099 | 16.8173 | 509.2081
388 | 7.6376 | 36.1644 | 28.1781 | 5.9493 | 31.9195 | 44.2819 | 35.44 | 9.9599 | 18.5022 | 13.5207 | 20.0792 | 24.0058 | 52.6502 | 21.4621 | 3.9729 | 26.7188 | 35.4613 | 5.6363 | 31.543 | 12.9818 | 18.208 | 21.2637 | 9.9836 | 48.1133 | 22.0657 | 585.6992
389 | 8.193 | 28.3268 | 24.4262 | 7.5703 | 18.0148 | 36.5273 | 25.8708 | 6.9804 | 17.6559 | 16.6814 | 16.7036 | 24.54 | 30.1073 | 21.5893 | 2.4208 | 27.9664 | 32.5285 | 5.8111 | 22.0008 | 11.621 | 15.6431 | 16.6562 | 9.115 | 54.9074 | 20.8598 | 502.7172
390 | 6.8708 | 44.4156 | 22.3262 | 8.1835 | 33.3191 | 43.1096 | 36.1896 | 6.4045 | 16.7338 | 14.3376 | 17.1039 | 23.3906 | 51.5763 | 21.9371 | 3.1729 | 25.9636 | 33.6818 | 3.1649 | 32.4857 | 10.1162 | 21.8528 | 16.321 | 11.5616 | 50.712 | 21.815 | 576.7457
391 | 6.7007 | 46.1976 | 28.6092 | 6.4237 | 30.0031 | 34.1133 | 28.7731 | 9.9789 | 18.254 | 10.1148 | 20.1749 | 25.9345 | 32.896 | 24.3634 | 3.2263 | 26.0289 | 33.2356 | 5.8407 | 22.2329 | 13.855 | 21.3054 | 16.2665 | 10.4299 | 55.026 | 19.4361 | 549.4207
392 | 6.0559 | 31.5053 | 22.3468 | 7.1675 | 33.2017 | 44.9632 | 35.9403 | 11.5468 | 14.9763 | 16.4147 | 21.4225 | 22.2882 | 50.2612 | 15.9156 | 3.1978 | 25.5169 | 33.918 | 5.6653 | 27.4588 | 12.3184 | 19.7474 | 18.7612 | 10.9879 | 39.4887 | 20.6673 | 551.7337
393 | 5.3921 | 41.4536 | 32.8362 | 7.4885 | 19.393 | 46.3649 | 27.6061 | 11.1303 | 13.4573 | 13.9776 | 21.8201 | 27.8805 | 34.3387 | 21.821 | 2.9421 | 23.1683 | 31.793 | 5.5936 | 24.4683 | 9.9762 | 25.9272 | 21.9435 | 6.7598 | 53.0811 | 17.3155 | 547.9287
394 | 7.8693 | 46.5467 | 16.4815 | 7.7206 | 38.7353 | 47.3792 | 37.063 | 9.3607 | 18.3175 | 14.6424 | 17.8752 | 24.4447 | 51.478 | 21.3533 | 3.6625 | 20.5896 | 37.241 | 5.7909 | 30.7507 | 9.6492 | 17.4638 | 21.9186 | 12.1221 | 55.8097 | 18.8187 | 593.0843
395 | 5.3394 | 34.1025 | 26.4994 | 6.7725 | 32.7943 | 36.2848 | 25.1536 | 11.2262 | 14.6814 | 7.9909 | 21.2865 | 27.6579 | 44.9448 | 24.9823 | 2.9569 | 23.767 | 26.1191 | 5.3556 | 28.5497 | 12.9397 | 24.9573 | 14.9483 | 7.8572 | 40.0949 | 10.986 | 518.2482
396 | 5.675 | 44.1746 | 29.2453 | 7.6093 | 30.7951 | 39.589 | 37.4759 | 9.8667 | 18.7513 | 13.4618 | 22.2176 | 24.3994 | 37.6051 | 22.246 | 2.8111 | 25.5415 | 24.4158 | 5.1173 | 26.7086 | 11.3175 | 24.0423 | 21.1983 | 11.4399 | 56.3476 | 20.96 | 573.0119
397 | 5.1644 | 39.7548 | 18.5774 | 7.517 | 25.1763 | 35.8177 | 27.8975 | 10.9872 | 17.1412 | 12.0887 | 20.0739 | 17.5313 | 42.3346 | 19.812 | 3.5735 | 18.4538 | 38.5353 | 4.8131 | 30.9179 | 10.1413 | 14.1775 | 16.4924 | 10.2794 | 54.8838 | 15.7519 | 517.894
398 | 6.639 | 48.8081 | 18.37 | 7.3365 | 36.0487 | 37.0219 | 32.4999 | 9.2007 | 13.5891 | 15.1644 | 18.6013 | 21.5443 | 39.7863 | 24.4994 | 3.2887 | 24.0763 | 26.4865 | 5.8759 | 26.4406 | 10.3372 | 16.3629 | 20.4077 | 7.4421 | 58.8732 | 20.3652 | 549.0658
399 | 5.5514 | 41.8441 | 31.0353 | 8.4177 | 18.6639 | 24.6213 | 36.2891 | 9.7928 | 18.8234 | 13.1426 | 15.7979 | 25.2386 | 49.219 | 14.7929 | 3.5018 | 21.0313 | 34.171 | 5.6081 | 27.1744 | 12.1771 | 26.3209 | 19.343 | 7.6886 | 54.5505 | 21.8391 | 546.636
400 | 7.9743 | 34.8773 | 21.6317 | 6.7108 | 37.4265 | 51.3886 | 21.9206 | 8.7698 | 14.0429 | 8.6457 | 20.542 | 14.3491 | 45.5714 | 18.5115 | 3.9143 | 18.2201 | 31.7348 | 3.7045 | 30.7045 | 9.575 | 19.9789 | 15.6935 | 6.8707 | 47.5635 | 21.0448 | 521.3665
401 | 5.6581 | 35.853 | 24.754 | 7.6032 | 35.0531 | 34.9478 | 29.386 | 8.0728 | 19.0509 | 14.8226 | 19.5203 | 27.3667 | 50.8877 | 24.4643 | 3.0146 | 19.4849 | 28.0538 | 4.5658 | 27.7856 | 13.8555 | 16.0323 | 17.7236 | 11.1653 | 53.4198 | 21.2858 | 553.8275
402 | 7.5556 | 46.8151 | 26.1912 | 6.6649 | 32.3258 | 44.2525 | 22.2436 | 8.2035 | 15.1901 | 14.6773 | 17.0361 | 25.886 | 44.3576 | 23.0197 | 2.6871 | 16.9388 | 26.296 | 5.7358 | 28.3709 | 11.2598 | 21.2965 | 19.6905 | 9.5472 | 43.2999 | 16.4653 | 536.0069
403 | 4.7848 | 25.2846 | 30.7763 | 7.7252 | 30.9307 | 43.2619 | 30.5743 | 9.1538 | 17.7075 | 11.0184 | 21.5996 | 23.2003 | 42.8488 | 24.492 | 3.596 | 26.3372 | 39.076 | 5.209 | 22.5964 | 12.8345 | 25.9221 | 18.6768 | 9.0684 | 52.7194 | 18.3642 | 557.7583
404 | 8.0677 | 36.3948 | 22.8149 | 8.4799 | 18.0667 | 34.6905 | 31.0352 | 9.6357 | 19.4543 | 13.551 | 21.9136 | 24.6271 | 49.8926 | 20.8649 | 2.8017 | 21.033 | 36.6833 | 5.4448 | 24.1159 | 13.0255 | 22.2364 | 19.0507 | 10.3338 | 58.8652 | 15.8873 | 548.9665
405 | 6.6318 | 45.4897 | 23.8991 | 8.4852 | 24.1593 | 30.8155 | 33.5857 | 5.4406 | 14.84 | 14.0402 | 12.3066 | 18.1788 | 50.4731 | 23.9403 | 2.9941 | 20.8296 | 31.7952 | 4.0507 | 28.2455 | 13.544 | 17.7638 | 19.6801 | 10.8806 | 53.5748 | 14.5605 | 530.2049
406 | 5.798 | 46.9745 | 26.895 | 8.4805 | 31.1552 | 37.944 | 36.6182 | 8.2542 | 18.4034 | 12.3356 | 18.2964 | 26.0206 | 32.8164 | 24.2539 | 3.7933 | 23.7809 | 30.383 | 5.1414 | 23.6711 | 7.3943 | 18.8025 | 17.52 | 10.2946 | 55.1376 | 14.5855 | 544.7502
407 | 7.5402 | 27.2912 | 29.871 | 5.3446 | 30.2599 | 51.3089 | 26.6362 | 9.9952 | 15.8189 | 9.5475 | 18.1309 | 17.7633 | 50.9866 | 25.8774 | 3.8349 | 23.9706 | 36.5534 | 5.5191 | 24.0079 | 11.126 | 23.7795 | 21.3947 | 12.0124 | 53.3054 | 20.5624 | 562.4382
408 | 7.2501 | 45.7012 | 29.2352 | 8.4173 | 31.7656 | 49.6503 | 27.5993 | 11.6006 | 11.9307 | 9.4445 | 9.9526 | 22.5989 | 42.0864 | 24.6268 | 3.7284 | 27.0237 | 25.4524 | 5.1684 | 28.0318 | 13.3349 | 18.4248 | 17.8473 | 8.2449 | 32.6926 | 21.4459 | 533.2545
409 | 6.1742 | 35.9854 | 31.4892 | 7.4053 | 18.172 | 52.079 | 30.728 | 9.7424 | 18.4653 | 12.2367 | 21.8017 | 17.0778 | 28.7469 | 23.7631 | 3.516 | 23.0933 | 20.9094 | 4.1 | 24.4747 | 13.0472 | 25.7607 | 20.1072 | 9.1899 | 54.939 | 14.9671 | 527.9715
410 | 7.6698 | 39.1305 | 19.4183 | 8.2994 | 36.7248 | 30.7539 | 36.1345 | 9.1758 | 16.8237 | 13.7241 | 18.1929 | 17.2728 | 35.9359 | 20.3189 | 3.8543 | 19.6995 | 18.8419 | 5.773 | 21.8077 | 10.7182 | 18.3086 | 17.6521 | 7.6442 | 56.9287 | 14.751 | 505.5543
411 | 6.3901 | 43.2664 | 19.1915 | 7.5401 | 32.3124 | 27.0713 | 30.8658 | 11.4469 | 19.8785 | 10.8849 | 14.1066 | 26.7372 | 46.8638 | 19.0358 | 2.5399 | 27.5557 | 25.8637 | 5.1393 | 24.2461 | 12.2837 | 19.9936 | 20.5972 | 8.949 | 48.0497 | 16.787 | 527.5961
412 | 5.8597 | 34.7046 | 23.8019 | 6.732 | 26.5563 | 39.4403 | 31.9599 | 6.0459 | 16.5051 | 11.5414 | 17.2558 | 15.2287 | 46.3164 | 19.0447 | 3.3383 | 20.3438 | 34.6158 | 5.7233 | 25.5307 | 13.2212 | 17.3765 | 19.1222 | 10.4842 | 35.1346 | 18.4108 | 504.294
413 | 7.3864 | 27.0344 | 21.1493 | 7.5185 | 27.4386 | 48.4959 | 25.4562 | 9.447 | 16.3808 | 15.3425 | 12.1524 | 15.3722 | 32.5881 | 24.9674 | 2.4919 | 24.5169 | 33.9393 | 5.1101 | 28.9369 | 12.5444 | 26.0813 | 20.2848 | 9.3486 | 55.9628 | 19.8317 | 529.7782
414 | 5.9541 | 35.2325 | 26.8243 | 8.5233 | 31.6057 | 41.3847 | 24.519 | 10.7506 | 17.1357 | 15.105 | 21.5083 | 25.0108 | 54.4892 | 19.8411 | 3.9836 | 20.4352 | 37.7273 | 5.7633 | 19.5481 | 12.7755 | 25.6958 | 19.1035 | 10.895 | 35.8059 | 18.241 | 547.8585
415 | 7.1554 | 40.8979 | 30.0979 | 5.1833 | 33.2184 | 44.8074 | 37.6727 | 9.5785 | 17.8478 | 16.1642 | 21.4651 | 20.0476 | 37.6741 | 21.8985 | 3.6203 | 15.2833 | 35.7208 | 5.7105 | 29.8699 | 12.0405 | 18.3226 | 16.01 | 9.5993 | 52.6021 | 22.0878 | 564.5759
416 | 5.1003 | 46.8242 | 23.5509 | 7.4192 | 27.3021 | 36.2566 | 36.6417 | 9.8938 | 19.2137 | 11.5298 | 18.7123 | 25.9299 | 49.6333 | 25.257 | 3.7078 | 25.7978 | 32.3381 | 5.2397 | 31.6015 | 10.8097 | 15.1323 | 18.7123 | 11.202 | 50.2742 | 16.7429 | 564.823
417 | 8.0579 | 39.1792 | 23.5942 | 6.127 | 26.3398 | 39.9119 | 30.4627 | 10.3165 | 15.9594 | 10.0799 | 12.4404 | 19.5805 | 27.1719 | 20.9151 | 2.7907 | 12.2402 | 29.7183 | 4.3581 | 18.7372 | 12.1094 | 19.2687 | 19.7699 | 7.7888 | 50.4629 | 13.094 | 480.4744
418 | 5.6268 | 36.2953 | 28.58 | 7.4797 | 30.9476 | 39.8674 | 29.602 | 8.4003 | 14.7168 | 15.5703 | 22.1699 | 21.6578 | 53.2676 | 18.015 | 3.917 | 22.892 | 35.29 | 3.3646 | 30.0806 | 8.4049 | 20.4517 | 21.0641 | 10.2717 | 59.899 | 12.4434 | 560.2756
419 | 7.8799 | 35.6199 | 29.7606 | 7.6674 | 25.9768 | 40.6663 | 33.3611 | 10.7157 | 17.9831 | 11.9335 | 16.8936 | 23.8875 | 25.6148 | 22.1031 | 3.6614 | 26.6987 | 28.6519 | 5.9312 | 25.3672 | 13.9822 | 14.4818 | 15.2077 | 11.6297 | 41.0306 | 19.9268 | 516.6324
420 | 6.8581 | 43.2471 | 24.8735 | 7.7686 | 24.4895 | 36.1613 | 36.3946 | 10.6547 | 18.1557 | 12.3567 | 16.0423 | 26.047 | 46.3864 | 21.3254 | 3.6657 | 19.6302 | 35.3389 | 5.7081 | 29.4596 | 13.9157 | 15.4647 | 19.1331 | 10.4808 | 40.3741 | 14.3426 | 538.2745
421 | 7.8929 | 42.8498 | 31.5195 | 8.6094 | 19.6952 | 43.8968 | 28.2554 | 9.2027 | 17.0628 | 13.4838 | 18.5353 | 23.4839 | 43.58 | 19.9241 | 2.9759 | 26.3676 | 30.141 | 4.7723 | 22.6795 | 11.4782 | 21.7 | 17.6232 | 12.157 | 57.3027 | 18.8704 | 554.0593
422 | 7.8799 | 42.4512 | 30.6303 | 8.4522 | 32.1342 | 43.4717 | 34.6982 | 9.8991 | 19.3131 | 14.8049 | 13.0026 | 20.3104 | 41.4472 | 22.3201 | 3.4588 | 25.4093 | 27.4072 | 4.2432 | 24.8045 | 13.1439 | 20.5519 | 19.4376 | 7.0808 | 58.237 | 11.3907 | 555.9799
423 | 8.2352 | 25.9623 | 30.8882 | 5.8313 | 17.1567 | 42.6098 | 19.1644 | 11.0494 | 14.8133 | 15.2599 | 15.3423 | 14.0309 | 55.5564 | 24.3055 | 3.8991 | 21.8647 | 34.1549 | 4.6334 | 23.1632 | 13.8059 | 15.7067 | 20.2972 | 9.6563 | 41.5029 | 15.9482 | 504.8383
424 | 6.8039 | 40.8372 | 21.5854 | 8.702 | 31.8987 | 41.689 | 33.7939 | 9.013 | 11.9274 | 14.346 | 13.6678 | 24.972 | 54.4856 | 20.6384 | 2.6259 | 20.5219 | 31.6065 | 4.9307 | 23.3346 | 10.5952 | 20.2825 | 14.183 | 9.0813 | 59.3703 | 20.7135 | 551.6057
425 | 6.815 | 39.4884 | 26.2042 | 8.6212 | 32.6914 | 46.9057 | 30.1552 | 8.2631 | 18.2289 | 9.3945 | 21.8553 | 25.5542 | 47.6949 | 22.9222 | 3.2764 | 23.2677 | 22.7704 | 5.9691 | 31.6283 | 13.3938 | 23.6685 | 12.1527 | 7.7387 | 55.7499 | 17.3099 | 561.7197
426 | 8.1694 | 49.6404 | 32.3676 | 7.5378 | 22.1113 | 36.9576 | 36.7229 | 9.3325 | 15.1468 | 16.4203 | 16.3413 | 18.1795 | 52.4965 | 23.5696 | 3.669 | 12.9505 | 20.5112 | 5.7572 | 29.4772 | 8.9878 | 17.623 | 15.7708 | 11.1597 | 55.5199 | 22.1609 | 548.5805
427 | 4.9259 | 31.4414 | 27.5595 | 7.5286 | 18.1444 | 37.0513 | 33.5038 | 10.0281 | 17.8924 | 16.3692 | 14.734 | 26.735 | 48.3622 | 23.8743 | 2.7705 | 23.9387 | 28.1659 | 5.7465 | 23.0575 | 9.4936 | 22.6613 | 17.2965 | 11.2691 | 52.1903 | 20.458 | 535.1979
428 | 5.4546 | 38.077 | 33.3272 | 8.1443 | 27.413 | 39.5882 | 24.586 | 7.3683 | 17.8299 | 14.0572 | 20.6914 | 16.2648 | 39.2902 | 19.6051 | 3.539 | 25.1444 | 34.1242 | 5.6023 | 32.0093 | 8.8164 | 22.7269 | 21.7706 | 10.2955 | 59.0091 | 16.9977 | 551.7325
429 | 6.3865 | 38.0943 | 30.6761 | 8.2919 | 37.6841 | 49.1922 | 34.6027 | 9.0408 | 19.3852 | 16.1616 | 22.2762 | 20.2109 | 44.1125 | 22.1039 | 3.8349 | 23.569 | 36.1077 | 4.865 | 28.7737 | 13.8521 | 19.0444 | 21.0898 | 9.9264 | 34.7333 | 20.6892 | 574.7044
430 | 5.1401 | 47.8769 | 22.964 | 7.9657 | 32.554 | 48.9936 | 26.4065 | 11.2782 | 18.0711 | 15.6876 | 22.3373 | 16.1275 | 53.4745 | 16.0708 | 3.8605 | 20.3075 | 27.8093 | 5.8829 | 32.9112 | 11.5048 | 20.3709 | 18.8807 | 10.1802 | 39.4187 | 16.3402 | 552.4148
431 | 8.2484 | 47.3735 | 31.6709 | 7.7501 | 25.6223 | 36.3435 | 25.7638 | 7.6056 | 11.9885 | 13.3208 | 17.1621 | 18.336 | 42.6733 | 21.3211 | 3.7799 | 18.2285 | 25.8463 | 5.1674 | 30.4663 | 9.0043 | 16.4143 | 21.1146 | 9.7883 | 31.0788 | 16.9129 | 502.9817
432 | 5.1921 | 27.3907 | 25.1344 | 8.4813 | 34.3405 | 40.2479 | 32.6777 | 10.955 | 18.2809 | 13.6216 | 20.6697 | 20.1332 | 31.5556 | 20.9416 | 2.7613 | 22.3503 | 29.3669 | 5.2886 | 26.8163 | 10.2609 | 23.7106 | 20.6581 | 10.8442 | 54.7693 | 19.5144 | 535.9631
433 | 4.7815 | 28.317 | 29.1193 | 4.785 | 38.0642 | 45.8397 | 38.2751 | 6.7877 | 14.8822 | 16.4576 | 20.7236 | 16.3649 | 53.483 | 19.8532 | 3.6543 | 14.7951 | 32.5305 | 4.5636 | 31.0804 | 8.509 | 16.0388 | 20.6941 | 10.6121 | 47.7344 | 19.1862 | 547.1322
434 | 6.8574 | 45.2232 | 29.0211 | 5.9045 | 38.2471 | 42.3022 | 33.6394 | 9.7077 | 13.91 | 12.8537 | 19.3753 | 21.0078 | 38.4305 | 23.5322 | 3.5292 | 24.9975 | 34.3367 | 4.9503 | 23.8985 | 12.7894 | 25.9397 | 19.6517 | 10.116 | 43.934 | 19.1561 | 563.3112
435 | 6.9059 | 48.2095 | 30.4149 | 8.7307 | 32.5276 | 39.0447 | 29.7474 | 8.7583 | 17.401 | 13.3272 | 17.6319 | 22.8648 | 48.9903 | 22.333 | 3.1446 | 26.4277 | 25.6745 | 3.4025 | 30.0577 | 13.3438 | 25.4813 | 21.3198 | 10.0146 | 37.0733 | 20.6396 | 563.4666
436 | 5.7354 | 38.7255 | 30.2837 | 7.7886 | 26.7674 | 31.6906 | 27.2745 | 6.1776 | 17.3555 | 7.6161 | 20.9499 | 13.3725 | 48.1334 | 24.925 | 3.7244 | 23.3937 | 31.1798 | 5.0325 | 28.8475 | 11.9838 | 22.6713 | 20.6174 | 7.3244 | 58.1647 | 13.1334 | 532.8684
437 | 8.2085 | 44.854 | 27.5872 | 7.0862 | 38.6347 | 33.1201 | 27.2071 | 6.2469 | 12.8088 | 14.4484 | 11.1384 | 23.225 | 46.0881 | 25.3184 | 2.934 | 23.9014 | 35.0934 | 4.6603 | 32.4738 | 11.758 | 21.4036 | 21.5218 | 11.8777 | 52.9757 | 14.1313 | 558.7028
438 | 7.6772 | 28.4875 | 27.8918 | 8.376 | 16.5758 | 52.4327 | 24.1271 | 6.3564 | 19.974 | 15.4517 | 18.4345 | 15.3623 | 36.1871 | 23.4825 | 2.4756 | 25.9589 | 24.568 | 5.489 | 31.7106 | 11.3685 | 18.2513 | 20.3376 | 7.5216 | 45.5864 | 21.8964 | 515.9804
439 | 5.5413 | 46.1144 | 27.9384 | 6.6089 | 31.3418 | 41.3537 | 33.2639 | 9.9189 | 16.6344 | 14.9993 | 22.2301 | 22.2992 | 53.5041 | 24.203 | 3.0062 | 24.4915 | 33.6472 | 5.1583 | 32.3717 | 12.8108 | 15.2984 | 16.2835 | 11.7207 | 45.2031 | 18.7238 | 574.6666
440 | 7.1791 | 37.9262 | 20.3548 | 6.2142 | 37.1345 | 48.8274 | 32.7346 | 11.0475 | 18.9864 | 14.0163 | 10.9316 | 20.8912 | 44.0427 | 19.7571 | 3.469 | 20.1168 | 35.3979 | 5.5087 | 21.4971 | 12.5294 | 24.0682 | 20.1018 | 10.0284 | 53.5953 | 16.1226 | 552.4789
441 | 7.2902 | 29.8216 | 25.711 | 6.4972 | 31.6516 | 29.3343 | 23.4854 | 7.7456 | 19.1848 | 15.979 | 16.6275 | 24.0209 | 40.8586 | 18.2075 | 3.5829 | 27.6821 | 25.3429 | 5.2945 | 30.5056 | 11.1523 | 19.0629 | 16.7005 | 12.3458 | 49.1626 | 12.8375 | 510.0851
442 | 5.2967 | 42.6521 | 30.0223 | 7.2448 | 38.6496 | 31.7286 | 22.3036 | 9.3311 | 18.4016 | 16.6418 | 16.2466 | 25.0918 | 43.0077 | 23.9543 | 3.5678 | 22.6532 | 30.9768 | 5.7592 | 28.3479 | 13.4532 | 15.3161 | 19.2177 | 8.5459 | 45.5428 | 18.4556 | 542.4089
443 | 7.691 | 38.3193 | 29.14 | 8.549 | 26.3395 | 47.3106 | 35.4392 | 9.7138 | 17.549 | 8.9731 | 17.2107 | 28.6288 | 47.8514 | 23.6839 | 3.5189 | 25.0285 | 27.3377 | 5.7813 | 27.0292 | 12.924 | 19.0866 | 18.9649 | 11.2714 | 50.5766 | 18.7601 | 566.6785
444 | 4.8143 | 39.6608 | 26.9044 | 7.6358 | 34.5436 | 52.0129 | 32.5473 | 11.6548 | 13.6722 | 13.2268 | 13.4685 | 20.2438 | 49.8748 | 22.8728 | 3.6316 | 27.722 | 37.8538 | 5.0608 | 26.4473 | 13.4835 | 24.2545 | 21.4668 | 11.5437 | 53.6746 | 14.9309 | 583.2025
445 | 6.8395 | 23.8875 | 21.1674 | 8.7415 | 31.142 | 34.1337 | 32.6082 | 9.8856 | 17.8708 | 12.3821 | 14.933 | 24.4037 | 48.7702 | 16.2662 | 2.845 | 15.3812 | 36.1917 | 5.3111 | 29.4057 | 10.605 | 20.6041 | 19.9517 | 10.4953 | 58.9129 | 18.3856 | 531.1205
446 | 7.7282 | 40.6575 | 19.4846 | 6.0486 | 29.5085 | 49.4212 | 31.2152 | 11.3013 | 15.5819 | 12.1053 | 21.8258 | 25.2815 | 35.5203 | 17.4294 | 2.689 | 23.3262 | 24.551 | 4.3184 | 21.9233 | 13.8359 | 14.2558 | 14.2634 | 8.3948 | 47.2007 | 19.38 | 517.2477
447 | 6.8516 | 30.7503 | 23.5503 | 7.592 | 21.4642 | 42.1205 | 37.5121 | 8.7165 | 15.7002 | 14.4598 | 18.3051 | 27.4321 | 42.0738 | 25.7094 | 3.8091 | 25.7516 | 33.7288 | 5.9068 | 16.8532 | 12.327 | 20.4046 | 18.4395 | 11.195 | 48.424 | 21.1196 | 540.1971
448 | 7.1353 | 24.5111 | 26.1075 | 5.3379 | 33.5184 | 45.2071 | 34.0126 | 6.258 | 11.7191 | 16.1126 | 14.6547 | 21.1002 | 55.1851 | 22.7317 | 3.5633 | 24.6214 | 35.5359 | 5.109 | 24.8556 | 11.6142 | 24.678 | 17.5292 | 11.174 | 47.8138 | 17.6876 | 547.7731
449 | 3.7743 | 38.8012 | 29.3068 | 8.4998 | 37.1406 | 43.3988 | 36.1301 | 6.4392 | 19.7519 | 12.7207 | 19.0247 | 19.519 | 44.0457 | 24.0851 | 3.043 | 24.855 | 36.7038 | 3.3707 | 21.456 | 8.4965 | 23.0434 | 19.1089 | 9.9106 | 38.179 | 14.6539 | 545.4589
450 | 7.0737 | 39.1682 | 30.8063 | 8.4715 | 25.8097 | 35.7389 | 23.9364 | 9.7808 | 19.1697 | 14.5917 | 19.183 | 27.8123 | 49.7331 | 25.5083 | 3.4548 | 25.303 | 38.4859 | 5.4055 | 24.8165 | 11.9042 | 20.6372 | 21.0798 | 11.8197 | 54.7993 | 19.5088 | 573.9982
451 | 7.0988 | 41.5988 | 30.723 | 5.6942 | 37.874 | 47.5814 | 34.0824 | 7.4918 | 17.8273 | 15.8676 | 17.7952 | 21.4397 | 37.4063 | 24.8505 | 3.3242 | 22.6781 | 23.5491 | 5.6794 | 30.7598 | 11.97 | 21.7448 | 18.1592 | 10.8126 | 36.6509 | 21.4 | 554.0591
452 | 7.6076 | 49.1209 | 28.5459 | 7.9143 | 35.7403 | 22.2417 | 23.5858 | 9.3568 | 19.7755 | 15.1161 | 15.5982 | 26.9248 | 44.0381 | 25.5783 | 2.7966 | 26.1925 | 36.3154 | 5.1289 | 28.7849 | 12.7042 | 20.2704 | 16.1941 | 8.0588 | 49.3839 | 15.4094 | 552.3834
453 | 7.4814 | 31.6474 | 20.1326 | 8.4587 | 21.6144 | 47.2449 | 36.9141 | 9.2277 | 16.6795 | 15.7255 | 20.0732 | 21.0234 | 43.0852 | 20.2571 | 3.9993 | 19.9323 | 35.705 | 5.2263 | 21.4644 | 7.4905 | 22.9195 | 16.2723 | 9.0276 | 50.0474 | 15.584 | 527.2336
454 | 5.2495 | 36.4541 | 25.751 | 8.426 | 29.1238 | 34.6279 | 36.4504 | 9.6067 | 16.477 | 16.031 | 16.2514 | 24.4063 | 43.9043 | 25.4765 | 3.4783 | 16.911 | 35.1368 | 5.6442 | 18.8384 | 13.5519 | 20.0516 | 15.6597 | 9.8785 | 48.7791 | 15.7546 | 531.9196
455 | 5.9344 | 47.1883 | 22.3621 | 8.5557 | 33.6983 | 39.0613 | 23.5474 | 6.4624 | 18.2165 | 12.8691 | 21.0216 | 19.6955 | 49.8511 | 20.8213 | 3.425 | 27.1882 | 33.2722 | 4.7898 | 19.53 | 11.9045 | 18.6108 | 21.1014 | 8.14 | 48.1924 | 20.9953 | 546.4348
456 | 6.9701 | 41.8709 | 30.5553 | 8.5008 | 23.6036 | 45.6294 | 34.8659 | 10.4435 | 19.057 | 13.7193 | 20.0886 | 24.6848 | 50.721 | 20.5982 | 3.0053 | 25.9417 | 24.4002 | 5.9489 | 26.4826 | 12.7133 | 23.4746 | 17.3773 | 11.5729 | 31.7228 | 21.1902 | 555.1381
457 | 6.1257 | 38.19 | 30.4694 | 8.5448 | 17.5606 | 42.3222 | 17.5102 | 8.289 | 17.6021 | 13.9026 | 19.7652 | 18.1987 | 46.2749 | 17.4578 | 3.0694 | 23.9142 | 32.9572 | 4.8717 | 27.3267 | 13.6472 | 21.1477 | 17.1331 | 10.7123 | 55.3535 | 16.2293 | 528.5753
458 | 7.6312 | 31.6202 | 31.5059 | 8.5673 | 32.498 | 44.81 | 32.3856 | 5.6806 | 14.1312 | 14.2367 | 22.3851 | 19.7839 | 50.8865 | 24.1598 | 3.8813 | 20.8315 | 34.2612 | 5.3809 | 21.7606 | 7.3532 | 22.7591 | 21.1196 | 11.6218 | 25.463 | 20.4988 | 535.2132
459 | 6.81 | 28.7131 | 24.1378 | 7.5147 | 31.2812 | 41.0583 | 35.6183 | 11.3557 | 19.3582 | 16.0695 | 20.1901 | 25.4897 | 52.1162 | 23.0605 | 3.9083 | 15.3257 | 30.5497 | 5.3662 | 25.4277 | 9.0903 | 11.0147 | 14.9596 | 10.2288 | 48.9177 | 18.1428 | 535.7049
460 | 5.4263 | 36.8422 | 24.9606 | 6.7593 | 22.6098 | 42.2451 | 31.1485 | 11.5579 | 15.9505 | 11.2978 | 18.7147 | 26.1272 | 49.8006 | 17.4892 | 2.7874 | 15.241 | 36.1922 | 5.1278 | 31.1814 | 7.8676 | 18.0572 | 17.5733 | 10.156 | 49.743 | 21.5386 | 536.3951
461 | 8.2876 | 44.932 | 23.5166 | 5.9298 | 19.8827 | 42.1411 | 37.7108 | 9.2615 | 19.9903 | 13.009 | 18.269 | 25.7398 | 37.6137 | 25.2747 | 3.3196 | 19.1928 | 38.0106 | 5.1546 | 27.561 | 13.0877 | 22.831 | 20.6827 | 9.1821 | 52.6205 | 11.3763 | 554.5774
462 | 7.2827 | 31.8759 | 32.7508 | 5.6902 | 33.0947 | 40.5203 | 29.5604 | 6.9038 | 17.3623 | 16.6784 | 16.1568 | 25.3328 | 22.0233 | 15.829 | 3.7403 | 20.2308 | 35.5422 | 5.2159 | 21.8524 | 12.4573 | 22.2373 | 14.1705 | 12.317 | 49.1694 | 17.3183 | 515.3128
463 | 7.213 | 39.4399 | 29.847 | 5.4655 | 30.5117 | 48.5916 | 19.7549 | 10.2632 | 16.8541 | 13.1033 | 20.9869 | 17.7224 | 42.9005 | 20.9086 | 3.3078 | 19.876 | 35.9889 | 5.5431 | 27.3197 | 13.1135 | 20.2595 | 13.507 | 6.9962 | 58.3856 | 17.7225 | 545.5824
464 | 7.5893 | 42.8279 | 23.789 | 8.6526 | 24.1643 | 41.9021 | 28.6532 | 11.5311 | 12.0823 | 12.275 | 16.6251 | 26.2152 | 50.1159 | 19.4065 | 3.0598 | 19.3472 | 33.644 | 4.7044 | 21.1095 | 10.8242 | 21.9351 | 19.8801 | 12.3554 | 50.29 | 15.0129 | 537.992
465 | 7.4311 | 36.0445 | 25.8217 | 7.6284 | 33.8187 | 43.6454 | 21.7013 | 8.4466 | 18.6898 | 10.7345 | 21.0023 | 27.4135 | 39.6279 | 18.88 | 3.1691 | 15.0826 | 36.0325 | 4.3333 | 24.5876 | 12.056 | 18.6542 | 17.5828 | 6.7983 | 51.6605 | 17.8185 | 528.661
466 | 5.8962 | 34.83 | 31.794 | 8.5377 | 34.0593 | 48.1802 | 32.8671 | 9.8751 | 19.7028 | 9.8275 | 17.85 | 28.0359 | 42.8853 | 25.0176 | 3.6669 | 24.9866 | 30.4248 | 5.1277 | 27.4866 | 12.7358 | 23.6546 | 21.1523 | 12.4417 | 50.8638 | 21.77 | 583.6694
467 | 4.2754 | 39.376 | 23.8811 | 7.9282 | 30.0642 | 34.6423 | 31.0903 | 9.4968 | 19.4073 | 15.9578 | 20.4234 | 23.5193 | 44.3479 | 24.5757 | 2.3361 | 27.0083 | 30.1016 | 4.5756 | 29.7633 | 13.516 | 19.2681 | 18.9478 | 8.6562 | 47.2984 | 21.932 | 552.3889
468 | 6.6744 | 41.5569 | 23.4186 | 7.167 | 32.9888 | 43.9211 | 31.5361 | 8.6624 | 11.335 | 16.1889 | 21.8119 | 23.8511 | 49.4731 | 17.724 | 3.8987 | 26.7099 | 31.8898 | 3.4122 | 28.6336 | 12.6402 | 19.0614 | 21.8543 | 5.7233 | 39.16 | 13.9003 | 543.193
469 | 8.1489 | 44.2176 | 30.7449 | 8.2755 | 19.4571 | 43.9715 | 30.6765 | 8.1649 | 14.0215 | 14.2077 | 13.9219 | 24.3864 | 36.8585 | 23.1809 | 3.1996 | 19.3572 | 26.3332 | 5.0794 | 25.7106 | 8.2769 | 25.8272 | 17.8972 | 8.3285 | 39.0462 | 19.9873 | 519.2769
470 | 7.4167 | 33.4527 | 20.7985 | 6.834 | 33.3749 | 45.3998 | 29.9725 | 10.1873 | 19.5014 | 10.9923 | 16.6149 | 27.6996 | 53.6124 | 20.8592 | 2.4212 | 15.5234 | 39.0928 | 5.1994 | 25.0256 | 10.2804 | 22.7856 | 21.9863 | 10.4779 | 54.32 | 18.4156 | 562.2443
471 | 5.976 | 42.4675 | 28.1665 | 7.5017 | 35.2313 | 45.9991 | 20.2338 | 10.7905 | 19.8332 | 13.1891 | 20.5257 | 25.7522 | 32.9791 | 23.4483 | 3.6892 | 16.4417 | 38.1448 | 3.8542 | 30.557 | 10.1274 | 10.5479 | 16.9408 | 6.7481 | 53.9166 | 18.8391 | 541.9007
472 | 5.445 | 37.5678 | 28.9093 | 8.6062 | 23.7992 | 37.257 | 30.0866 | 9.9216 | 19.258 | 13.1799 | 20.7332 | 17.8538 | 51.5824 | 25.396 | 3.8039 | 23.1139 | 28.8638 | 4.2523 | 21.5005 | 10.6335 | 21.2047 | 18.9785 | 10.3979 | 45.1254 | 16.6233 | 534.0939
473 | 7.1057 | 36.0088 | 28.4542 | 7.5116 | 32.1608 | 24.0151 | 38.5694 | 8.6398 | 17.1979 | 11.3088 | 11.562 | 21.0985 | 40.9735 | 24.896 | 2.9017 | 25.6395 | 33.1159 | 4.9364 | 28.1781 | 11.1817 | 21.0218 | 16.3746 | 11.8018 | 32.8267 | 21.3254 | 518.8057
474 | 6.47 | 41.8303 | 26.4243 | 6.5788 | 22.7998 | 36.2844 | 36.6126 | 8.9887 | 17.0803 | 16.1656 | 16.78 | 19.825 | 39.4818 | 17.8965 | 2.4633 | 16.4857 | 26.0201 | 5.9422 | 20.4162 | 12.5977 | 25.2243 | 17.4046 | 8.9679 | 43.0401 | 18.8541 | 510.6344
475 | 4.2716 | 42.3809 | 27.5412 | 7.2604 | 31.9042 | 46.6998 | 27.9958 | 11.0763 | 14.3897 | 12.6205 | 16.0631 | 22.8197 | 41.1567 | 15.2359 | 3.1462 | 22.4637 | 36.568 | 4.719 | 25.1853 | 13.2203 | 24.5489 | 19.9352 | 10.5225 | 30.1882 | 20.7745 | 532.6878
476 | 7.1661 | 27.3185 | 17.3248 | 6.1868 | 36.5236 | 46.8177 | 37.4064 | 8.2904 | 16.1537 | 12.9475 | 14.3504 | 26.7621 | 49.9557 | 21.6859 | 3.5769 | 23.185 | 25.6127 | 3.3761 | 24.8511 | 8.6708 | 21.0908 | 18.1247 | 6.2804 | 54.0235 | 15.2833 | 532.965
477 | 3.7984 | 33.3859 | 29.4552 | 6.8401 | 32.0735 | 47.1283 | 29.7028 | 7.9511 | 14.0257 | 16.3081 | 21.0156 | 26.2878 | 36.9286 | 24.0968 | 3.7974 | 19.1312 | 21.1195 | 5.3678 | 31.0304 | 9.8439 | 23.109 | 21.1235 | 11.5401 | 51.6704 | 20.876 | 547.6069
478 | 5.0059 | 35.7807 | 26.7774 | 4.721 | 36.8563 | 43.9326 | 34.0088 | 9.4011 | 19.9629 | 8.9997 | 21.9144 | 25.0575 | 41.1934 | 14.7858 | 3.4178 | 24.0312 | 38.8933 | 4.9824 | 26.6234 | 12.4452 | 16.4243 | 14.4118 | 7.9414 | 33.7436 | 17.5313 | 528.843
479 | 4.1415 | 38.8905 | 28.9125 | 7.1821 | 37.1056 | 40.4397 | 36.3029 | 11.5914 | 19.5541 | 11.4795 | 21.3772 | 27.3484 | 48.6557 | 19.3352 | 3.775 | 27.8881 | 26.5972 | 5.7152 | 30.6214 | 12.5834 | 25.0388 | 21.7434 | 10.1667 | 54.515 | 21.4233 | 592.3836
480 | 6.6591 | 33.7047 | 26.6205 | 7.3641 | 23.0485 | 46.8144 | 31.8671 | 9.5772 | 19.5387 | 9.7443 | 17.8877 | 18.2344 | 32.6752 | 21.8924 | 2.9149 | 25.8004 | 25.532 | 4.6626 | 24.7283 | 11.8391 | 21.946 | 15.3895 | 10.158 | 45.8738 | 15.5861 | 510.0591
481 | 5.545 | 46.1335 | 32.9245 | 7.3708 | 27.7934 | 39.9425 | 34.4288 | 11.1893 | 14.4958 | 16.228 | 15.8937 | 28.2903 | 51.7561 | 24.9177 | 3.9107 | 21.7419 | 30.4521 | 5.987 | 29.1281 | 12.0069 | 20.5105 | 18.5782 | 9.977 | 30.3791 | 10.7519 | 550.333
482 | 6.1772 | 37.5184 | 26.3471 | 7.5929 | 36.544 | 49.2079 | 29.6404 | 9.7859 | 13.1082 | 15.633 | 19.527 | 22.8709 | 42.789 | 22.6826 | 3.9942 | 23.2535 | 29.6958 | 5.6768 | 30.1239 | 13.3845 | 21.9916 | 15.3957 | 10.7818 | 47.4555 | 12.2619 | 553.4398
483 | 7.3658 | 44.8871 | 28.4497 | 7.7361 | 37.1489 | 46.7441 | 36.0098 | 8.037 | 15.9245 | 12.2121 | 20.4004 | 24.4665 | 46.854 | 24.7353 | 2.3494 | 26.9876 | 23.1076 | 3.3977 | 29.9816 | 10.0133 | 25.2953 | 18.9268 | 8.0145 | 47.5907 | 18.3871 | 575.023
484 | 5.588 | 37.6463 | 26.8113 | 6.4917 | 35.7221 | 40.0248 | 36.2691 | 10.7947 | 15.3322 | 8.9883 | 14.1498 | 20.1353 | 45.19 | 25.2649 | 3.9891 | 18.5814 | 28.3036 | 4.8483 | 31.4673 | 10.9962 | 23.6309 | 13.6195 | 10.0362 | 55.5998 | 19.397 | 548.8779
485 | 7.5781 | 41.8203 | 30.9437 | 5.489 | 32.0029 | 46.5217 | 36.1443 | 8.7332 | 19.7544 | 16.1909 | 19.4995 | 18.3882 | 47.3447 | 21.6812 | 3.8436 | 24.7354 | 38.9017 | 5.0208 | 25.5328 | 13.0373 | 18.9598 | 20.2075 | 7.1727 | 55.2587 | 16.505 | 581.2673
486 | 7.4569 | 46.8592 | 31.5135 | 7.7158 | 35.7255 | 45.9042 | 38.674 | 10.8065 | 18.0156 | 14.6516 | 15.6656 | 14.6853 | 42.8595 | 19.7351 | 3.7697 | 27.5424 | 31.3442 | 5.9253 | 30.3638 | 11.2866 | 15.8286 | 17.8269 | 10.5498 | 40.3671 | 16.9159 | 561.9886
487 | 6.2231 | 24.7274 | 21.0857 | 6.9851 | 37.8844 | 47.1201 | 34.1467 | 10.5882 | 17.9683 | 15.2036 | 21.181 | 15.5563 | 48.8424 | 20.549 | 3.3141 | 19.3597 | 23.9859 | 3.6153 | 28.6057 | 12.8564 | 24.6999 | 20.1376 | 9.6256 | 28.8799 | 15.8207 | 518.9622
488 | 7.7016 | 36.845 | 22.8497 | 8.0427 | 30.3666 | 33.591 | 35.4222 | 11.5822 | 18.5976 | 9.5178 | 11.6769 | 25.98 | 53.0746 | 21.8947 | 3.3722 | 24.7957 | 18.5946 | 5.5855 | 26.1562 | 13.1172 | 18.5795 | 13.2473 | 9.2497 | 32.1908 | 18.0763 | 510.1076
489 | 5.2561 | 49.0223 | 32.7102 | 8.0715 | 26.7486 | 50.7841 | 24.6752 | 8.8006 | 17.6569 | 15.6826 | 18.8964 | 27.6551 | 17.1997 | 24.9757 | 2.4033 | 18.4358 | 28.078 | 4.4723 | 17.068 | 13.7024 | 20.1351 | 20.1116 | 9.8988 | 47.3903 | 18.4925 | 528.323
490 | 8.2352 | 45.2011 | 27.9963 | 7.0637 | 38.2106 | 29.0707 | 35.9254 | 9.3229 | 19.1015 | 13.6987 | 19.2915 | 27.3674 | 44.1465 | 25.243 | 3.9425 | 25.5493 | 35.8731 | 5.0587 | 30.0421 | 13.5579 | 21.3872 | 20.9617 | 9.657 | 41.7193 | 17.4787 | 575.1022
491 | 5.2881 | 43.7593 | 30.044 | 6.9195 | 35.217 | 39.2245 | 32.2444 | 10.9354 | 19.7572 | 16.3395 | 20.4903 | 25.05 | 52.8679 | 20.7794 | 3.0841 | 19.2414 | 19.5293 | 4.7286 | 27.9823 | 9.5729 | 21.9606 | 21.9202 | 10.8833 | 47.9021 | 13.6704 | 559.3917
492 | 8.0193 | 28.9218 | 25.9337 | 7.0228 | 31.4091 | 49.0898 | 35.1434 | 9.9472 | 18.8678 | 15.8384 | 14.8874 | 16.1755 | 46.0953 | 22.5001 | 3.9591 | 24.1561 | 37.7674 | 5.9569 | 31.6891 | 9.3781 | 26.0351 | 16.0406 | 10.1929 | 53.6704 | 21.1697 | 569.867
493 | 4.6377 | 43.1437 | 21.9435 | 7.1869 | 25.4204 | 50.7982 | 25.7515 | 9.9287 | 16.5752 | 8.7235 | 21.0109 | 12.5568 | 44.9968 | 18.2286 | 3.6296 | 20.5408 | 33.3144 | 5.3306 | 23.161 | 13.4798 | 23.0078 | 12.5059 | 8.5183 | 44.6281 | 18.5635 | 517.5822
494 | 7.4745 | 43.3014 | 26.6777 | 7.4292 | 22.3804 | 52.0232 | 36.7447 | 8.7077 | 12.208 | 14.9067 | 20.4715 | 27.4902 | 36.2299 | 16.7348 | 3.9772 | 22.6095 | 34.4695 | 5.148 | 31.1698 | 11.5268 | 20.6743 | 16.2195 | 11.8575 | 46.8631 | 21.6024 | 558.8972
495 | 5.785 | 42.4424 | 28.1146 | 6.6776 | 37.9594 | 46.2219 | 25.894 | 10.8707 | 19.2226 | 11.559 | 20.5514 | 23.1815 | 27.1766 | 19.4339 | 3.4823 | 25.4842 | 37.5985 | 5.1936 | 30.5969 | 12.7654 | 19.6388 | 17.5943 | 6.71 | 35.7771 | 22.1572 | 542.0889
496 | 8.0636 | 39.1351 | 32.6184 | 5.2556 | 28.6065 | 42.3161 | 24.8102 | 9.6819 | 19.6091 | 15.5334 | 15.8598 | 20.4615 | 33.5511 | 23.2459 | 3.8627 | 21.8009 | 24.123 | 4.4948 | 30.1542 | 13.5041 | 21.5057 | 12.9378 | 10.6971 | 33.5179 | 20.488 | 515.8344
497 | 5.7933 | 27.7775 | 30.4236 | 7.0664 | 35.1476 | 29.4434 | 39.1282 | 9.0376 | 14.7745 | 11.4968 | 19.2007 | 20.6491 | 40.0183 | 25.9025 | 3.8386 | 23.003 | 37.1987 | 5.8054 | 31.46 | 11.536 | 23.6119 | 15.082 | 9.741 | 40.0543 | 22.3046 | 539.4951
498 | 5.6744 | 32.3209 | 26.5047 | 7.7814 | 30.4999 | 32.9003 | 36.0464 | 10.7699 | 19.9247 | 11.5966 | 20.6934 | 24.4933 | 38.3762 | 20.495 | 3.9234 | 27.6099 | 36.8629 | 5.8482 | 22.9892 | 12.7426 | 26.7749 | 19.9296 | 6.4721 | 31.5722 | 21.8569 | 534.6589
499 | 6.7763 | 45.4338 | 19.4875 | 7.394 | 16.4643 | 42.6167 | 37.8814 | 9.1785 | 19.0316 | 14.4719 | 14.3094 | 18.433 | 47.9847 | 25.5953 | 3.1609 | 21.3528 | 34.3758 | 3.7625 | 32.8514 | 10.9947 | 20.074 | 15.3232 | 8.1647 | 53.1384 | 14.721 | 542.978
500 | 6.5674 | 46.8699 | 29.251 | 8.131 | 35.7119 | 40.4582 | 27.1018 | 7.6704 | 14.5391 | 13.4228 | 17.5112 | 24.5717 | 35.5498 | 25.1439 | 2.5323 | 21.9234 | 37.0241 | 4.0407 | 32.728 | 10.8988 | 22.4841 | 21.4478 | 12.003 | 50.9442 | 19.7553 | 568.2818
501 | 4.3873 | 38.6072 | 28.5961 | 5.1017 | 33.7008 | 45.3838 | 30.9269 | 9.1309 | 16.3454 | 15.3556 | 16.7657 | 22.5919 | 42.025 | 24.6041 | 3.5053 | 26.4251 | 31.6365 | 4.2794 | 29.1732 | 9.6441 | 23.0533 | 21.3907 | 11.5547 | 40.0604 | 18.0929 | 552.338
502 | 7.8814 | 45.0178 | 29.8965 | 6.8468 | 38.7787 | 46.2089 | 34.019 | 8.1847 | 12.1877 | 13.7483 | 17.8685 | 21.7287 | 48.0089 | 20.6585 | 2.6538 | 15.7519 | 23.4288 | 5.9574 | 19.9882 | 13.9605 | 16.1658 | 14.5018 | 10.0659 | 42.4183 | 19.2833 | 535.2099
503 | 7.3833 | 29.275 | 32.0134 | 8.6887 | 31.6867 | 31.8472 | 31.4417 | 10.6122 | 19.1333 | 9.5685 | 18.734 | 21.8917 | 36.8584 | 19.2452 | 3.087 | 23.6414 | 28.4158 | 5.0049 | 31.6653 | 12.8462 | 17.0473 | 16.8536 | 9.5997 | 35.7938 | 21.2211 | 513.5551
504 | 6.0189 | 39.357 | 26.3431 | 5.7879 | 35.1569 | 38.803 | 25.407 | 11.485 | 16.9968 | 9.527 | 19.233 | 17.657 | 48.2558 | 24.8327 | 2.8285 | 20.6116 | 20.9695 | 4.7256 | 20.9018 | 9.8544 | 26.3036 | 20.8782 | 11.3262 | 41.7954 | 16.2453 | 521.3014
505 | 8.2624 | 33.781 | 31.0164 | 8.0446 | 26.1764 | 27.8385 | 32.9956 | 10.4992 | 10.4491 | 13.0933 | 13.2041 | 20.6933 | 52.3261 | 19.7151 | 3.9632 | 18.7605 | 19.7176 | 5.8608 | 22.5564 | 12.7777 | 21.7341 | 20.5781 | 8.9274 | 27.6323 | 19.1975 | 489.8005
506 | 6.612 | 40.5599 | 25.2166 | 7.4058 | 22.0732 | 45.0253 | 37.7444 | 10.874 | 19.1559 | 15.4474 | 13.9757 | 27.2098 | 29.0209 | 16.35 | 2.6531 | 22.2843 | 37.1648 | 5.8891 | 18.1651 | 12.8127 | 18.7514 | 20.0651 | 9.5866 | 53.5996 | 11.475 | 529.1177
507 | 7.6466 | 37.9975 | 25.4313 | 6.0764 | 34.7914 | 45.911 | 32.7415 | 6.2197 | 19.3585 | 8.3313 | 21.9633 | 20.5221 | 53.763 | 23.2278 | 3.9472 | 22.0234 | 31.9576 | 5.2909 | 19.7668 | 10.3679 | 16.4093 | 21.8237 | 9.7527 | 54.0795 | 18.5096 | 557.9102
508 | 6.4429 | 35.8521 | 28.2871 | 5.9064 | 19.6805 | 48.9414 | 29.71 | 6.5662 | 12.0798 | 11.1217 | 16.6077 | 23.0823 | 40.0935 | 25.5737 | 3.2075 | 25.7962 | 30.3846 | 4.6155 | 24.2706 | 12.0351 | 19.5513 | 20.9447 | 10.749 | 56.7059 | 11.2098 | 529.4154
509 | 6.2184 | 43.9129 | 32.4269 | 6.9913 | 29.3331 | 35.3419 | 38.5781 | 9.3593 | 18.2706 | 12.158 | 21.8637 | 17.6224 | 37.5966 | 19.7936 | 3.614 | 22.6978 | 35.0218 | 4.7153 | 28.7098 | 11.8769 | 14.3878 | 19.3104 | 8.6865 | 56.5718 | 12.3356 | 547.3945
510 | 4.3237 | 42.0899 | 23.1506 | 6.0107 | 28.3786 | 46.858 | 19.7632 | 8.7059 | 15.905 | 10.3039 | 14.0847 | 22.9902 | 48.4137 | 17.7035 | 2.882 | 22.5512 | 30.0928 | 5.96 | 30.546 | 11.7534 | 22.4459 | 14.6693 | 8.2539 | 44.6444 | 19.1098 | 521.5903
511 | 5.7977 | 37.1536 | 28.8055 | 7.6962 | 19.548 | 43.6062 | 18.6434 | 9.128 | 17.5899 | 8.7703 | 16.8515 | 27.4703 | 48.9859 | 19.8794 | 3.5695 | 18.4508 | 32.3362 | 3.3585 | 20.3062 | 12.3019 | 20.7839 | 18.8429 | 10.7986 | 42.242 | 17.6114 | 510.5278
512 | 8.3117 | 48.662 | 17.0476 | 8.6765 | 31.6659 | 39.105 | 31.5956 | 8.9386 | 19.4428 | 12.9628 | 20.4056 | 20.4011 | 49.3011 | 21.2624 | 3.6355 | 20.9127 | 35.0893 | 4.4243 | 29.5909 | 11.837 | 26.2174 | 21.187 | 11.1343 | 52.6669 | 18.8151 | 573.2887
513 | 6.8195 | 34.4617 | 22.0385 | 8.18 | 30.3225 | 46.3604 | 34.117 | 11.6891 | 15.6269 | 12.6476 | 22.0101 | 23.118 | 42.6971 | 20.9955 | 3.5082 | 17.6862 | 30.6799 | 4.9397 | 16.7317 | 13.843 | 22.041 | 20.6497 | 7.6174 | 41.3684 | 11.3284 | 521.4774
514 | 7.1233 | 45.1251 | 32.6388 | 5.7004 | 16.5854 | 40.7789 | 32.8137 | 9.9023 | 14.539 | 8.7432 | 18.7516 | 19.9365 | 34.9535 | 23.6002 | 3.9962 | 22.3163 | 26.5853 | 5.8679 | 28.2893 | 13.2295 | 12.6204 | 18.5352 | 11.5714 | 25.6338 | 18.0802 | 497.9175
515 | 5.9777 | 44.7534 | 31.1275 | 8.4207 | 34.7305 | 35.2717 | 37.6643 | 9.6594 | 16.5094 | 13.4804 | 16.1368 | 26.0382 | 49.3473 | 22.0433 | 2.4194 | 15.9251 | 23.0049 | 5.7585 | 26.5374 | 12.0879 | 23.6197 | 20.2931 | 12.0177 | 53.9658 | 20.1096 | 566.8994
516 | 7.9377 | 40.4387 | 26.3537 | 8.3351 | 26.9863 | 38.392 | 36.9232 | 7.2173 | 11.9732 | 13.1036 | 22.3938 | 19.4521 | 39.8242 | 21.3665 | 3.8325 | 17.8436 | 21.1623 | 3.9289 | 31.3444 | 12.8364 | 22.1595 | 16.4887 | 9.3749 | 49.495 | 20.1236 | 529.2873
517 | 6.38 | 45.6984 | 17.7123 | 6.3346 | 34.8088 | 42.6452 | 30.3131 | 9.1247 | 12.6768 | 15.7337 | 21.0847 | 23.3235 | 46.2801 | 24.4873 | 3.3062 | 25.5288 | 37.7027 | 5.845 | 15.2259 | 12.6286 | 25.8484 | 21.6828 | 11.8999 | 40.5414 | 21.4885 | 558.3013
518 | 6.8764 | 38.3988 | 23.5164 | 8.1969 | 38.2014 | 39.6839 | 21.436 | 9.468 | 16.8565 | 14.1581 | 18.4087 | 19.1654 | 41.6433 | 20.119 | 3.9534 | 24.2604 | 20.9335 | 4.5827 | 18.4841 | 9.3031 | 16.1119 | 15.3746 | 12.0184 | 57.5838 | 12.3577 | 511.0925
519 | 4.3791 | 43.7225 | 31.0327 | 8.4342 | 28.6582 | 44.1684 | 28.2834 | 10.4865 | 15.7488 | 13.5728 | 14.4822 | 25.1713 | 39.8825 | 17.108 | 3.2303 | 18.3909 | 32.6552 | 5.3938 | 25.5743 | 9.8844 | 26.0684 | 16.0202 | 11.3388 | 46.9492 | 17.4651 | 538.1013
520 | 6.7919 | 46.6387 | 20.9089 | 5.9145 | 33.1652 | 46.6002 | 27.3377 | 11.3302 | 15.086 | 13.792 | 16.3042 | 24.3374 | 49.5748 | 22.5723 | 3.3934 | 24.0514 | 35.6675 | 4.1148 | 19.3315 | 9.0825 | 24.5581 | 20.2808 | 10.6603 | 50.5406 | 17.4252 | 559.4602
521 | 7.5599 | 33.2342 | 25.3591 | 6.2404 | 27.2752 | 36.9339 | 34.7631 | 9.4741 | 19.7972 | 11.2961 | 18.5405 | 16.9709 | 38.2401 | 23.0154 | 2.3825 | 17.6069 | 31.0558 | 5.923 | 30.2686 | 12.8288 | 10.812 | 18.9686 | 8.8619 | 53.4071 | 16.6678 | 517.4831
522 | 7.2744 | 38.939 | 24.6263 | 7.488 | 22.0355 | 29.5036 | 21.2538 | 11.4407 | 19.1956 | 12.8642 | 20.2794 | 26 | 46.6066 | 21.9954 | 3.988 | 14.5354 | 28.3767 | 5.3813 | 27.4621 | 10.5037 | 11.0414 | 14.3425 | 12.3032 | 49.337 | 18.4744 | 505.2482
523 | 5.8494 | 33.8731 | 26.8316 | 7.0706 | 26.9095 | 42.4501 | 30.2116 | 10.9095 | 19.8386 | 15.743 | 15.2953 | 25.4563 | 49.7929 | 13.8127 | 2.5495 | 26.6805 | 31.0783 | 5.3697 | 32.7024 | 8.8215 | 18.1799 | 21.6506 | 12.3297 | 29.4531 | 17.8494 | 530.7089
524 | 3.5733 | 20.6446 | 27.4353 | 4.8079 | 33.8466 | 40.327 | 33.9173 | 9.9831 | 19.7237 | 9.4313 | 12.0385 | 15.3965 | 51.8313 | 22.7048 | 2.7097 | 27.4835 | 38.2593 | 5.8182 | 30.0772 | 11.6864 | 24.4974 | 20.4706 | 10.9514 | 50.8994 | 17.9172 | 546.4315
525 | 7.2137 | 31.2914 | 30.5111 | 6.7559 | 33.1268 | 44.066 | 32.962 | 7.4237 | 17.664 | 11.2986 | 21.7919 | 27.7035 | 51.4581 | 22.9354 | 3.2645 | 16.6817 | 25.905 | 3.9101 | 30.6934 | 13.9081 | 17.0697 | 14.6342 | 11.3057 | 46.489 | 14.5243 | 544.5876
526 | 7.3789 | 42.891 | 26.4415 | 7.2065 | 29.4279 | 47.9506 | 28.2435 | 11.1048 | 14.0526 | 9.6096 | 16.3972 | 21.4666 | 48.319 | 18.7795 | 3.3088 | 17.0159 | 29.0987 | 3.9363 | 23.7574 | 11.6295 | 22.5561 | 17.4197 | 8.5923 | 51.7731 | 20.1217 | 538.4788
527 | 7.2447 | 28.6495 | 30.6984 | 7.1488 | 36.9018 | 42.1754 | 31.9862 | 10.5008 | 18.021 | 15.7632 | 17.0736 | 18.3114 | 45.4948 | 25.9367 | 3.919 | 24.1427 | 34.8757 | 5.9509 | 20.3574 | 13.5496 | 17.5519 | 21.3792 | 9.377 | 39.812 | 21.6045 | 548.4262
528 | 6.7832 | 42.0366 | 23.2668 | 5.4729 | 25.8608 | 39.4802 | 25.3543 | 8.2149 | 19.7846 | 11.5636 | 20.7451 | 22.9397 | 51.1307 | 25.8433 | 2.9843 | 23.8954 | 38.9531 | 5.4206 | 22.8054 | 9.4285 | 24.0205 | 18.9477 | 12.3962 | 32.968 | 15.5383 | 535.8347
529 | 5.5341 | 34.6128 | 24.1621 | 7.2395 | 36.2245 | 38.589 | 36.7794 | 11.4294 | 17.9098 | 8.7201 | 22.4213 | 26.1872 | 31.2876 | 22.3303 | 3.5429 | 23.4908 | 30.1116 | 4.2381 | 30.6234 | 13.3764 | 25.9399 | 20.1708 | 8.0111 | 48.0652 | 21.7763 | 552.7736
530 | 6.5438 | 48.5274 | 32.0566 | 8.5361 | 32.2225 | 46.5294 | 29.8425 | 7.7845 | 18.9287 | 13.8341 | 11.3054 | 22.2252 | 39.3744 | 16.6468 | 3.7619 | 20.2292 | 34.3494 | 5.3157 | 32.7718 | 7.7998 | 24.9 | 19.831 | 11.4268 | 55.2332 | 22.2972 | 572.2732
531 | 5.2493 | 29.671 | 31.3199 | 8.112 | 33.3736 | 49.2974 | 36.6788 | 3.8836 | 19.7725 | 11.0789 | 15.5934 | 27.9072 | 49.7595 | 25.4128 | 3.8145 | 25.759 | 31.6888 | 5.7545 | 21.8559 | 9.5924 | 19.9002 | 18.5591 | 10.8389 | 54.9184 | 15.1881 | 564.9797
532 | 5.9747 | 38.2263 | 21.8476 | 6.2904 | 37.8265 | 26.1958 | 36.4898 | 11.7265 | 19.1312 | 14.0898 | 12.6434 | 21.646 | 37.2068 | 19.9938 | 3.406 | 27.749 | 31.1779 | 5.5923 | 20.6415 | 8.2673 | 22.0074 | 14.3712 | 9.4941 | 32.5168 | 19.3905 | 503.9029
533 | 7.0189 | 48.2344 | 22.534 | 5.1425 | 27.4973 | 48.2762 | 28.8031 | 10.8262 | 18.1186 | 15.2491 | 17.1941 | 23.3619 | 34.5794 | 21.9129 | 3.2673 | 17.1802 | 33.8556 | 5.4008 | 31.4007 | 13.9292 | 16.4176 | 19.1206 | 8.0189 | 55.6355 | 14.289 | 547.2641
534 | 6.8662 | 40.8577 | 24.4603 | 7.9392 | 31.6906 | 37.5592 | 33.5616 | 6.152 | 18.2232 | 10.3386 | 15.3641 | 25.7777 | 49.9428 | 22.2849 | 2.7689 | 21.2964 | 29.2933 | 4.516 | 19.501 | 11.3316 | 24.1603 | 17.3938 | 9.4784 | 53.0634 | 16.8252 | 540.6463
535 | 7.0654 | 31.4046 | 21.7661 | 7.0432 | 38.3602 | 51.0297 | 25.3805 | 11.4143 | 17.584 | 13.6763 | 19.0251 | 22.3786 | 46.9355 | 23.7691 | 3.8129 | 20.4893 | 20.9225 | 4.8119 | 30.7336 | 13.1811 | 22.6953 | 18.4958 | 10.3971 | 46.8618 | 18.1482 | 547.3821
536 | 4.2337 | 45.885 | 33.5079 | 6.865 | 24.3488 | 45.3072 | 31.1134 | 11.4248 | 12.2366 | 12.1937 | 21.6976 | 19.3145 | 34.4958 | 22.3451 | 3.7725 | 22.7513 | 33.2696 | 5.8106 | 30.4619 | 13.566 | 21.6676 | 15.6808 | 10.5346 | 52.6823 | 17.8528 | 553.0187
537 | 7.7331 | 26.3725 | 22.4659 | 8.3045 | 31.489 | 47.8938 | 34.6611 | 10.1648 | 17.8331 | 16.0374 | 16.7974 | 18.2419 | 54.2646 | 24.2713 | 3.9927 | 22.7527 | 30.2091 | 5.5931 | 19.5449 | 12.2585 | 20.4864 | 17.2501 | 8.85 | 46.0435 | 14.0908 | 537.6023
538 | 7.304 | 48.7502 | 27.5568 | 8.6601 | 20.0035 | 38.6462 | 23.2332 | 11.5934 | 17.4265 | 16.6658 | 20.1797 | 23.5456 | 52.1471 | 20.4316 | 3.4151 | 17.009 | 30.9219 | 3.6877 | 28.6333 | 13.5282 | 17.5796 | 13.0476 | 12.2682 | 52.6495 | 15.0833 | 543.9672
539 | 7.9776 | 41.9716 | 28.1682 | 5.1012 | 18.8222 | 52.3343 | 33.993 | 11.3753 | 16.6412 | 10.9235 | 21.5905 | 22.5494 | 21.5921 | 22.1476 | 3.7984 | 23.1543 | 27.9758 | 5.8888 | 26.5383 | 12.1089 | 18.6184 | 21.4052 | 10.651 | 50.4649 | 14.4213 | 530.2131
540 | 8.2422 | 28.6451 | 29.1375 | 8.622 | 32.0631 | 45.072 | 23.2866 | 10.7446 | 18.1155 | 16.7729 | 19.74 | 22.4717 | 47.9384 | 25.1865 | 3.6148 | 24.9931 | 33.3721 | 5.5609 | 32.8548 | 13.2041 | 16.3968 | 17.0626 | 9.4384 | 23.4837 | 17.2918 | 533.3112
541 | 7.205 | 47.1317 | 26.7502 | 8.4426 | 32.8395 | 44.9654 | 27.5431 | 8.7958 | 18.1522 | 11.6297 | 16.9995 | 20.8416 | 45.5308 | 18.9138 | 2.892 | 22.8771 | 27.0958 | 5.0259 | 23.8386 | 11.8857 | 21.3332 | 19.5323 | 12.1289 | 52.1503 | 17.4004 | 551.901
542 | 6.9881 | 34.4555 | 26.8545 | 7.6771 | 27.0765 | 49.4394 | 32.6855 | 10.0269 | 19.0091 | 14.0173 | 19.9619 | 23.0239 | 47.0711 | 20.3512 | 3.5798 | 24.4286 | 30.5061 | 4.7576 | 31.2096 | 12.9717 | 22.7164 | 21.4556 | 7.3801 | 37.426 | 21.3244 | 556.3938
543 | 6.6787 | 43.258 | 20.4166 | 5.8799 | 25.627 | 49.4582 | 30.8466 | 11.4964 | 12.3865 | 13.5808 | 13.2868 | 19.3322 | 25.7355 | 24.9562 | 2.9298 | 25.4616 | 33.5896 | 3.5835 | 27.4903 | 13.3345 | 18.8263 | 21.0366 | 10.0861 | 36.9612 | 12.7991 | 509.0381
544 | 5.748 | 48.556 | 30.8729 | 7.0135 | 23.6297 | 51.1165 | 30.997 | 8.4978 | 16.5731 | 16.4074 | 20.8214 | 21.2416 | 37.7401 | 17.2477 | 2.9111 | 22.5045 | 29.7985 | 3.7087 | 32.2873 | 10.6504 | 17.7488 | 14.1757 | 7.9971 | 40.7267 | 21.9177 | 540.8893
545 | 8.2483 | 47.1289 | 26.5333 | 8.1344 | 37.2208 | 45.5691 | 24.8633 | 11.0794 | 19.9348 | 12.2615 | 12.9973 | 18.0856 | 49.7337 | 24.8729 | 3.5934 | 26.7003 | 36.2352 | 5.5301 | 23.8699 | 12.0869 | 19.7985 | 20.0885 | 10.4435 | 46.8728 | 21.6717 | 573.5543
546 | 7.0371 | 33.0368 | 30.99 | 6.0105 | 21.2792 | 49.3052 | 25.7465 | 11.7818 | 15.5531 | 16.256 | 19.4408 | 15.2604 | 50.8368 | 21.337 | 3.8461 | 26.2887 | 37.48 | 5.5806 | 17.7975 | 11.3331 | 16.8603 | 18.3993 | 11.2156 | 35.8911 | 11.3412 | 519.9049
547 | 7.741 | 45.9446 | 30.4482 | 7.4655 | 27.5792 | 49.1819 | 25.5431 | 9.963 | 15.2553 | 16.2053 | 11.8663 | 16.8461 | 38.0372 | 19.4879 | 3.7822 | 26.3425 | 18.8176 | 5.7448 | 24.2025 | 13.8051 | 25.2447 | 21.2957 | 10.2585 | 44.242 | 21.3677 | 536.6678
548 | 7.5761 | 41.3657 | 23.9264 | 4.8456 | 35.388 | 37.5034 | 34.2162 | 8.951 | 16.7935 | 11.9671 | 20.8664 | 15.5124 | 22.8123 | 25.8808 | 3.7252 | 19.9091 | 28.4464 | 4.9516 | 25.2592 | 12.7204 | 24.0655 | 17.2314 | 10.9753 | 31.1379 | 19.3192 | 505.3461
549 | 7.6134 | 41.4199 | 20.8395 | 8.788 | 29.4507 | 48.3786 | 20.4471 | 9.7329 | 18.5113 | 9.5884 | 22.0815 | 15.3863 | 51.6545 | 24.3759 | 2.758 | 24.1864 | 36.553 | 5.7707 | 29.2547 | 12.7952 | 26.2503 | 19.6277 | 11.3903 | 49.4473 | 9.8683 | 556.1698
550 | 7.1824 | 43.0073 | 17.5486 | 7.9802 | 27.9712 | 51.2714 | 37.624 | 10.4917 | 11.8803 | 11.626 | 12.7748 | 21.8982 | 38.4643 | 25.2147 | 3.0665 | 15.5105 | 31.5048 | 5.8708 | 23.9286 | 11.1788 | 16.2773 | 20.8834 | 7.8603 | 47.9583 | 22.0787 | 531.0532
551 | 7.5561 | 40.0695 | 26.3913 | 6.0077 | 31.4875 | 49.3083 | 30.0905 | 11.117 | 19.7794 | 15.5073 | 17.6452 | 15.3584 | 42.5075 | 21.6098 | 2.6888 | 23.6161 | 33.3946 | 5.7871 | 27.9778 | 11.7222 | 26.3447 | 21.5795 | 10.9249 | 43.9673 | 15.2059 | 557.6442
552 | 7.1843 | 28.3623 | 30.3115 | 7.4792 | 33.9298 | 52.1517 | 37.671 | 8.8692 | 19.6266 | 12.0399 | 21.7905 | 17.7531 | 34.3411 | 22.8137 | 3.7789 | 20.0455 | 18.8598 | 5.9692 | 27.2279 | 10.4276 | 25.6031 | 21.966 | 10.3256 | 56.185 | 17.5927 | 552.3052
553 | 5.405 | 34.2882 | 20.8396 | 7.9088 | 35.1459 | 43.2959 | 26.5311 | 6.5065 | 19.5231 | 10.4174 | 21.1635 | 25.597 | 54.6776 | 21.3261 | 3.8032 | 27.4323 | 22.1169 | 5.5152 | 29.1931 | 12.7315 | 22.7657 | 15.1184 | 10.2156 | 56.4065 | 18.9007 | 556.825
554 | 8.0711 | 38.6883 | 27.3773 | 7.8711 | 18.5357 | 51.0001 | 30.7278 | 9.4723 | 19.6163 | 15.9737 | 17.6335 | 19.5915 | 36.5047 | 23.7658 | 3.7485 | 22.714 | 24.1062 | 5.7293 | 25.0389 | 10.936 | 19.5836 | 21.4123 | 10.3296 | 54.4406 | 15.8629 | 538.7312
555 | 7.3936 | 29.7859 | 27.7818 | 7.3227 | 34.363 | 43.307 | 25.9824 | 9.0538 | 11.7201 | 15.3421 | 22.3032 | 19.3314 | 32.442 | 24.4996 | 3.2148 | 18.4806 | 37.2563 | 5.9845 | 23.4914 | 11.9433 | 21.384 | 19.1862 | 12.2403 | 21.8961 | 21.8667 | 507.573
556 | 5.5812 | 30.5768 | 23.6441 | 5.7196 | 36.7083 | 48.6708 | 37.4344 | 10.0392 | 19.5976 | 9.3908 | 21.4625 | 24.8969 | 47.3085 | 25.687 | 3.7559 | 22.8577 | 27.036 | 5.4154 | 22.9707 | 12.6293 | 19.8809 | 18.4131 | 9.3901 | 49.2628 | 12.4718 | 550.8013
557 | 4.1994 | 40.2103 | 31.9438 | 7.4845 | 39.1327 | 41.9185 | 33.8619 | 9.4563 | 19.569 | 14.5068 | 17.6318 | 22.8638 | 51.5427 | 23.1188 | 3.2456 | 17.4713 | 39.0167 | 4.3636 | 30.0012 | 11.9405 | 18.4304 | 13.7694 | 8.1058 | 43.7122 | 21.797 | 569.2938
558 | 7.6788 | 36.7148 | 26.2237 | 8.7095 | 34.0605 | 44.0051 | 33.3233 | 10.3061 | 17.6674 | 16.3475 | 18.626 | 21.5446 | 54.1793 | 24.8339 | 3.8252 | 19.4338 | 32.9193 | 4.0082 | 25.9537 | 12.9981 | 20.8674 | 16.1401 | 9.3195 | 52.6183 | 15.9895 | 568.2935
559 | 4.8588 | 44.4003 | 18.0376 | 7.3807 | 28.071 | 49.8386 | 32.6123 | 10.3339 | 15.0682 | 15.1577 | 16.2914 | 21.7593 | 54.2745 | 23.5991 | 3.8295 | 25.4834 | 35.7595 | 5.3904 | 24.0873 | 12.672 | 20.1082 | 13.3199 | 6.3468 | 50.55 | 16.7805 | 556.0111
560 | 7.9032 | 35.1276 | 21.3955 | 6.9468 | 35.9886 | 33.6775 | 19.5131 | 8.6876 | 13.865 | 14.8598 | 22.0308 | 19.2206 | 44.2812 | 23.9178 | 2.9505 | 21.237 | 28.5063 | 5.8902 | 24.2387 | 13.9554 | 23.5629 | 14.8259 | 8.7369 | 47.2776 | 14.3395 | 512.9359
561 | 5.8998 | 40.3378 | 31.6541 | 8.0732 | 31.9963 | 47.0247 | 36.6978 | 9.3647 | 17.7773 | 11.9887 | 19.1121 | 25.2277 | 49.7654 | 20.1511 | 3.3108 | 23.7172 | 38.0921 | 5.6355 | 28.9931 | 12.3149 | 23.1354 | 14.4955 | 11.7772 | 48.4015 | 20.9061 | 585.8502
562 | 7.8801 | 33.5052 | 25.999 | 7.2375 | 20.3436 | 28.3767 | 32.6742 | 11.4176 | 14.4967 | 16.1869 | 17.0535 | 19.6212 | 39.268 | 22.8427 | 3.9808 | 25.8649 | 32.7135 | 4.0478 | 26.8823 | 11.8147 | 20.7851 | 18.5708 | 11.7995 | 41.4876 | 15.5882 | 510.4382
563 | 6.5082 | 43.0054 | 30.5596 | 8.6927 | 30.733 | 50.7006 | 37.3953 | 11.1715 | 19.0839 | 11.3431 | 20.1694 | 22.9604 | 42.2871 | 18.985 | 3.8758 | 18.0554 | 37.7515 | 4.3634 | 25.5554 | 10.7327 | 17.4414 | 21.2674 | 8.268 | 55.0465 | 16.1202 | 572.0731
564 | 6.6815 | 38.5669 | 29.542 | 8.4904 | 37.7787 | 37.7091 | 31.3407 | 10.6734 | 19.2623 | 11.9277 | 19.2735 | 26.1151 | 44.9995 | 23.2732 | 2.8317 | 25.803 | 38.0677 | 5.2757 | 24.9086 | 11.9748 | 25.2344 | 17.4374 | 9.7133 | 56.5103 | 12.2427 | 575.6335
565 | 5.7495 | 31.8262 | 26.1289 | 7.9667 | 28.8349 | 51.6334 | 16.1747 | 11.1316 | 16.9255 | 12.1895 | 10.3116 | 26.6258 | 45.3712 | 25.5728 | 3.4274 | 21.8754 | 28.3372 | 4.8163 | 23.6714 | 13.6295 | 22.5224 | 11.6605 | 11.0263 | 48.4315 | 20.902 | 526.7423
566 | 7.2373 | 43.6931 | 33.0659 | 7.0382 | 34.6679 | 48.4051 | 36.7341 | 9.2731 | 19.8691 | 10.6238 | 21.6522 | 23.6234 | 45.5809 | 21.5078 | 2.4438 | 22.099 | 35.1626 | 5.786 | 29.5812 | 10.1985 | 22.1691 | 15.3146 | 9.7891 | 44.0883 | 15.1946 | 574.7988
567 | 3.4983 | 36.7058 | 31.9414 | 7.4544 | 33.8427 | 52.2366 | 38.172 | 5.3449 | 12.3356 | 14.6349 | 19.2167 | 18.7532 | 54.9572 | 20.4482 | 3.8956 | 20.667 | 35.4152 | 5.6321 | 24.2118 | 10.4212 | 25.0654 | 15.5812 | 10.7 | 48.2614 | 15.8819 | 565.2746
568 | 6.3317 | 40.4858 | 19.664 | 7.7801 | 17.9918 | 50.5887 | 29.3287 | 7.9506 | 19.8087 | 11.4756 | 19.8525 | 28.6197 | 50.278 | 17.2931 | 3.3066 | 25.0503 | 36.5988 | 3.5071 | 32.4869 | 9.6943 | 24.6052 | 20.2858 | 5.9191 | 54.2515 | 17.916 | 561.0706
569 | 5.8496 | 32.8858 | 24.035 | 8.1505 | 32.2575 | 46.5158 | 32.8859 | 10.7517 | 19.5561 | 10.8091 | 17.3733 | 28.4836 | 54.0511 | 18.3486 | 3.545 | 20.0042 | 29.2986 | 5.7835 | 31.3714 | 12.72 | 25.3027 | 20.4736 | 9.6847 | 51.0739 | 18.6949 | 569.9062
570 | 7.6595 | 40.9037 | 27.609 | 8.781 | 33.7779 | 33.3367 | 34.6919 | 10.3021 | 15.941 | 15.496 | 15.4076 | 19.6198 | 44.7025 | 21.5496 | 3.6268 | 23.7723 | 30.6637 | 4.786 | 29.4389 | 11.7837 | 26.8683 | 20.7143 | 10.0586 | 54.5383 | 20.2037 | 566.233
571 | 6.2569 | 37.123 | 30.6009 | 5.4367 | 26.6236 | 43.54 | 23.7917 | 8.8351 | 16.9491 | 15.5469 | 18.8925 | 16.1069 | 48.122 | 24.6198 | 3.5303 | 17.2555 | 26.123 | 5.903 | 22.0084 | 8.7403 | 16.0932 | 18.4357 | 12.2166 | 54.821 | 14.0607 | 521.633
572 | 7.6398 | 35.5706 | 26.8471 | 8.2351 | 33.8402 | 43.2183 | 35.7641 | 5.9418 | 18.2825 | 16.3665 | 21.0384 | 27.1938 | 45.2474 | 19.9527 | 3.8021 | 17.5712 | 29.1431 | 4.5678 | 20.037 | 12.4271 | 23.0799 | 18.8058 | 10.8249 | 38.0957 | 22.2502 | 545.7431
573 | 5.8858 | 37.5515 | 21.1128 | 7.2344 | 34.3633 | 30.7644 | 29.2013 | 8.7358 | 14.9318 | 16.4067 | 21.0434 | 27.8629 | 46.4694 | 22.2362 | 3.6327 | 16.3172 | 21.8281 | 5.2966 | 29.7458 | 13.8925 | 20.5299 | 18.5426 | 10.8807 | 51.6186 | 19.6575 | 535.7419
574 | 7.3125 | 26.9592 | 29.3529 | 8.1464 | 29.3241 | 37.5352 | 33.8466 | 9.693 | 19.1224 | 12.9019 | 19.256 | 26.0866 | 41.8912 | 25.3697 | 3.8399 | 23.7007 | 33.3443 | 4.5265 | 25.7955 | 13.4876 | 22.7111 | 21.149 | 7.3658 | 43.8595 | 16.7826 | 543.3604
575 | 7.3452 | 26.1631 | 32.0629 | 7.8841 | 26.8541 | 26.0274 | 32.673 | 9.1558 | 17.733 | 11.8599 | 15.2045 | 22.276 | 48.0996 | 18.4408 | 3.2492 | 27.3077 | 32.2802 | 4.2288 | 27.7083 | 12.0826 | 12.309 | 15.6178 | 7.8078 | 34.9844 | 21.9462 | 501.3015
576 | 6.3042 | 44.6725 | 32.797 | 6.5734 | 34.5721 | 46.6399 | 33.065 | 10.0898 | 18.262 | 11.2295 | 19.2647 | 19.2926 | 32.0773 | 23.3966 | 3.6674 | 21.9254 | 21.1205 | 5.2632 | 27.0055 | 13.8998 | 21.4846 | 21.7595 | 9.2308 | 50.4339 | 17.798 | 551.8254
577 | 7.2944 | 42.964 | 29.3469 | 6.3125 | 24.8218 | 45.661 | 25.9846 | 9.3931 | 17.8011 | 15.1569 | 17.2867 | 27.0028 | 40.9396 | 22.7844 | 2.8339 | 24.536 | 35.5076 | 5.7779 | 23.9412 | 13.3933 | 19.4724 | 19.5465 | 9.9383 | 37.9886 | 20.6623 | 546.3477
578 | 7.7423 | 44.1022 | 32.8505 | 8.3173 | 30.8052 | 47.5729 | 31.3152 | 10.2714 | 19.7094 | 14.3505 | 18.735 | 21.9751 | 47.0091 | 24.7498 | 2.772 | 20.6759 | 27.6907 | 5.9829 | 29.374 | 10.8209 | 21.0884 | 21.1275 | 8.4707 | 52.3129 | 20.368 | 580.19
579 | 7.3708 | 40.1074 | 29.9061 | 7.6575 | 25.1682 | 46.6912 | 28.298 | 10.2408 | 16.4111 | 14.1897 | 20.2504 | 15.724 | 45.6956 | 15.9232 | 3.3149 | 18.0111 | 28.9597 | 4.3901 | 24.1327 | 8.8882 | 22.0251 | 21.1213 | 12.4306 | 42.3094 | 13.4945 | 522.7116
580 | 6.1509 | 38.1944 | 31.5195 | 5.6156 | 27.253 | 38.1723 | 31.8752 | 6.8166 | 15.6863 | 14.9887 | 10.974 | 22.9615 | 42.2909 | 14.4119 | 3.2011 | 25.0773 | 25.2955 | 5.3751 | 26.8344 | 8.8513 | 17.5669 | 17.0056 | 8.7782 | 52.8969 | 20.2035 | 517.9968
581 | 7.541 | 45.9593 | 26.5978 | 8.1561 | 26.7796 | 45.9239 | 37.3911 | 10.9985 | 18.892 | 16.239 | 20.7609 | 24.9902 | 27.1125 | 18.9989 | 3.5711 | 20.7964 | 34.5232 | 4.9596 | 31.5232 | 10.0042 | 19.5749 | 16.2816 | 12.2783 | 48.8983 | 17.9453 | 556.6969
582 | 5.1289 | 33.1508 | 29.4716 | 7.7377 | 35.5888 | 38.1595 | 26.226 | 7.8726 | 19.9433 | 13.5667 | 16.6909 | 18.3299 | 47.1278 | 23.9702 | 2.7022 | 17.1534 | 35.6302 | 3.6304 | 20.8648 | 9.8396 | 15.0048 | 18.3586 | 10.8497 | 45.2155 | 18.3485 | 520.5625
583 | 4.0913 | 28.0878 | 16.0861 | 8.5819 | 19.3397 | 46.8409 | 20.94 | 10.4532 | 15.1982 | 15.2432 | 20.5196 | 20.1562 | 40.3764 | 24.7094 | 2.9887 | 20.4248 | 35.7838 | 5.3526 | 29.8543 | 9.7733 | 17.0471 | 16.8124 | 11.9193 | 43.4835 | 16.2489 | 500.3127
584 | 8.0954 | 26.2081 | 21.8347 | 7.8226 | 25.1507 | 50.5421 | 38.3146 | 11.7527 | 14.0641 | 12.5672 | 21.4145 | 26.92 | 55.8909 | 21.9187 | 3.8237 | 20.9549 | 35.1016 | 5.9263 | 21.626 | 9.6616 | 23.3638 | 18.18 | 8.5747 | 49.3731 | 17.1635 | 556.2454
585 | 6.8764 | 33.2786 | 31.5882 | 8.6973 | 26.1577 | 46.5466 | 27.8447 | 7.551 | 16.2669 | 10.5137 | 22.3962 | 20.6976 | 37.3365 | 24.692 | 3.6075 | 17.5714 | 22.7137 | 5.881 | 19.8902 | 11.9015 | 19.6509 | 21.9491 | 8.0773 | 33.5955 | 17.6615 | 502.943
586 | 4.61 | 40.3936 | 21.4425 | 7.8722 | 28.8684 | 39.9561 | 35.9049 | 7.7449 | 15.9481 | 11.5578 | 19.6728 | 15.1756 | 55.0657 | 19.864 | 3.9116 | 23.2284 | 36.5324 | 5.9706 | 29.5316 | 13.6937 | 22.0361 | 13.4758 | 10.9574 | 32.3641 | 17.1762 | 532.9545
587 | 4.8084 | 44.8423 | 25.2858 | 5.349 | 23.2304 | 41.5979 | 30.0361 | 7.765 | 17.1693 | 14.3613 | 22.4517 | 16.8761 | 43.2422 | 21.1218 | 3.5605 | 25.9406 | 27.2505 | 5.5632 | 29.4405 | 13.7513 | 19.7134 | 16.8112 | 10.8488 | 57.8438 | 14.1725 | 543.0338
588 | 5.2247 | 30.461 | 29.4887 | 7.3626 | 34.6524 | 43.6245 | 26.032 | 7.1315 | 15.2163 | 13.1329 | 16.1257 | 20.3986 | 28.1937 | 24.3513 | 3.945 | 16.8735 | 29.1986 | 5.8478 | 30.4191 | 10.0599 | 19.8594 | 19.8968 | 7.8492 | 52.3227 | 19.0431 | 516.7109
589 | 5.9911 | 42.4333 | 21.8033 | 8.1968 | 36.843 | 51.7792 | 35.7244 | 11.4372 | 18.715 | 16.6452 | 19.4492 | 17.002 | 47.2049 | 17.095 | 3.455 | 21.5896 | 34.9979 | 5.9835 | 26.0536 | 12.858 | 10.8147 | 14.7414 | 11.5913 | 40.155 | 19.2108 | 551.7704
590 | 7.7826 | 46.2047 | 24.6065 | 6.3527 | 31.8914 | 33.3488 | 32.919 | 10.5442 | 15.2572 | 8.8447 | 17.7717 | 20.3145 | 47.2086 | 20.0766 | 3.0517 | 15.0892 | 37.0547 | 5.6532 | 27.003 | 11.9443 | 23.0021 | 13.6494 | 11.3138 | 45.6737 | 18.9547 | 535.513
591 | 7.9175 | 45.1209 | 19.8417 | 7.8521 | 25.9468 | 29.3889 | 24.8037 | 7.6088 | 15.424 | 10.4272 | 21.0726 | 25.7023 | 51.3223 | 25.1295 | 3.9816 | 24.4522 | 38.0564 | 5.4456 | 24.0793 | 10.581 | 18.9356 | 20.9083 | 8.5896 | 42.9932 | 20.8054 | 536.3865
592 | 7.6078 | 34.2868 | 28.2135 | 6.5987 | 27.5938 | 49.0558 | 36.4437 | 10.762 | 13.3147 | 15.4069 | 12.8796 | 21.8915 | 51.5251 | 25.299 | 3.0481 | 24.9957 | 21.2695 | 5.2486 | 21.3762 | 12.9983 | 17.561 | 20.9404 | 8.7405 | 56.9882 | 13.2895 | 547.335
593 | 6.4733 | 39.4505 | 30.881 | 8.7595 | 32.368 | 32.7698 | 34.981 | 7.0984 | 15.9744 | 13.9096 | 16.7571 | 19.3058 | 49.4311 | 18.4041 | 3.6671 | 20.0122 | 28.394 | 5.9119 | 31.769 | 13.5573 | 21.1135 | 16.5063 | 12.0632 | 49.9822 | 20.3755 | 549.9158
594 | 6.4597 | 40.3772 | 22.0858 | 7.881 | 26.8012 | 41.8145 | 33.7243 | 9.4508 | 12.7163 | 10.2077 | 16.5356 | 21.5358 | 50.9916 | 15.0315 | 3.171 | 19.7031 | 32.3718 | 5.9528 | 26.9731 | 11.1991 | 23.6783 | 18.3773 | 8.4029 | 41.1596 | 20.6499 | 527.252
595 | 5.671 | 47.3582 | 32.561 | 8.4629 | 22.8397 | 37.5947 | 17.6921 | 8.0342 | 11.9399 | 11.0498 | 20.1396 | 25.2136 | 37.1765 | 19.7881 | 3.0528 | 22.0271 | 35.8633 | 5.519 | 31.4218 | 9.355 | 20.3401 | 20.4062 | 10.5142 | 50.462 | 15.2562 | 529.7387
596 | 6.6582 | 40.6839 | 19.4208 | 8.2996 | 26.9655 | 45.5542 | 36.5413 | 10.6772 | 18.1938 | 14.9833 | 20.5035 | 24.6988 | 54.3842 | 21.2239 | 3.4639 | 25.9651 | 33.8969 | 3.9327 | 25.6476 | 9.9784 | 24.3973 | 14.1819 | 7.7889 | 52.3143 | 21.1111 | 571.4665
597 | 6.2543 | 34.7806 | 31.1164 | 6.9118 | 33.8466 | 32.1225 | 36.8091 | 8.732 | 19.3507 | 14.8026 | 12.6298 | 27.3352 | 21.2245 | 23.7952 | 2.9169 | 25.6756 | 31.08 | 5.9188 | 26.4089 | 13.3912 | 15.9884 | 16.0382 | 10.8905 | 33.9132 | 21.7606 | 513.6935
598 | 5.0248 | 45.5031 | 32.4962 | 6.4948 | 17.1669 | 48.5198 | 34.3367 | 8.6644 | 19.0931 | 8.1202 | 20.2611 | 13.7789 | 29.4161 | 23.9639 | 2.5137 | 27.4747 | 22.0642 | 5.2194 | 31.5236 | 10.8594 | 15.9861 | 21.6344 | 11.2327 | 57.9796 | 19.5256 | 538.8535
599 | 7.8167 | 38.679 | 28.3684 | 6.8932 | 26.6759 | 43.3243 | 27.5914 | 8.0562 | 17.1473 | 16.467 | 18.2088 | 14.8282 | 38.3548 | 17.1304 | 3.2321 | 24.5723 | 26.4143 | 4.9145 | 30.5401 | 13.3425 | 21.603 | 17.1819 | 12.168 | 41.3115 | 21.7238 | 526.5456
600 | 6.1967 | 43.4419 | 25.1794 | 8.1881 | 38.6638 | 44.6511 | 25.6409 | 6.192 | 12.7 | 16.4558 | 13.0272 | 23.9368 | 44.1627 | 23.0557 | 3.2494 | 25.0396 | 31.1576 | 4.9545 | 20.2071 | 10.8097 | 21.0983 | 18.6048 | 10.7438 | 41.1128 | 14.777 | 533.2468
601 | 7.575 | 43.7227 | 24.8155 | 6.2289 | 32.3559 | 39.3686 | 36.2427 | 9.822 | 14.053 | 11.283 | 21.2988 | 20.3049 | 42.2827 | 21.9149 | 3.8906 | 25.7444 | 25.2854 | 5.1013 | 30.1144 | 12.5662 | 22.4004 | 20.6704 | 11.8495 | 53.7349 | 19.3739 | 562.0002
602 | 6.8845 | 39.1015 | 32.0122 | 7.1433 | 31.7235 | 48.0338 | 30.1747 | 9.5071 | 17.9913 | 15.9045 | 19.8216 | 15.9946 | 54.5401 | 22.4584 | 2.5009 | 22.7306 | 36.0709 | 3.9417 | 28.5355 | 12.5443 | 25.6006 | 20.6767 | 11.8377 | 53.2813 | 12.3324 | 581.3437
603 | 7.594 | 36.9259 | 29.6331 | 8.7027 | 29.6428 | 39.3411 | 30.0842 | 10.2737 | 17.0788 | 16.4536 | 17.0516 | 27.8153 | 48.0749 | 19.9583 | 3.8177 | 25.7485 | 27.7585 | 4.7222 | 30.3623 | 12.8677 | 24.8319 | 20.8883 | 5.6765 | 42.6492 | 18.3673 | 556.3201
604 | 7.5041 | 45.4865 | 28.115 | 4.876 | 33.8176 | 49.0432 | 25.4124 | 10.5505 | 14.5613 | 12.9681 | 12.9994 | 20.5482 | 30.4521 | 22.7439 | 3.8867 | 18.0032 | 37.1558 | 5.2279 | 31.602 | 11.5011 | 23.7302 | 11.4817 | 10.7156 | 48.9889 | 17.8613 | 539.2328
605 | 6.2204 | 43.5896 | 28.8304 | 7.451 | 35.6316 | 43.2819 | 28.799 | 11.7657 | 16.5519 | 10.5721 | 16.0094 | 23.4568 | 51.3616 | 23.4549 | 3.3783 | 22.6949 | 35.0818 | 5.495 | 32.7699 | 9.9038 | 15.8657 | 21.577 | 10.498 | 46.7116 | 20.966 | 571.9184
606 | 7.3822 | 44.7826 | 28.7566 | 5.4351 | 32.9067 | 39.6665 | 37.8434 | 9.3219 | 15.8324 | 11.8331 | 19.4262 | 18.7104 | 37.83 | 22.8364 | 3.631 | 24.5086 | 21.2766 | 5.2662 | 22.2838 | 10.4321 | 14.0437 | 18.1282 | 9.3896 | 41.2516 | 20.7358 | 523.5107
607 | 6.8723 | 47.2635 | 26.7269 | 8.5734 | 30.9179 | 35.5003 | 37.2171 | 11.9671 | 12.8315 | 10.3843 | 14.3992 | 25.833 | 48.4918 | 23.6093 | 3.886 | 17.2859 | 27.5294 | 5.9063 | 17.1201 | 12.5096 | 21.9692 | 21.4325 | 9.4043 | 38.3633 | 19.6763 | 535.6705
608 | 8.2882 | 48.0192 | 28.7863 | 7.8619 | 36.544 | 32.0805 | 26.6265 | 7.1807 | 17.4741 | 16.0723 | 21.4948 | 22.5413 | 18.8784 | 16.6771 | 3.9527 | 22.8752 | 38.0146 | 4.7901 | 22.5626 | 12.901 | 20.7881 | 21.9003 | 10.6876 | 52.8967 | 17.599 | 537.4934
609 | 4.8966 | 34.7021 | 32.2353 | 7.2793 | 23.5869 | 39.199 | 34.0854 | 9.8671 | 12.5037 | 15.8704 | 19.9226 | 25.6706 | 50.2282 | 22.1883 | 2.953 | 24.2879 | 25.4795 | 4.4671 | 31.8796 | 9.5058 | 22.1986 | 14.5334 | 12.4872 | 47.191 | 20.16 | 547.3787
610 | 5.976 | 44.7936 | 24.9131 | 6.6052 | 33.1672 | 45.1916 | 29.4944 | 7.0043 | 18.6753 | 16.2789 | 17.3861 | 21.2525 | 52.9161 | 19.8335 | 3.2321 | 13.5916 | 31.7175 | 5.7537 | 17.5555 | 11.1508 | 16.3405 | 20.6179 | 11.787 | 59.556 | 12.8463 | 547.6367
611 | 5.1442 | 28.5613 | 25.2412 | 6.6714 | 34.7642 | 44.1723 | 33.5042 | 10.7288 | 13.7329 | 13.2275 | 17.8434 | 23.8985 | 51.8707 | 17.8437 | 3.8014 | 27.821 | 34.6715 | 5.825 | 31.0957 | 13.8314 | 17.6452 | 21.2632 | 9.0642 | 57.2101 | 14.8423 | 564.2752
612 | 6.237 | 43.3462 | 18.1038 | 5.6247 | 38.5824 | 23.8786 | 23.3961 | 7.1237 | 18.0611 | 12.2476 | 14.2745 | 18.6151 | 38.9642 | 25.242 | 2.4541 | 22.6499 | 38.2732 | 5.3073 | 24.872 | 10.8373 | 21.9504 | 15.5134 | 10.9422 | 52.2279 | 19.6292 | 518.3539
613 | 5.9515 | 41.2362 | 29.3543 | 6.6772 | 31.9438 | 41.2587 | 36.1449 | 10.9961 | 15.7222 | 15.4378 | 10.591 | 25.8554 | 49.7901 | 23.149 | 2.9976 | 25.2276 | 32.1424 | 5.4106 | 32.8282 | 12.6206 | 23.8141 | 21.1843 | 12.3578 | 55.7301 | 22.0179 | 590.4393
614 | 6.7029 | 31.9649 | 32.8456 | 7.8109 | 28.3377 | 47.6398 | 31.1893 | 8.3405 | 14.718 | 8.2916 | 21.919 | 25.473 | 36.4486 | 13.8029 | 3.0669 | 26.0252 | 31.7263 | 4.7822 | 26.0092 | 13.474 | 21.0945 | 20.2167 | 9.0827 | 50.7086 | 14.6201 | 536.2911
615 | 8.3453 | 46.3987 | 19.5994 | 7.0499 | 25.6622 | 50.3858 | 33.135 | 9.6356 | 15.7425 | 13.782 | 18.5832 | 17.3556 | 29.6399 | 20.9096 | 3.7129 | 16.9465 | 36.3149 | 3.6722 | 19.7202 | 10.4543 | 20.7012 | 20.1735 | 10.9543 | 48.1692 | 15.8909 | 522.9348
616 | 7.4606 | 30.2015 | 27.4515 | 6.0708 | 24.784 | 42.6353 | 38.614 | 9.16 | 19.021 | 10.9754 | 17.1087 | 16.9551 | 42.5358 | 17.6154 | 3.157 | 18.9471 | 17.6839 | 5.9389 | 26.0462 | 11.0224 | 17.9456 | 14.0951 | 11.8957 | 48.5918 | 16.9692 | 502.882
617 | 5.1983 | 43.6188 | 30.5296 | 7.9416 | 30.5394 | 38.1917 | 29.0682 | 10.0299 | 17.8673 | 16.1511 | 19.9479 | 19.1555 | 35.3554 | 20.75 | 2.4149 | 19.6926 | 32.202 | 4.8177 | 23.6239 | 13.4595 | 19.8921 | 21.2644 | 8.8498 | 50.206 | 21.4028 | 542.1705
618 | 7.7891 | 38.8521 | 30.8364 | 6.526 | 32.597 | 43.3266 | 29.0035 | 10.2011 | 14.1305 | 10.9757 | 16.0393 | 23.4027 | 47.0377 | 23.6868 | 2.5378 | 26.5798 | 36.2295 | 3.5226 | 18.2722 | 12.5186 | 20.4467 | 17.0673 | 10.2487 | 39.2093 | 18.2517 | 539.2886
619 | 6.5507 | 42.8283 | 30.1856 | 5.383 | 34.6129 | 39.9481 | 32.7711 | 5.9621 | 14.1467 | 14.8916 | 16.3592 | 24.9512 | 40.3811 | 23.0553 | 3.9708 | 20.807 | 29.0487 | 5.3467 | 30.2371 | 13.3837 | 23.2366 | 20.9646 | 8.8227 | 52.1111 | 12.7634 | 552.7192
620 | 6.4069 | 36.6823 | 25.1961 | 6.9027 | 27.4954 | 26.5971 | 36.5845 | 10.4754 | 18.5321 | 15.5315 | 22.4139 | 11.9846 | 50.7187 | 13.6033 | 3.3628 | 22.6575 | 36.0039 | 4.8612 | 25.3395 | 11.3391 | 18.4659 | 19.4528 | 10.3572 | 41.8351 | 21.1266 | 523.9261
621 | 7.4233 | 47.5351 | 25.2758 | 6.7965 | 37.099 | 49.3485 | 23.6505 | 9.7632 | 19.8357 | 16.3369 | 15.9871 | 27.8488 | 31.8802 | 23.3339 | 2.6091 | 23.6843 | 27.2948 | 5.8598 | 24.0965 | 12.8895 | 20.5004 | 20.185 | 8.0046 | 56.3014 | 18.0457 | 561.5857
622 | 6.3026 | 48.4617 | 33.4095 | 6.5321 | 30.5974 | 46.7294 | 29.508 | 11.4148 | 13.889 | 16.0088 | 17.8531 | 26.0584 | 48.0231 | 25.278 | 3.7756 | 24.8966 | 36.9056 | 5.2192 | 28.1587 | 13.7501 | 25.705 | 18.3169 | 8.0978 | 44.5402 | 16.3828 | 585.8142
623 | 4.3892 | 48.251 | 30.702 | 7.2822 | 32.1336 | 39.8709 | 35.5835 | 11.5875 | 18.6738 | 10.7334 | 17.034 | 20.4142 | 48.3975 | 23.3306 | 3.8964 | 23.6241 | 23.9257 | 4.8728 | 20.1956 | 13.5142 | 22.3398 | 18.5401 | 11.0995 | 51.8435 | 18.2141 | 560.4493
624 | 7.3745 | 35.7868 | 26.2619 | 6.0366 | 27.6806 | 33.628 | 38.4116 | 9.6334 | 19.1944 | 12.4968 | 19.3074 | 18.5519 | 37.2492 | 13.4553 | 3.7647 | 26.9002 | 36.6722 | 5.4223 | 31.9555 | 10.6947 | 19.884 | 20.3013 | 9.1344 | 47.0738 | 12.6094 | 529.481
625 | 5.6825 | 37.5691 | 29.1927 | 6.5637 | 29.7157 | 35.2918 | 35.9365 | 9.9337 | 19.8507 | 13.8614 | 14.985 | 22.339 | 38.3104 | 18.479 | 3.7427 | 26.0117 | 35.4941 | 3.3584 | 30.1447 | 8.2326 | 21.6292 | 17.3 | 10.2191 | 41.8183 | 20.7861 | 536.4481
626 | 6.7454 | 39.6342 | 15.5491 | 8.2618 | 39.0708 | 49.9137 | 36.3529 | 9.0454 | 15.8089 | 16.1743 | 20.6678 | 23.3788 | 22.2372 | 15.9073 | 2.5241 | 11.7638 | 38.5189 | 4.4294 | 28.4288 | 12.5303 | 22.2162 | 21.9917 | 10.6035 | 51.6807 | 16.7881 | 540.223
627 | 7.2919 | 39.2651 | 31.9895 | 7.6711 | 31.9981 | 41.2004 | 28.8101 | 11.311 | 14.007 | 16.0603 | 20.1436 | 28.1183 | 29.4864 | 24.5589 | 3.7028 | 20.7213 | 35.3334 | 4.2705 | 32.1472 | 9.94 | 26.6957 | 15.6531 | 8.1265 | 41.4446 | 19.4141 | 549.3611
628 | 6.7526 | 42.3526 | 17.7702 | 7.7651 | 30.1559 | 44.5291 | 28.6756 | 7.885 | 13.8551 | 14.1992 | 19.5947 | 12.295 | 43.016 | 25.7402 | 3.3184 | 19.0053 | 20.7137 | 4.6123 | 31.7642 | 13.038 | 23.508 | 13.4676 | 10.552 | 52.0428 | 18.9809 | 525.5896
629 | 6.6072 | 37.2507 | 31.9899 | 7.9137 | 24.8483 | 53.0256 | 28.0024 | 6.9689 | 13.6264 | 9.2757 | 19.7597 | 24.6047 | 53.5168 | 20.3188 | 3.1693 | 19.236 | 32.3108 | 4.8822 | 21.453 | 11.6037 | 20.8679 | 16.3508 | 7.4544 | 52.9213 | 9.384 | 537.342
630 | 7.2589 | 37.5929 | 31.0212 | 8.1662 | 17.4192 | 37.8389 | 20.0955 | 11.6907 | 15.9601 | 12.8622 | 20.8844 | 28.6492 | 40.4717 | 21.9124 | 3.2821 | 25.7533 | 36.6203 | 5.5371 | 20.8502 | 10.3898 | 16.2235 | 21.0623 | 8.3644 | 50.1487 | 19.3446 | 529.3993
631 | 6.1265 | 45.9513 | 32.053 | 7.6006 | 30.2081 | 31.9292 | 29.4483 | 7.3098 | 19.1871 | 16.4334 | 22.1052 | 22.7727 | 53.9581 | 25.4295 | 3.5071 | 22.5375 | 32.5577 | 5.9349 | 31.8435 | 11.4153 | 16.9248 | 21.5478 | 7.7713 | 43.1818 | 20.5834 | 568.318
632 | 8.2458 | 39.2574 | 24.3513 | 4.7243 | 28.7065 | 42.3043 | 22.4799 | 10.0314 | 17.0943 | 14.1784 | 21.3118 | 25.5234 | 37.6945 | 20.004 | 2.5761 | 27.2389 | 21.2034 | 3.7418 | 31.38 | 9.5162 | 14.6037 | 21.1551 | 12.1342 | 42.5144 | 10.4424 | 512.4134
633 | 7.1488 | 40.9005 | 31.3998 | 6.4888 | 31.2254 | 49.4426 | 23.6987 | 5.9713 | 14.8246 | 13.3908 | 17.6202 | 26.1017 | 46.8299 | 17.0058 | 3.9766 | 25.8655 | 25.5462 | 5.7401 | 28.0782 | 13.3177 | 19.3427 | 21.2556 | 7.9657 | 45.7963 | 14.8345 | 543.7681
634 | 5.9703 | 37.6717 | 28.1178 | 7.4927 | 32.2517 | 50.2721 | 32.874 | 7.6812 | 18.1561 | 11.1429 | 20.6419 | 17.8906 | 45.648 | 19.3057 | 3.9378 | 21.719 | 37.5278 | 5.9811 | 27.7541 | 12.5158 | 21.4612 | 12.8941 | 9.7952 | 46.1137 | 16.0343 | 550.8508
635 | 7.1142 | 32.6899 | 24.5546 | 6.4952 | 21.7189 | 44.0999 | 25.2424 | 11.5225 | 19.8654 | 10.799 | 15.9597 | 16.0366 | 36.0628 | 20.1943 | 3.7652 | 25.5514 | 20.7387 | 5.0245 | 26.4849 | 13.0541 | 19.3274 | 21.6857 | 8.1481 | 40.0883 | 19.5325 | 495.7563
636 | 5.6655 | 27.7884 | 24.176 | 7.8564 | 23.4099 | 50.2235 | 35.466 | 8.6056 | 18.7753 | 15.5421 | 20.9635 | 18.6308 | 52.7709 | 19.7623 | 3.5985 | 21.7848 | 29.7315 | 4.7679 | 19.7106 | 8.3561 | 21.313 | 18.1992 | 8.2747 | 50.7788 | 19.2 | 535.3513
637 | 7.0073 | 40.2802 | 22.1664 | 7.1053 | 31.0161 | 40.7645 | 37.1809 | 10.7975 | 13.6056 | 14.572 | 16.9761 | 23.4438 | 49.9691 | 20.0234 | 3.3792 | 26.1907 | 35.3555 | 5.205 | 32.8165 | 13.7016 | 25.2957 | 17.8416 | 11.2814 | 36.1693 | 18.9856 | 561.1303
638 | 7.2844 | 45.9286 | 25.6768 | 8.783 | 34.0227 | 46.0439 | 37.9754 | 9.1742 | 19.6217 | 15.4324 | 15.3849 | 25.4407 | 38.0207 | 17.5228 | 3.4374 | 24.03 | 30.5247 | 5.1671 | 29.76 | 11.1431 | 22.2426 | 17.7406 | 8.0388 | 39.2849 | 15.7204 | 553.402
639 | 7.6319 | 35.7447 | 32.1534 | 8.1341 | 24.8229 | 36.1916 | 35.2263 | 9.0436 | 12.2629 | 12.4415 | 12.9201 | 17.1397 | 44.6369 | 24.1095 | 3.0697 | 20.8337 | 25.6437 | 5.9889 | 25.4584 | 11.3956 | 19.6245 | 18.1757 | 7.7095 | 27.6387 | 13.3886 | 491.386
640 | 6.5811 | 43.7057 | 30.1126 | 8.6216 | 26.4654 | 37.2881 | 24.2615 | 5.9305 | 11.3897 | 15.1195 | 14.6933 | 28.5079 | 48.8378 | 21.125 | 3.4629 | 14.7501 | 30.7751 | 4.3151 | 18.2606 | 9.3805 | 21.4995 | 21.0263 | 10.235 | 48.3502 | 18.8396 | 523.5347
641 | 5.0714 | 35.1504 | 25.8136 | 8.7039 | 27.8263 | 31.9526 | 21.5243 | 8.4811 | 18.4446 | 15.6339 | 18.103 | 21.2819 | 35.6013 | 19.1316 | 3.5727 | 21.0287 | 36.8422 | 4.599 | 30.4306 | 9.1133 | 16.7447 | 18.5185 | 12.0006 | 49.5067 | 20.2468 | 515.3236
642 | 5.0527 | 42.0911 | 23.7771 | 5.5703 | 33.8636 | 46.6015 | 26.407 | 11.0115 | 18.7892 | 16.5763 | 21.1752 | 25.4074 | 35.71 | 23.9862 | 3.5617 | 24.9609 | 31.8339 | 4.9196 | 30.469 | 13.2551 | 20.8208 | 18.6426 | 8.4899 | 44.3878 | 20.0425 | 557.4029
643 | 8.1746 | 34.5919 | 32.5088 | 5.7274 | 22.9467 | 35.2093 | 21.9862 | 11.6379 | 15.6311 | 16.3653 | 15.2454 | 23.5938 | 40.831 | 25.4581 | 3.7357 | 15.3256 | 28.6758 | 4.5448 | 32.2466 | 12.3436 | 20.5516 | 15.7113 | 8.0176 | 55.9788 | 21.8957 | 528.9346
644 | 6.8782 | 42.0507 | 31.152 | 8.3533 | 24.0041 | 34.1218 | 30.7892 | 10.7237 | 13.57 | 12.6269 | 19.1118 | 25.1777 | 54.6973 | 19.5365 | 3.6456 | 17.9634 | 34.648 | 4.6611 | 20.0144 | 11.7798 | 18.0799 | 20.8528 | 11.7253 | 39.2037 | 20.9881 | 536.3553
645 | 8.2181 | 43.4559 | 28.0989 | 8.1262 | 20.7513 | 43.6717 | 29.357 | 10.5135 | 16.8135 | 13.054 | 21.5895 | 17.1228 | 40.1947 | 16.7108 | 3.9928 | 23.4702 | 33.8969 | 5.2046 | 30.6131 | 9.5499 | 23.0707 | 18.2404 | 11.3595 | 45.1849 | 20.0331 | 542.2938
646 | 3.433 | 46.4657 | 22.3368 | 6.9687 | 26.8889 | 48.4476 | 24.7121 | 8.6448 | 15.7121 | 14.4633 | 17.4524 | 17.3698 | 44.5747 | 21.644 | 3.9143 | 20.3628 | 28.5523 | 5.6045 | 27.7063 | 13.005 | 15.2966 | 19.1498 | 11.5194 | 41.5723 | 20.189 | 525.9861
647 | 7.0896 | 41.5194 | 25.9351 | 7.8165 | 37.1807 | 40.2173 | 27.2545 | 8.78 | 13.5262 | 11.5774 | 17.995 | 22.8268 | 45.3776 | 21.0663 | 3.5796 | 13.4288 | 37.2633 | 3.7821 | 24.6719 | 10.1507 | 17.686 | 15.1467 | 9.731 | 51.7933 | 20.4037 | 535.7995
648 | 4.4972 | 32.7995 | 21.0195 | 6.5508 | 17.9645 | 46.3424 | 15.0078 | 8.6324 | 18.5593 | 14.4979 | 12.8883 | 24.913 | 36.1153 | 25.7624 | 3.9617 | 27.7056 | 23.6629 | 5.1118 | 32.8043 | 12.1706 | 21.6467 | 15.9601 | 10.8253 | 55.415 | 15.0732 | 509.8876
649 | 4.831 | 35.5918 | 23.6144 | 6.4163 | 21.0348 | 48.1126 | 31.1843 | 8.5075 | 18.7832 | 14.6126 | 21.733 | 25.0228 | 35.4222 | 20.984 | 2.3314 | 24.7947 | 36.569 | 5.1708 | 22.6138 | 12.2009 | 19.973 | 20.4618 | 10.0754 | 48.3689 | 19.5217 | 537.9319
650 | 6.4875 | 43.2247 | 30.5362 | 8.0481 | 36.7501 | 37.1131 | 26.1321 | 9.7473 | 14.0847 | 15.864 | 22.1535 | 16.7138 | 54.3424 | 18.8131 | 3.6051 | 18.7486 | 31.3594 | 4.6375 | 22.366 | 11.4465 | 24.0914 | 17.7131 | 12.3528 | 32.7236 | 19.8025 | 538.8569
651 | 7.2436 | 46.2045 | 30.6425 | 5.8123 | 35.5823 | 50.4312 | 35.8357 | 10.1276 | 19.1168 | 15.0026 | 17.5037 | 22.8848 | 40.7174 | 25.7971 | 3.4712 | 27.1873 | 27.2345 | 5.2921 | 20.457 | 11.0867 | 21.9046 | 19.5005 | 12.126 | 49.1463 | 18.8893 | 579.1977
652 | 5.8638 | 43.593 | 26.2068 | 6.6166 | 35.155 | 42.3013 | 36.2777 | 8.5612 | 16.6363 | 11.2767 | 16.0173 | 23.0718 | 47.6882 | 23.8849 | 2.3972 | 25.3776 | 34.0178 | 4.9656 | 32.2949 | 10.414 | 15.3075 | 20.0024 | 11.2989 | 45.4326 | 20.9549 | 565.6141
653 | 7.6424 | 38.0671 | 21.5144 | 6.968 | 24.6733 | 39.8383 | 36.5675 | 6.0898 | 13.8261 | 13.382 | 17.7225 | 19.287 | 45.9338 | 18.3924 | 2.5968 | 21.414 | 31.8785 | 5.8294 | 20.4905 | 13.2921 | 22.2803 | 19.8906 | 6.3083 | 32.7664 | 19.9885 | 506.6398
654 | 5.4396 | 42.2298 | 31.1149 | 4.8146 | 34.0065 | 45.7932 | 38.1803 | 10.1865 | 19.4298 | 13.3288 | 19.3013 | 26.5498 | 43.8856 | 19.5027 | 3.3772 | 26.6995 | 28.0445 | 5.8861 | 29.0423 | 12.0752 | 22.6681 | 17.4349 | 6.5014 | 49.1345 | 16.0969 | 570.7241
655 | 6.8697 | 42.7442 | 28.7322 | 6.6679 | 31.6051 | 49.1451 | 29.7166 | 10.6712 | 14.0093 | 14.5174 | 17.291 | 19.888 | 47.8592 | 19.3848 | 3.6705 | 22.1677 | 38.5933 | 3.6458 | 30.1205 | 10.1885 | 19.0849 | 19.1119 | 11.578 | 54.6731 | 21.8163 | 573.7523
656 | 7.1436 | 24.4074 | 31.5835 | 7.898 | 22.8921 | 43.6383 | 24.1982 | 9.8413 | 16.4638 | 14.0057 | 21.8839 | 26.2794 | 50.3516 | 19.6527 | 3.3393 | 23.2024 | 35.5712 | 4.2165 | 32.9407 | 8.4616 | 13.2025 | 21.2809 | 11.4672 | 41.8959 | 16.3725 | 532.1902
657 | 6.5126 | 45.3604 | 26.1061 | 5.8061 | 29.935 | 42.9639 | 33.9801 | 9.2204 | 19.8421 | 13.9253 | 16.1504 | 24.7399 | 37.1013 | 19.5067 | 3.5444 | 25.2612 | 35.1275 | 5.4223 | 27.139 | 11.9046 | 23.0193 | 19.4087 | 10.066 | 52.7398 | 22.1389 | 566.9221
658 | 8.0226 | 47.9612 | 30.0174 | 8.3605 | 25.736 | 34.2962 | 19.4838 | 7.4207 | 15.2508 | 15.8943 | 19.9091 | 24.8604 | 37.3884 | 24.1454 | 3.8252 | 21.9752 | 32.3091 | 4.8178 | 20.0828 | 9.7486 | 11.5197 | 19.802 | 11.5696 | 55.2511 | 13.233 | 522.8806
659 | 5.1678 | 34.4023 | 26.0434 | 7.8154 | 33.4871 | 43.5512 | 21.517 | 10.4339 | 18.0036 | 10.8287 | 15.7624 | 26.7845 | 34.1912 | 22.7481 | 2.7063 | 18.6461 | 29.1983 | 4.4697 | 28.889 | 8.8766 | 23.7253 | 14.9188 | 7.4567 | 45.4049 | 10.9815 | 506.0098
660 | 6.3269 | 23.7643 | 26.6663 | 8.5705 | 29.2513 | 37.763 | 33.9955 | 7.031 | 13.6563 | 12.0049 | 12.4611 | 24.7793 | 46.5095 | 22.3082 | 2.8286 | 17.7284 | 33.8552 | 5.8743 | 25.999 | 11.7932 | 19.548 | 21.1353 | 10.2524 | 47.5831 | 14.6234 | 516.3093
661 | 8.0018 | 35.7603 | 31.7352 | 8.5856 | 25.7421 | 28.9329 | 38.4557 | 9.4741 | 18.6993 | 14.2186 | 15.3912 | 26.6998 | 37.8228 | 25.6609 | 3.6294 | 14.9381 | 29.836 | 4.6682 | 28.7274 | 11.7095 | 21.4692 | 18.967 | 6.9566 | 53.0704 | 20.5337 | 539.6859
662 | 7.3793 | 35.1429 | 25.4112 | 8.2575 | 37.6199 | 51.558 | 38.552 | 11.2383 | 18.1168 | 11.2221 | 18.4634 | 22.8411 | 49.9304 | 24.6934 | 2.3751 | 24.776 | 18.8609 | 5.0569 | 32.3536 | 12.4062 | 23.0861 | 15.7053 | 12.0605 | 45.1366 | 19.6659 | 571.9096
663 | 7.3987 | 17.8423 | 26.1947 | 8.5151 | 18.9993 | 38.416 | 29.4916 | 8.7727 | 12.1755 | 13.631 | 15.5882 | 23.099 | 46.1514 | 24.6286 | 3.2433 | 12.4649 | 35.1873 | 4.8867 | 25.1166 | 8.8028 | 25.1954 | 15.9269 | 10.2416 | 47.6167 | 20.623 | 500.2091
664 | 5.1529 | 36.1516 | 27.8751 | 8.5122 | 34.4627 | 48.5995 | 23.8936 | 7.9208 | 17.0625 | 14.6246 | 17.4818 | 28.2256 | 37.5896 | 25.8845 | 3.9702 | 27.6795 | 15.5468 | 5.7585 | 22.0839 | 12.3867 | 24.3563 | 19.9502 | 11.0164 | 53.9864 | 14.9759 | 545.148
665 | 4.454 | 40.8255 | 22.9192 | 6.5853 | 36.3869 | 45.2335 | 31.8218 | 10.0247 | 18.9474 | 14.1007 | 21.429 | 17.7403 | 41.931 | 25.4041 | 3.6051 | 24.6699 | 22.4997 | 5.304 | 32.8434 | 9.7395 | 26.2904 | 15.0905 | 9.6563 | 44.2643 | 11.358 | 543.1243
666 | 6.3753 | 45.128 | 26.1462 | 7.5 | 33.5995 | 50.0831 | 27.236 | 8.0846 | 16.6086 | 13.3546 | 20.244 | 27.5924 | 51.2375 | 16.5784 | 3.62 | 26.3865 | 34.1814 | 4.2865 | 29.087 | 12.4991 | 16.7497 | 14.5133 | 9.9487 | 59.0015 | 19.239 | 579.2807
667 | 4.7987 | 47.1529 | 23.9759 | 8.3176 | 39.1318 | 51.6895 | 26.4337 | 6.1634 | 18.3761 | 10.0393 | 19.1559 | 24.773 | 32.2048 | 24.8751 | 3.4608 | 20.2085 | 35.5907 | 4.4776 | 26.2021 | 13.0036 | 22.1748 | 11.873 | 6.6323 | 47.4975 | 20.135 | 548.3439
668 | 6.6397 | 19.1267 | 25.786 | 4.3742 | 30.9285 | 35.9554 | 22.5923 | 8.5328 | 12.0521 | 16.4066 | 19.6042 | 20.1441 | 31.568 | 25.7691 | 3.9951 | 15.8494 | 35.0628 | 5.7662 | 22.9399 | 10.3089 | 24.565 | 13.7426 | 9.2019 | 56.2363 | 17.809 | 494.9568
669 | 7.9608 | 38.0433 | 32.6458 | 8.3117 | 34.379 | 40.9063 | 37.8721 | 10.9477 | 15.4638 | 15.468 | 19.6667 | 18.8439 | 45.0095 | 25.7956 | 3.984 | 25.0205 | 27.0781 | 4.0945 | 32.0891 | 13.1836 | 24.0263 | 17.9076 | 12.0989 | 40.8268 | 19.853 | 571.4768
670 | 7.7554 | 40.7786 | 30.5289 | 8.2488 | 31.6344 | 34.6267 | 28.8394 | 9.0835 | 16.7176 | 16.5009 | 20.9479 | 26.0223 | 50.4552 | 25.3892 | 3.9285 | 26.5976 | 31.8854 | 3.8237 | 20.8815 | 12.4176 | 24.7991 | 20.4363 | 10.266 | 51.3231 | 17.048 | 570.9356
671 | 7.2213 | 46.3571 | 18.7544 | 7.8134 | 20.8186 | 51.2366 | 25.4478 | 9.4164 | 18.6002 | 16.0688 | 19.7165 | 27.5852 | 47.9317 | 23.2886 | 3.3524 | 26.9442 | 16.0842 | 5.9086 | 25.6642 | 10.9483 | 24.1439 | 21.7359 | 10.9736 | 56.4461 | 20.4902 | 562.9482
672 | 8.0956 | 45.9294 | 20.3363 | 8.2577 | 27.814 | 31.2145 | 26.6379 | 11.6377 | 15.619 | 13.2343 | 15.2388 | 24.9644 | 43.0688 | 21.4126 | 3.9489 | 21.1974 | 23.1361 | 4.2236 | 28.1951 | 11.1238 | 26.6299 | 20.8036 | 12.0151 | 55.384 | 12.8975 | 533.0161
673 | 5.3439 | 43.8705 | 30.2285 | 6.4768 | 29.9014 | 44.5266 | 32.6717 | 9.4759 | 16.0041 | 15.8584 | 12.722 | 19.6401 | 50.9233 | 19.3227 | 3.3982 | 14.6928 | 33.2833 | 4.7871 | 23.711 | 8.9221 | 24.7648 | 21.345 | 10.9878 | 59.5859 | 15.6634 | 558.1074
674 | 7.9364 | 44.7733 | 31.3861 | 5.8863 | 29.3495 | 47.5454 | 34.5023 | 9.5403 | 12.5427 | 12.4186 | 19.0551 | 20.1323 | 49.676 | 24.7416 | 3.7729 | 22.9556 | 38.1694 | 5.333 | 26.7419 | 12.6335 | 20.6196 | 18.5185 | 7.5929 | 49.563 | 11.1877 | 566.5737
675 | 6.0746 | 36.1197 | 24.3375 | 8.4232 | 25.4557 | 39.6824 | 31.2211 | 6.7085 | 17.6637 | 14.4293 | 15.7309 | 22.4475 | 32.9064 | 24.0975 | 2.99 | 24.3742 | 28.357 | 4.6718 | 27.6729 | 13.2451 | 22.5305 | 18.6283 | 9.6576 | 56.1753 | 16.5443 | 530.145
676 | 5.5512 | 37.9343 | 23.3894 | 7.8996 | 30.1649 | 46.0749 | 35.0254 | 8.419 | 18.4945 | 16.3835 | 18.3153 | 25.0822 | 43.2384 | 15.7559 | 3.5873 | 20.9088 | 26.4369 | 5.7737 | 31.9571 | 10.3734 | 21.4346 | 15.5391 | 10.4968 | 57.0421 | 16.9561 | 552.2346
677 | 6.9562 | 33.2224 | 25.5927 | 6.1477 | 32.4766 | 53.7328 | 23.9227 | 10.5036 | 19.6932 | 14.2088 | 18.7819 | 10.5746 | 33.7929 | 25.1576 | 3.348 | 24.9528 | 36.9259 | 5.2539 | 21.4506 | 13.9558 | 24.9208 | 20.5658 | 11.2058 | 49.0653 | 20.1171 | 546.5256
678 | 5.5642 | 42.3053 | 31.6147 | 8.7073 | 32.0308 | 36.1473 | 27.4774 | 8.9186 | 14.4238 | 13.111 | 17.6969 | 17.9395 | 49.1237 | 23.7249 | 3.9859 | 23.4943 | 37.4853 | 5.8187 | 28.8534 | 13.0846 | 22.9599 | 21.3045 | 9.5893 | 46.3861 | 19.4468 | 561.194
679 | 6.6763 | 33.3661 | 25.5903 | 5.0824 | 22.2419 | 45.1921 | 30.0929 | 9.8944 | 17.8132 | 16.0108 | 20.9223 | 23.071 | 52.7381 | 23.9689 | 3.6599 | 19.1031 | 30.7127 | 4.6834 | 24.1082 | 11.3274 | 19.7521 | 20.0561 | 10.7485 | 44.6082 | 20.4801 | 541.9003
680 | 8.0184 | 34.2891 | 24.2485 | 8.5601 | 34.0722 | 50.0199 | 25.5221 | 10.56 | 18.1966 | 15.3973 | 18.2513 | 19.4058 | 38.539 | 20.9544 | 3.0564 | 27.2489 | 34.6925 | 5.9045 | 27.7036 | 10.9623 | 24.2217 | 21.0664 | 8.0861 | 28.9937 | 18.8372 | 536.808
681 | 7.4155 | 32.5941 | 20.381 | 6.1628 | 28.491 | 39.8213 | 26.061 | 10.7215 | 14.1263 | 10.942 | 21.2722 | 24.4516 | 25.0671 | 19.1298 | 3.6471 | 21.4485 | 24.1595 | 3.8399 | 27.3564 | 12.3862 | 15.8983 | 18.9096 | 8.3018 | 44.1598 | 16.0568 | 482.8014
682 | 6.2556 | 47.1443 | 27.6598 | 7.9103 | 33.5162 | 48.8009 | 30.0337 | 8.6924 | 17.689 | 10.2761 | 17.8602 | 19.9567 | 52.7428 | 25.2721 | 3.6241 | 24.3462 | 36.644 | 5.0505 | 30.2136 | 9.9777 | 20.9781 | 15.5577 | 7.2533 | 45.0314 | 11.2368 | 563.7234
683 | 5.9117 | 39.0326 | 28.0311 | 6.1418 | 26.3802 | 47.8403 | 36.8279 | 8.4537 | 19.5549 | 13.2019 | 21.6658 | 27.2846 | 37.8987 | 20.832 | 3.005 | 25.3994 | 29.1309 | 5.803 | 21.8528 | 8.3981 | 22.2906 | 20.4086 | 10.5983 | 49.8125 | 15.2969 | 551.0532
684 | 6.4 | 38.5612 | 19.7929 | 5.5752 | 29.6974 | 47.1841 | 16.1772 | 10.1631 | 18.4434 | 11.0294 | 16.1761 | 20.1042 | 34.6365 | 20.4005 | 3.5368 | 25.5033 | 29.6145 | 5.2859 | 19.7496 | 10.1029 | 17.3804 | 20.9731 | 12.1563 | 34.0323 | 17.6304 | 490.3068
685 | 7.9011 | 43.132 | 29.1504 | 8.7783 | 23.8547 | 52.4399 | 26.4489 | 10.3795 | 13.4567 | 10.9757 | 19.3025 | 22.1458 | 45.0742 | 19.5163 | 3.9861 | 20.0614 | 38.4753 | 4.5393 | 30.9792 | 11.6389 | 23.6148 | 17.043 | 12.4845 | 45.83 | 18.9927 | 560.2014
686 | 6.4821 | 36.9118 | 27.8554 | 8.0913 | 31.4381 | 30.8098 | 34.2321 | 9.9341 | 19.8849 | 14.0943 | 14.1391 | 23.8683 | 52.1986 | 22.5897 | 2.7453 | 22.1664 | 23.8059 | 5.2203 | 18.1289 | 13.9772 | 19.8724 | 15.1164 | 11.2566 | 49.5979 | 15.1005 | 529.5175
687 | 7.5784 | 44.9407 | 18.1942 | 8.0004 | 37.3844 | 45.1603 | 26.5561 | 10.1309 | 13.3464 | 13.0018 | 17.6744 | 19.1888 | 45.5083 | 15.8917 | 3.3396 | 20.8271 | 20.9141 | 4.6299 | 23.7598 | 11.9168 | 21.682 | 18.4893 | 8.597 | 36.6022 | 19.0416 | 512.3564
688 | 7.8031 | 34.9218 | 28.9417 | 6.9685 | 35.4452 | 45.4532 | 24.707 | 10.3499 | 18.3871 | 11.2494 | 16.3339 | 24.3676 | 43.8963 | 25.4478 | 2.3918 | 26.6971 | 21.9857 | 3.3997 | 31.7941 | 12.4251 | 16.3833 | 19.2632 | 9.0123 | 54.5314 | 20.1641 | 552.3202
689 | 7.3875 | 41.3717 | 20.8323 | 6.3677 | 31.5592 | 43.2276 | 27.9775 | 8.8913 | 14.7769 | 11.2858 | 21.1621 | 21.2781 | 25.122 | 23.8 | 3.6186 | 21.2908 | 31.0853 | 5.8907 | 32.7136 | 10.8666 | 22.3408 | 21.2016 | 6.9379 | 54.3426 | 15.1467 | 530.4748
690 | 7.4816 | 39.4194 | 29.8861 | 7.6199 | 21.5162 | 38.9173 | 38.2616 | 9.2362 | 19.6841 | 14.6419 | 16.972 | 28.1241 | 34.8733 | 23.6837 | 3.1622 | 21.4756 | 35.287 | 5.3812 | 21.9799 | 13.3135 | 26.5373 | 16.556 | 11.6256 | 52.7323 | 16.7691 | 555.1371
691 | 7.741 | 32.3409 | 18.6263 | 8.2018 | 34.3263 | 44.6102 | 31.7568 | 9.3318 | 18.105 | 15.2356 | 16.6209 | 17.4165 | 36.176 | 24.4495 | 3.2281 | 25.7268 | 34.2489 | 5.6914 | 24.6983 | 13.9701 | 18.8629 | 15.7555 | 10.2149 | 37.8264 | 19.972 | 525.1339
692 | 5.6834 | 45.5499 | 23.6579 | 6.7333 | 23.9119 | 34.1313 | 27.9918 | 10.5498 | 19.905 | 15.1333 | 21.0671 | 22.054 | 50.1789 | 15.6562 | 3.7033 | 21.5454 | 38.1829 | 5.8767 | 23.5014 | 12.607 | 24.8223 | 21.6391 | 9.2501 | 56.8608 | 17.3574 | 557.5501
693 | 7.8898 | 20.6316 | 31.4191 | 6.6414 | 37.8663 | 45.6837 | 22.0954 | 10.2792 | 16.3316 | 10.6431 | 21.4139 | 21.0054 | 50.4959 | 20.4885 | 3.5558 | 26.4814 | 28.2726 | 5.6739 | 23.0929 | 8.1545 | 23.4497 | 14.202 | 12.3799 | 49.5005 | 21.2485 | 538.8965
694 | 4.1316 | 42.0519 | 29.2416 | 5.1969 | 37.6141 | 46.9654 | 32.817 | 11.7012 | 16.804 | 14.7787 | 16.3874 | 25.9497 | 54.8585 | 18.7421 | 3.4515 | 27.7232 | 37.7551 | 4.9588 | 24.656 | 11.2056 | 23.2619 | 21.4194 | 10.3144 | 42.6877 | 14.8951 | 579.5689
695 | 5.5264 | 38.0535 | 26.1715 | 7.6364 | 28.1463 | 52.6559 | 37.9958 | 10.9863 | 17.8993 | 12.1713 | 21.0872 | 17.0735 | 41.1853 | 23.2544 | 2.4939 | 21.1728 | 20.578 | 4.6408 | 27.8547 | 13.7619 | 16.1949 | 17.9433 | 8.4272 | 35.5466 | 20.0343 | 528.4912
696 | 6.7955 | 47.065 | 31.7128 | 8.0635 | 34.7815 | 28.4077 | 33.4688 | 5.8036 | 16.9386 | 15.148 | 18.3536 | 23.3294 | 30.8815 | 14.3096 | 2.4296 | 17.881 | 29.1317 | 5.9438 | 18.3199 | 12.9734 | 18.7943 | 18.7207 | 11.6882 | 53.0338 | 21.6355 | 525.611
697 | 6.1714 | 36.3645 | 24.5819 | 7.5482 | 33.4904 | 46.301 | 25.5402 | 9.7005 | 15.638 | 16.39 | 11.7302 | 19.5204 | 31.4497 | 22.0349 | 3.6461 | 16.526 | 24.1932 | 5.1873 | 27.6975 | 10.8602 | 19.9668 | 20.8365 | 11.1399 | 45.4464 | 13.6067 | 505.5678
698 | 5.2268 | 46.348 | 30.5452 | 4.8811 | 35.9159 | 51.2131 | 22.2861 | 10.8774 | 17.0709 | 12.0588 | 22.0115 | 24.0599 | 34.6612 | 22.237 | 2.8685 | 26.6779 | 31.8158 | 3.9644 | 24.3439 | 10.6503 | 23.4162 | 19.0407 | 9.8005 | 48.6268 | 14.5613 | 555.1592
699 | 7.6747 | 45.4438 | 30.6874 | 5.9819 | 35.6088 | 42.6755 | 36.9853 | 10.9221 | 19.0902 | 15.4946 | 15.9396 | 19.1404 | 27.3836 | 20.6161 | 3.7473 | 24.3745 | 28.3788 | 5.3413 | 29.186 | 11.4087 | 17.1888 | 21.3102 | 11.467 | 31.9797 | 21.686 | 539.7122
700 | 8.2045 | 38.1715 | 19.3042 | 7.0422 | 29.2074 | 43.0427 | 36.1562 | 6.4894 | 14.8906 | 10.7999 | 22.1914 | 23.0139 | 29.2319 | 22.0343 | 3.2157 | 18.4502 | 31.8382 | 5.2475 | 19.5768 | 13.8683 | 15.1012 | 20.9345 | 12.0591 | 49.5081 | 19.9752 | 519.5549
701 | 6.3985 | 27.4592 | 25.4724 | 4.6834 | 32.8389 | 35.244 | 35.417 | 8.1607 | 18.4304 | 16.3342 | 13.6329 | 24.5923 | 49.0999 | 22.0613 | 3.1285 | 22.3507 | 21.4692 | 5.8019 | 29.6748 | 7.8817 | 20.7439 | 12.2964 | 6.4047 | 55.1922 | 21.9656 | 526.7347
702 | 5.4605 | 36.968 | 20.9729 | 7.3667 | 30.1129 | 37.8182 | 34.9835 | 11.9135 | 16.4556 | 14.4973 | 19.4595 | 22.128 | 39.205 | 25.3669 | 2.3098 | 23.8454 | 28.6266 | 5.665 | 20.3834 | 12.1197 | 20.834 | 18.0343 | 12.2209 | 44.8742 | 17.9269 | 529.5487
703 | 7.7419 | 43.8535 | 29.2323 | 7.9869 | 33.6635 | 35.2015 | 27.8756 | 9.5404 | 15.8235 | 16.6758 | 17.2012 | 22.492 | 52.917 | 25.6869 | 3.8097 | 15.3988 | 34.9536 | 5.2158 | 26.8995 | 8.3913 | 19.6917 | 21.7665 | 7.6949 | 56.9834 | 20.9121 | 567.6093
704 | 8.3193 | 32.5152 | 27.3336 | 5.8292 | 32.2678 | 48.7035 | 36.416 | 9.366 | 16.5603 | 12.7933 | 17.1797 | 17.6709 | 39.2362 | 19.3606 | 3.3983 | 25.1985 | 25.3248 | 4.057 | 26.1449 | 13.6475 | 17.709 | 18.0748 | 12.2307 | 46.1688 | 16.8689 | 532.3748
705 | 5.9045 | 47.5715 | 27.0145 | 7.724 | 31.3703 | 46.3791 | 30.9223 | 10.3435 | 17.2113 | 14.6952 | 19.5126 | 23.2948 | 36.6181 | 23.3921 | 2.1164 | 16.52 | 35.5144 | 4.8227 | 29.828 | 11.3056 | 19.9485 | 12.8566 | 10.2615 | 54.0566 | 21.1419 | 560.326
706 | 7.5798 | 37.2233 | 30.1461 | 8.2124 | 37.0789 | 50.2966 | 35.2814 | 9.1828 | 18.401 | 10.5694 | 22.2362 | 26.1074 | 49.1558 | 24.8709 | 3.334 | 20.9101 | 31.8393 | 5.0433 | 24.3692 | 11.8059 | 23.7044 | 18.7545 | 11.6243 | 27.9365 | 17.063 | 562.7263
707 | 6.1371 | 26.9607 | 26.9162 | 6.0665 | 33.8706 | 43.7734 | 37.1214 | 10.6283 | 14.5652 | 12.3391 | 21.6094 | 27.3741 | 45.0806 | 23.5409 | 3.8835 | 26.9874 | 37.7031 | 4.3307 | 30.2947 | 10.5667 | 14.6018 | 18.199 | 12.125 | 53.6766 | 20.7147 | 569.0668
708 | 7.9701 | 44.0939 | 30.1684 | 8.1732 | 18.0667 | 49.1151 | 23.6326 | 10.611 | 12.6673 | 10.6636 | 19.9754 | 20.3363 | 40.0778 | 19.5411 | 3.1216 | 16.9983 | 33.5738 | 5.7445 | 28.87 | 12.3319 | 13.4819 | 15.6563 | 11.7829 | 54.0781 | 21.4521 | 532.1842
709 | 7.8571 | 42.4732 | 30.8754 | 8.2292 | 25.0928 | 37.5502 | 38.2189 | 11.6646 | 12.8794 | 12.5405 | 14.6048 | 23.6466 | 40.8061 | 20.4607 | 2.4003 | 19.1015 | 28.9616 | 4.9325 | 31.5981 | 9.5019 | 20.1466 | 19.1402 | 10.9994 | 51.9551 | 19.2848 | 544.9214
710 | 7.2045 | 34.1009 | 27.8154 | 8.0818 | 32.7443 | 42.8641 | 30.4814 | 9.2843 | 19.4119 | 13.9061 | 16.0197 | 20.6593 | 31.0223 | 24.218 | 2.8439 | 22.9705 | 36.1998 | 5.2498 | 19.1065 | 11.7526 | 22.4181 | 21.0445 | 8.9066 | 50.2104 | 15.3249 | 533.8418
711 | 7.2016 | 41.9649 | 23.806 | 8.0101 | 21.5394 | 46.9378 | 35.4477 | 11.3827 | 15.6972 | 9.3638 | 19.6151 | 28.4213 | 33.8796 | 20.4248 | 2.7937 | 19.9947 | 29.9785 | 4.8175 | 18.5397 | 7.7101 | 21.4339 | 15.4854 | 9.0879 | 29.6991 | 14.2663 | 497.4985
712 | 8.1092 | 47.7853 | 22.1177 | 5.1058 | 29.6207 | 42.1784 | 29.1203 | 10.279 | 17.0949 | 14.0937 | 21.845 | 20.063 | 42.0608 | 20.7582 | 2.4706 | 25.3476 | 29.0987 | 5.8003 | 25.8623 | 10.6476 | 18.3592 | 18.7962 | 11.1891 | 55.2549 | 21.3884 | 554.4467
713 | 8.1164 | 48.1505 | 27.3277 | 8.4214 | 38.8398 | 35.3482 | 35.939 | 8.1483 | 11.8453 | 8.8903 | 18.7024 | 20.666 | 55.0317 | 20.3264 | 2.9891 | 21.3934 | 34.3605 | 5.5318 | 18.5138 | 13.2953 | 25.7624 | 14.4446 | 10.08 | 37.2343 | 17.845 | 547.2039
714 | 7.1274 | 43.8792 | 25.2653 | 7.9588 | 32.3283 | 49.9553 | 31.2665 | 9.6793 | 19.2439 | 7.1555 | 20.978 | 14.1858 | 25.5547 | 25.246 | 3.904 | 24.7091 | 26.5687 | 5.4269 | 32.1706 | 10.5573 | 22.3428 | 16.2293 | 9.5977 | 51.4215 | 14.0374 | 536.7895
715 | 6.8024 | 41.6609 | 31.3995 | 6.1666 | 27.3986 | 40.8631 | 27.8822 | 8.8317 | 18.7118 | 12.3749 | 19.6664 | 24.4394 | 40.0408 | 21.7759 | 3.7281 | 22.8585 | 27.5409 | 4.4991 | 29.5601 | 13.3556 | 26.3098 | 17.4327 | 11.5669 | 43.967 | 16.539 | 545.3723
716 | 6.8272 | 29.9602 | 20.2954 | 7.2643 | 36.3732 | 40.0136 | 35.3801 | 10.5059 | 16.1864 | 16.2134 | 19.3289 | 21.3066 | 22.5085 | 25.7696 | 2.8764 | 24.0565 | 31.0802 | 4.6239 | 31.1275 | 13.4846 | 18.3507 | 16.726 | 10.5778 | 48.7144 | 18.6585 | 528.2097
717 | 6.4929 | 46.5106 | 24.7709 | 6.7682 | 37.3571 | 42.5904 | 35.1673 | 9.3594 | 16.4565 | 14.7373 | 16.0221 | 22.2996 | 44.3898 | 20.5291 | 3.2123 | 16.894 | 37.0065 | 5.825 | 31.1495 | 11.7086 | 22.1611 | 13.0502 | 10.3061 | 50.2195 | 13.9391 | 558.9231
718 | 5.387 | 43.5013 | 29.3836 | 5.9329 | 36.8307 | 44.3704 | 20.8541 | 6.6031 | 18.1851 | 11.1017 | 13.3455 | 23.5607 | 42.6081 | 17.5661 | 3.9292 | 20.6505 | 31.9146 | 5.3888 | 16.5641 | 12.9249 | 20.6214 | 20.1977 | 9.2581 | 26.8962 | 20.6628 | 508.2386
719 | 7.8539 | 39.6499 | 24.943 | 4.6913 | 31.9481 | 42.7889 | 34.7863 | 10.0721 | 15.4892 | 11.1804 | 17.245 | 18.1993 | 44.3192 | 22.658 | 3.7824 | 24.8393 | 37.075 | 4.1154 | 21.5178 | 8.2107 | 25.1979 | 21.6766 | 8.9797 | 42.3813 | 15.4365 | 539.0374
720 | 7.0244 | 29.4626 | 26.792 | 7.3151 | 31.103 | 41.8815 | 29.4389 | 10.6595 | 17.2177 | 15.3929 | 13.5138 | 19.1059 | 52.0027 | 24.6498 | 3.8426 | 19.4613 | 27.4376 | 5.9493 | 32.6113 | 11.1175 | 24.5764 | 18.106 | 7.9325 | 37.4147 | 9.8026 | 523.8117
721 | 6.7692 | 34.071 | 27.7879 | 8.2913 | 32.2027 | 48.4529 | 33.6928 | 8.9549 | 18.3355 | 15.1754 | 18.5952 | 13.964 | 50.3667 | 21.1893 | 3.0249 | 26.6444 | 27.9538 | 5.4663 | 32.7742 | 11.7175 | 22.4818 | 20.9597 | 11.3004 | 51.391 | 19.9645 | 571.5271
722 | 8.0858 | 40.6413 | 30.6357 | 8.4507 | 36.0129 | 48.6294 | 33.3565 | 10.2631 | 15.2271 | 12.8652 | 16.3106 | 19.4269 | 48.2197 | 20.7037 | 3.9412 | 27.118 | 34.9385 | 5.3086 | 24.2145 | 12.3353 | 24.6948 | 21.4878 | 9.571 | 42.9398 | 17.6477 | 573.0263
723 | 4.7508 | 22.4687 | 28.2616 | 7.6303 | 23.211 | 46.1694 | 37.9303 | 7.5346 | 15.2978 | 15.7184 | 20.7858 | 27.1258 | 52.1915 | 22.7137 | 3.0921 | 20.9842 | 35.8763 | 4.2134 | 25.2506 | 13.7718 | 20.2159 | 21.2282 | 10.6461 | 53.7359 | 17.8197 | 558.6238
724 | 7.5013 | 39.7472 | 24.9674 | 7.4356 | 34.4631 | 48.4182 | 36.2048 | 6.2291 | 12.1779 | 16.3965 | 18.6333 | 23.8216 | 44.8667 | 20.151 | 3.7199 | 25.7406 | 33.4306 | 5.9013 | 32.2418 | 13.0483 | 21.6549 | 20.2792 | 10.6578 | 56.2329 | 14.0448 | 577.9658
725 | 8.0426 | 45.5139 | 30.0825 | 7.9764 | 31.0889 | 35.5824 | 37.9491 | 9.0876 | 19.7037 | 12.278 | 20.8895 | 28.2221 | 48.1294 | 13.6248 | 3.447 | 20.2931 | 28.4279 | 4.9642 | 30.1646 | 9.0593 | 21.5794 | 19.3519 | 8.1128 | 54.2981 | 13.9822 | 561.8514
726 | 7.8352 | 36.1595 | 26.1562 | 6.956 | 36.7531 | 52.2774 | 35.0582 | 8.1043 | 18.9713 | 14.1894 | 20.539 | 20.377 | 44.4046 | 25.8068 | 3.3508 | 16.9904 | 28.5428 | 5.5495 | 29.6458 | 11.3772 | 18.2145 | 17.0502 | 10.7284 | 40.3873 | 18.9533 | 554.3781
727 | 6.4025 | 39.3057 | 28.9529 | 6.6112 | 37.4158 | 36.8907 | 34.4147 | 4.7398 | 16.8697 | 12.7683 | 15.6015 | 19.3529 | 49.008 | 15.3456 | 3.4479 | 26.0013 | 34.4541 | 5.7133 | 22.9451 | 11.5157 | 24.8678 | 16.7223 | 11.2697 | 38.9972 | 17.6934 | 537.3073
728 | 6.0494 | 46.0676 | 24.5388 | 8.3916 | 30.7353 | 50.9955 | 38.8487 | 7.9297 | 13.021 | 14.0766 | 13.697 | 19.835 | 40.3434 | 22.2622 | 3.931 | 24.6543 | 36.2562 | 4.6167 | 30.7138 | 13.3886 | 21.0508 | 19.0173 | 11.8264 | 25.2889 | 19.4897 | 547.0256
729 | 5.2553 | 41.0636 | 13.7966 | 5.6689 | 30.8188 | 40.02 | 26.4709 | 10.7361 | 17.2859 | 9.8584 | 19.2122 | 19.6503 | 50.5347 | 25.096 | 2.9689 | 24.528 | 36.5839 | 5.8943 | 25.7034 | 13.0007 | 19.7447 | 20.8869 | 8.8156 | 42.4606 | 16.1943 | 532.249
730 | 6.1249 | 45.2159 | 26.898 | 6.0428 | 37.4867 | 47.4255 | 34.0279 | 9.6918 | 17.298 | 9.5639 | 18.6884 | 24.5154 | 38.6517 | 22.7962 | 2.7697 | 21.6485 | 29.407 | 4.6657 | 25.2165 | 12.2578 | 19.2197 | 17.1524 | 9.9933 | 46.9589 | 12.8421 | 546.5588
731 | 5.9799 | 41.5744 | 29.3046 | 7.702 | 31.1073 | 48.1386 | 28.0801 | 10.1607 | 19.7477 | 14.3006 | 19.7452 | 22.6898 | 45.4675 | 20.1448 | 3.8679 | 26.4606 | 24.053 | 5.1088 | 27.3803 | 8.5655 | 24.2777 | 18.5477 | 9.2173 | 57.1992 | 16.6204 | 565.4416
732 | 8.2844 | 38.3837 | 21.5826 | 6.9443 | 21.7185 | 18.7511 | 31.9399 | 8.3231 | 15.1798 | 14.7432 | 19.9999 | 15.7246 | 33.5304 | 21.2332 | 3.1837 | 24.2359 | 28.4012 | 5.868 | 31.8436 | 10.9931 | 22.8244 | 18.6401 | 10.8727 | 51.593 | 20.0871 | 504.8814
733 | 4.5005 | 36.2904 | 29.8282 | 8.2081 | 36.0478 | 43.8973 | 36.6851 | 9.9429 | 15.8609 | 12.7778 | 22.2975 | 18.938 | 43.9294 | 18.9708 | 3.9154 | 19.5464 | 23.8653 | 5.1537 | 26.925 | 12.0965 | 15.2213 | 21.2775 | 9.4728 | 57.3831 | 13.1117 | 546.1434
734 | 6.2943 | 40.9298 | 23.8934 | 8.0959 | 26.0562 | 33.3257 | 31.4066 | 10.1734 | 18.8153 | 14.2004 | 20.9561 | 19.4848 | 39.127 | 18.5317 | 3.8464 | 27.3939 | 33.5856 | 5.8885 | 29.4132 | 10.2276 | 22.259 | 19.3404 | 10.6002 | 54.0296 | 14.2734 | 542.1484
735 | 7.811 | 41.3794 | 29.5415 | 6.3564 | 33.3305 | 41.6741 | 37.681 | 8.8153 | 18.5835 | 16.2885 | 21.7122 | 25.2871 | 43.6545 | 22.2777 | 3.9385 | 23.5465 | 34.2928 | 5.9069 | 32.788 | 11.7519 | 23.5124 | 21.9069 | 10.9195 | 50.7219 | 21.8677 | 595.546
736 | 8.0963 | 43.709 | 26.5271 | 5.835 | 27.176 | 28.53 | 27.9201 | 9.3495 | 19.0706 | 8.0176 | 16.0205 | 21.6835 | 51.3981 | 22.1625 | 3.9817 | 27.8963 | 34.3011 | 5.754 | 20.0495 | 13.7724 | 22.875 | 21.0338 | 12.3752 | 35.7391 | 19.0574 | 532.3315
737 | 7.4042 | 32.8546 | 26.3269 | 6.4485 | 33.118 | 35.3216 | 38.0369 | 8.655 | 12.6335 | 16.4307 | 16.8206 | 24.5291 | 25.0963 | 24.539 | 3.1755 | 25.713 | 36.7957 | 5.8191 | 29.6998 | 12.8395 | 15.5199 | 16.4927 | 7.0166 | 52.7898 | 16.102 | 530.1785
738 | 7.9241 | 39.8069 | 29.5708 | 7.68 | 21.3056 | 26.4363 | 32.1463 | 9.4619 | 19.4944 | 10.5953 | 20.8602 | 22.9075 | 42.0729 | 24.875 | 3.9246 | 24.5191 | 20.9107 | 3.9699 | 31.5704 | 9.4285 | 18.594 | 19.3475 | 10.5505 | 38.1014 | 22.2561 | 518.3096
739 | 6.3582 | 44.2217 | 27.8927 | 6.8375 | 35.0573 | 49.196 | 30.7093 | 8.3937 | 18.31 | 15.5216 | 15.4591 | 17.4588 | 48.554 | 15.9108 | 3.8801 | 27.5414 | 33.8733 | 5.1802 | 25.6128 | 13.198 | 21.0385 | 21.4012 | 6.0007 | 55.194 | 20.5043 | 573.3052
740 | 7.5366 | 47.4838 | 28.5086 | 6.6139 | 39.0116 | 40.9418 | 21.0242 | 9.7032 | 16.7451 | 14.7911 | 16.5471 | 27.4063 | 36.3658 | 23.4911 | 2.5212 | 19.839 | 35.515 | 5.9904 | 29.9462 | 9.6157 | 18.713 | 19.6689 | 11.5581 | 33.5247 | 15.1286 | 538.1909
741 | 8.2322 | 44.1921 | 15.7765 | 7.0076 | 37.7116 | 49.9024 | 31.9456 | 8.3727 | 19.6782 | 16.119 | 14.499 | 14.9144 | 47.5692 | 22.58 | 3.8881 | 18.3736 | 38.6628 | 3.8715 | 28.2087 | 9.4623 | 23.2083 | 21.483 | 10.4598 | 29.3435 | 11.9472 | 537.4093
742 | 6.5181 | 40.8264 | 28.5685 | 6.4729 | 27.5646 | 42.2697 | 37.017 | 9.8186 | 18.9045 | 16.5021 | 14.0267 | 17.002 | 34.1167 | 21.7454 | 3.9031 | 20.8717 | 36.7527 | 3.6949 | 32.2104 | 11.8592 | 19.8538 | 16.0396 | 9.0242 | 40.7422 | 18.9973 | 535.3024
743 | 6.8067 | 39.5206 | 31.3425 | 8.4642 | 33.9487 | 42.9361 | 31.1236 | 9.7494 | 19.4097 | 16.4299 | 15.5583 | 26.4199 | 53.9639 | 19.7381 | 2.7838 | 11.8388 | 30.013 | 5.3526 | 28.1829 | 13.5029 | 23.5978 | 19.8492 | 9.0983 | 48.4604 | 17.5384 | 565.6297
744 | 8.1032 | 37.7391 | 23.377 | 7.2638 | 37.9985 | 47.8658 | 30.4527 | 10.0775 | 18.6737 | 15.7869 | 21.7865 | 24.3847 | 53.6206 | 25.8874 | 3.9081 | 22.4464 | 21.5644 | 5.7833 | 32.5906 | 9.307 | 24.2593 | 21.0606 | 10.7621 | 51.0997 | 15.2704 | 581.0692
745 | 5.5274 | 39.0042 | 23.9361 | 8.6492 | 35.1017 | 47.4198 | 25.36 | 6.0868 | 18.3732 | 10.4085 | 20.0455 | 22.4773 | 46.5819 | 22.9836 | 3.1868 | 21.6934 | 29.1816 | 5.5435 | 25.7239 | 12.0415 | 18.5263 | 20.5839 | 11.579 | 45.0565 | 17.7417 | 542.8134
746 | 6.1049 | 44.2638 | 16.8128 | 8.2678 | 35.2598 | 48.6274 | 38.0065 | 9.9123 | 13.0008 | 12.1074 | 17.5768 | 23.0387 | 39.1125 | 22.2929 | 3.6298 | 26.9484 | 32.8111 | 5.0658 | 26.5739 | 9.1535 | 21.0675 | 21.0076 | 10.1732 | 43.1953 | 16.3735 | 550.3838
747 | 5.3027 | 43.1172 | 32.9254 | 6.1661 | 20.3822 | 37.2499 | 38.7864 | 7.9537 | 12.0506 | 14.2266 | 18.6291 | 25.9706 | 52.2554 | 21.1248 | 3.3973 | 19.8208 | 32.4331 | 4.7445 | 18.306 | 12.5774 | 24.2029 | 15.9864 | 11.6554 | 53.1264 | 15.2034 | 547.5944
748 | 6.7839 | 31.9696 | 19.1434 | 7.2112 | 29.6745 | 45.7893 | 35.0785 | 10.3887 | 19.5138 | 11.901 | 14.9236 | 25.7111 | 49.7884 | 24.7127 | 3.9706 | 16.9176 | 21.7326 | 4.9483 | 18.7701 | 13.6587 | 24.2667 | 17.2352 | 10.2769 | 53.7491 | 19.6815 | 537.7972
749 | 7.4839 | 27.4962 | 22.4902 | 8.4992 | 28.5455 | 47.1196 | 30.7361 | 11.1511 | 16.2068 | 14.8318 | 11.3176 | 23.6747 | 41.2682 | 21.1165 | 3.4427 | 15.7678 | 31.7394 | 4.8943 | 28.1303 | 13.5007 | 18.3608 | 14.5236 | 9.6914 | 35.3988 | 20.7583 | 508.1459
750 | 7.2193 | 36.4883 | 25.3308 | 7.4934 | 34.3166 | 47.0949 | 28.99 | 6.8423 | 17.58 | 11.9397 | 21.2319 | 25.4537 | 54.9476 | 25.8397 | 3.1304 | 21.8989 | 27.6061 | 3.2829 | 22.9659 | 11.3611 | 16.7314 | 21.3862 | 6.9225 | 53.5133 | 15.469 | 555.0357
751 | 6.0535 | 39.2337 | 28.0432 | 6.9701 | 35.9528 | 47.5945 | 32.4146 | 11.1235 | 14.4466 | 12.85 | 19.6182 | 24.0017 | 43.6011 | 23.283 | 2.8061 | 19.2683 | 31.6549 | 3.9352 | 31.3785 | 12.3071 | 20.8759 | 20.2258 | 9.9071 | 45.4691 | 20.7557 | 563.7705
752 | 8.0859 | 40.5165 | 25.4937 | 6.5319 | 27.2459 | 42.842 | 22.5653 | 10.5181 | 12.4981 | 8.7051 | 17.8101 | 22.1411 | 28.439 | 20.9636 | 3.9861 | 15.8627 | 27.5229 | 5.7527 | 17.5288 | 12.6433 | 12.3256 | 20.2416 | 10.8256 | 47.544 | 18.8032 | 487.3927
753 | 5.7405 | 34.3774 | 31.7451 | 4.8109 | 32.4022 | 33.035 | 19.1937 | 8.6252 | 12.7161 | 16.109 | 19.183 | 23.6115 | 50.313 | 20.7556 | 3.842 | 16.3342 | 32.7523 | 5.1454 | 24.8644 | 10.8747 | 20.4793 | 21.4636 | 5.8695 | 33.0546 | 12.7396 | 500.0378
754 | 6.6383 | 41.7329 | 16.6828 | 7.3546 | 30.707 | 37.3574 | 34.738 | 10.5665 | 19.5163 | 13.3612 | 21.5065 | 19.4783 | 40.6219 | 25.7383 | 3.3047 | 20.3528 | 19.3898 | 5.6306 | 28.632 | 9.8131 | 15.5889 | 16.4714 | 7.2452 | 53.7039 | 13.346 | 519.4785
755 | 6.9182 | 45.7997 | 27.5012 | 8.3818 | 30.847 | 48.0054 | 35.5965 | 9.3899 | 10.5618 | 16.3353 | 13.1863 | 26.5426 | 43.1507 | 24.6393 | 3.086 | 21.5436 | 33.673 | 5.195 | 19.209 | 9.9914 | 21.8962 | 16.2762 | 8.833 | 47.9049 | 16.8906 | 551.3547
756 | 6.189 | 39.1236 | 33.4931 | 6.7245 | 33.1516 | 44.7407 | 24.0418 | 10.0717 | 13.3463 | 13.7217 | 21.6723 | 27.6618 | 38.2425 | 24.4526 | 2.5015 | 26.0427 | 37.9598 | 4.3008 | 24.5198 | 13.6142 | 20.1669 | 13.6478 | 10.7588 | 46.6617 | 17.5001 | 554.3074
757 | 5.1817 | 39.727 | 27.0084 | 8.2568 | 27.5921 | 36.7147 | 36.4163 | 10.2714 | 16.9266 | 13.8181 | 16.7902 | 16.6223 | 53.7544 | 24.7886 | 2.7975 | 21.5604 | 39.1447 | 5.9138 | 27.3768 | 12.5074 | 23.0654 | 19.0373 | 7.5862 | 54.0632 | 16.5043 | 563.4253
758 | 5.8289 | 30.5168 | 29.9995 | 6.5469 | 35.1251 | 37.5981 | 26.0977 | 8.9594 | 19.1235 | 10.5133 | 20.6895 | 13.9124 | 47.9991 | 23.085 | 3.6377 | 20.3564 | 26.4992 | 4.6763 | 22.4804 | 12.9047 | 20.2231 | 16.6058 | 11.3679 | 49.426 | 15.6204 | 519.7931
759 | 5.8999 | 34.4048 | 32.491 | 8.7104 | 37.5436 | 31.3145 | 30.5301 | 6.9538 | 19.4511 | 12.4078 | 21.5982 | 27.3135 | 34.4033 | 25.9473 | 3.5626 | 23.0779 | 32.1031 | 4.0964 | 24.5162 | 13.5413 | 20.0835 | 19.0333 | 11.3643 | 37.2027 | 20.7092 | 538.2598
760 | 8.2459 | 26.3625 | 31.5432 | 7.1501 | 31.5762 | 43.9418 | 30.7065 | 7.9247 | 16.4742 | 9.2921 | 12.7884 | 24.2935 | 41.8701 | 18.1928 | 3.5362 | 16.2328 | 30.371 | 4.4243 | 27.0728 | 10.7443 | 24.2652 | 21.2226 | 10.4141 | 52.3941 | 18.2904 | 529.33
761 | 8.3531 | 35.5851 | 29.9156 | 7.2746 | 24.7922 | 51.0269 | 20.2711 | 10.2896 | 15.365 | 9.1215 | 16.7426 | 22.8936 | 47.2707 | 25.963 | 3.7831 | 22.465 | 35.6564 | 5.8586 | 23.4441 | 9.5741 | 26.8326 | 20.8463 | 6.6392 | 33.4591 | 18.6784 | 532.1016
762 | 6.7772 | 39.2945 | 33.259 | 5.9445 | 28.6016 | 41.6891 | 35.3123 | 9.0604 | 17.8457 | 16.2748 | 13.1546 | 26.7797 | 52.3506 | 16.9063 | 3.7477 | 26.0576 | 36.2549 | 5.8436 | 32.7355 | 12.544 | 26.2452 | 21.8084 | 10.5595 | 51.9631 | 19.4941 | 590.5037
763 | 7.4349 | 37.5771 | 22.9511 | 8.3124 | 27.9863 | 50.3376 | 25.8257 | 10.3613 | 11.4551 | 14.9128 | 21.088 | 24.4019 | 42.2495 | 25.6939 | 3.8897 | 24.1176 | 30.3273 | 5.1178 | 30.9452 | 13.6779 | 25.9011 | 18.6508 | 10.3724 | 52.1934 | 17.5263 | 563.3067
764 | 7.7376 | 33.8022 | 26.422 | 8.3338 | 29.8131 | 51.4401 | 33.6441 | 8.2344 | 17.2556 | 10.8802 | 13.3159 | 17.6032 | 39.7979 | 15.5707 | 2.3788 | 22.4569 | 27.7572 | 4.6663 | 29.9506 | 8.1324 | 24.2084 | 20.2908 | 7.8471 | 39.3984 | 16.6456 | 517.5834
765 | 5.4262 | 31.8288 | 31.4649 | 8.3707 | 35.2698 | 36.6638 | 29.2767 | 11.5402 | 15.7069 | 11.7561 | 14.7963 | 20.7853 | 38.9736 | 24.4874 | 2.7015 | 20.0005 | 17.3343 | 5.3685 | 29.5654 | 10.9088 | 20.3065 | 18.4131 | 9.751 | 50.9903 | 14.6485 | 516.3352
766 | 6.7508 | 36.391 | 21.5991 | 5.7936 | 27.9282 | 51.6951 | 32.0507 | 10.288 | 14.9313 | 8.3704 | 22.3606 | 27.2383 | 53.7145 | 24.7997 | 3.8422 | 25.9914 | 34.6703 | 5.9968 | 32.582 | 9.1764 | 22.4595 | 19.5283 | 12.245 | 54.364 | 12.2412 | 577.0085
767 | 6.6923 | 32.1336 | 25.5848 | 5.9911 | 33.5777 | 27.3777 | 30.6506 | 8.2554 | 12.9677 | 14.843 | 21.8156 | 14.4307 | 41.998 | 25.4963 | 3.8094 | 19.5533 | 25.5354 | 5.5451 | 23.6824 | 9.6172 | 11.5123 | 16.1975 | 9.3732 | 56.6616 | 20.9386 | 504.2406
768 | 7.4762 | 27.4102 | 24.3068 | 8.3638 | 34.4846 | 47.972 | 37.3073 | 9.5752 | 19.6787 | 15.7793 | 21.6517 | 25.2288 | 30.3931 | 25.9716 | 3.2565 | 23.0089 | 26.398 | 4.8275 | 29.8943 | 9.7332 | 24.5986 | 20.8757 | 10.5725 | 50.7866 | 14.5394 | 554.0905
769 | 8.1917 | 48.8282 | 32.0083 | 6.8366 | 31.6322 | 45.5503 | 27.8195 | 9.2189 | 18.5213 | 14.9028 | 10.4999 | 14.3846 | 49.0341 | 21.4691 | 3.411 | 24.2963 | 35.032 | 5.5587 | 28.2105 | 12.9902 | 21.7583 | 19.8746 | 10.3606 | 44.8344 | 19.3036 | 564.5276
770 | 5.7073 | 43.3516 | 26.9058 | 8.7512 | 28.0574 | 52.2077 | 18.4635 | 8.9382 | 13.4847 | 13.3989 | 20.0354 | 27.4768 | 52.5474 | 22.1653 | 3.5918 | 24.9383 | 27.4161 | 5.2719 | 28.805 | 12.8881 | 23.1322 | 19.084 | 9.2376 | 43.658 | 19.1062 | 558.6205
771 | 7.9557 | 33.2117 | 29.4525 | 8.4495 | 31.8384 | 45.2788 | 28.0471 | 7.5634 | 15.2705 | 13.085 | 21.8002 | 15.1628 | 43.9185 | 18.5054 | 2.8385 | 19.023 | 35.2126 | 5.8142 | 26.6556 | 9.4271 | 24.633 | 20.9347 | 6.7029 | 55.8334 | 22.1768 | 548.7914
772 | 8.018 | 37.8923 | 31.8837 | 6.2529 | 34.0514 | 45.2233 | 35.7671 | 6.3303 | 19.2746 | 14.6046 | 14.0143 | 17.652 | 42.4156 | 21.7349 | 2.8628 | 24.0005 | 32.053 | 4.3729 | 30.788 | 11.0874 | 18.7869 | 14.6089 | 10.2665 | 33.7538 | 21.7663 | 539.4621
773 | 7.157 | 39.7317 | 26.3478 | 6.2126 | 26.6351 | 40.3578 | 31.1658 | 7.7758 | 18.7266 | 12.0809 | 22.4911 | 19.9882 | 50.1015 | 23.5366 | 3.8651 | 26.5764 | 31.0339 | 4.8807 | 32.5277 | 12.5503 | 24.1658 | 18.5816 | 9.9364 | 56.6123 | 21.469 | 574.5076
774 | 6.3828 | 41.6055 | 23.3681 | 7.7044 | 28.4701 | 34.4316 | 37.8079 | 8.6676 | 14.2827 | 14.5778 | 20.5539 | 25.7516 | 51.7151 | 24.7531 | 3.179 | 22.0485 | 25.1287 | 5.5015 | 18.393 | 12.7038 | 26.3438 | 16.3524 | 8.7059 | 34.6747 | 19.9477 | 533.0514
775 | 7.2627 | 37.771 | 22.1573 | 6.4385 | 38.2784 | 45.9549 | 37.2896 | 9.5442 | 17.9837 | 12.0407 | 12.9867 | 23.9705 | 42.0317 | 17.5217 | 3.675 | 24.5322 | 35.9634 | 3.8263 | 29.596 | 12.0437 | 19.603 | 20.3558 | 9.1642 | 39.5467 | 12.7347 | 542.2726
776 | 5.2838 | 46.0442 | 26.0075 | 8.6748 | 35.2435 | 39.0225 | 27.2354 | 10.0458 | 17.1601 | 15.8821 | 12.7908 | 27.5835 | 32.79 | 20.8048 | 3.7136 | 13.8998 | 34.0017 | 5.4538 | 24.7688 | 13.6145 | 13.9949 | 18.4692 | 7.6552 | 39.7305 | 21.9477 | 521.8187
777 | 7.4089 | 33.2479 | 24.5276 | 5.0101 | 36.0819 | 42.4857 | 27.1957 | 7.1601 | 18.1719 | 16.7308 | 14.3939 | 20.8969 | 53.4325 | 18.0467 | 2.584 | 19.9783 | 28.2571 | 5.9495 | 28.834 | 12.7631 | 18.7261 | 18.0382 | 10.9021 | 44.7375 | 15.6504 | 531.211
778 | 8.021 | 39.5313 | 17.3428 | 8.0252 | 22.757 | 48.1861 | 27.5618 | 6.297 | 18.1761 | 16.427 | 15.1644 | 28.0459 | 40.4954 | 23.9406 | 2.6093 | 27.4048 | 35.8688 | 4.7575 | 30.9703 | 11.9157 | 22.7697 | 16.2034 | 9.1442 | 45.2272 | 15.2406 | 542.0833
779 | 7.1967 | 34.5145 | 31.9757 | 7.9762 | 25.2554 | 40.95 | 25.8477 | 9.3456 | 17.6468 | 14.2525 | 17.9855 | 22.218 | 36.5073 | 22.9988 | 3.9718 | 20.7614 | 32.8828 | 5.3526 | 23.2725 | 10.5163 | 16.923 | 21.947 | 6.5398 | 57.6529 | 16.1797 | 530.6707
780 | 6.4665 | 48.7384 | 23.9306 | 7.5792 | 38.9108 | 45.7879 | 38.0696 | 8.071 | 18.5713 | 13.2121 | 21.4421 | 27.4967 | 46.131 | 23.8333 | 3.434 | 23.4638 | 35.4563 | 5.9004 | 32.6114 | 11.2304 | 11.6211 | 20.7648 | 10.8887 | 41.15 | 13.8705 | 578.6318
781 | 6.3478 | 42.5247 | 25.4695 | 6.2356 | 34.92 | 32.0024 | 21.4117 | 7.5403 | 18.9506 | 11.2994 | 13.9895 | 23.0766 | 50.0129 | 25.9752 | 3.4332 | 25.2925 | 29.779 | 5.9886 | 25.4683 | 13.6859 | 24.8104 | 15.8974 | 11.1257 | 43.9416 | 13.0102 | 532.1888
782 | 7.0413 | 37.2189 | 26.9151 | 7.7819 | 21.7071 | 34.3671 | 29.2122 | 9.8976 | 19.3922 | 9.8442 | 14.0958 | 21.7196 | 40.0267 | 24.1332 | 3.9386 | 16.1931 | 32.8627 | 4.4324 | 27.9861 | 11.5964 | 25.71 | 16.1268 | 11.8322 | 38.6143 | 16.8801 | 509.5258
783 | 7.6109 | 40.1597 | 21.0085 | 8.5253 | 38.2215 | 42.9834 | 27.5427 | 8.9095 | 13.8044 | 10.3945 | 19.8121 | 25.9648 | 42.9 | 25.5102 | 2.2755 | 24.2394 | 34.822 | 5.7053 | 30.1129 | 9.2819 | 23.6021 | 14.2668 | 8.2514 | 33.997 | 15.2105 | 535.112
784 | 6.3272 | 38.9316 | 21.5624 | 7.1361 | 14.5039 | 46.6196 | 38.4653 | 9.0065 | 16.458 | 16.5704 | 20.3922 | 15.6039 | 41.3161 | 22.3124 | 3.3486 | 27.0485 | 36.4558 | 5.703 | 30.6734 | 11.6838 | 24.3174 | 15.4069 | 12.4841 | 52.1878 | 16.9978 | 551.5127
785 | 8.1514 | 47.9025 | 32.4894 | 4.5119 | 33.1147 | 45.5073 | 35.184 | 10.1691 | 17.0916 | 11.6284 | 13.3221 | 20.2075 | 48.3848 | 24.4283 | 3.3639 | 25.418 | 37.1952 | 5.7161 | 25.1026 | 13.44 | 24.1557 | 17.5762 | 9.1419 | 57.0971 | 15.1308 | 585.4303
786 | 5.6548 | 43.3267 | 30.4323 | 6.9247 | 24.7465 | 37.6282 | 30.4626 | 10.8092 | 13.9513 | 15.9035 | 17.7101 | 24.5552 | 44.6126 | 24.9966 | 3.8229 | 22.9596 | 32.1921 | 5.3584 | 32.0567 | 13.3723 | 19.2743 | 16.3805 | 10.8024 | 47.9616 | 18.0763 | 553.9715
787 | 6.4329 | 40.6237 | 24.9196 | 8.4306 | 32.2101 | 33.1571 | 31.8548 | 11.7198 | 13.9305 | 12.7554 | 21.3547 | 23.1694 | 26.2738 | 24.49 | 3.0853 | 26.3078 | 35.7513 | 4.1249 | 23.0674 | 13.4212 | 21.5165 | 21.3343 | 9.8744 | 37.2371 | 16.986 | 524.0285
788 | 8.1556 | 40.323 | 33.2339 | 8.7358 | 34.7774 | 33.3652 | 36.5215 | 7.4478 | 14.7735 | 11.0824 | 18.7401 | 23.9829 | 36.763 | 23.871 | 3.4159 | 20.7662 | 35.2225 | 4.8303 | 30.9545 | 12.352 | 20.7295 | 17.7383 | 11.4789 | 44.677 | 19.006 | 552.9442
789 | 3.373 | 36.5417 | 18.0981 | 5.9635 | 39.4135 | 42.9099 | 32.548 | 10.6519 | 13.3195 | 12.4303 | 10.4676 | 18.9593 | 35.9491 | 21.1382 | 3.3779 | 21.1548 | 31.2084 | 3.838 | 22.4033 | 11.4378 | 16.801 | 15.6629 | 10.4071 | 59.7455 | 17.9043 | 515.7049
790 | 8.27 | 44.9089 | 23.2457 | 5.7622 | 34.5306 | 38.9693 | 36.7215 | 8.0586 | 19.5364 | 9.3808 | 20.2098 | 19.8042 | 43.8728 | 24.5116 | 3.268 | 22.8864 | 22.0292 | 3.9398 | 25.9831 | 12.1987 | 22.7224 | 18.9642 | 12.2507 | 51.9127 | 17.2655 | 551.203
791 | 7.4134 | 34.8222 | 21.8851 | 7.1628 | 34.1139 | 50.1893 | 25.7656 | 10.5432 | 15.6899 | 13.5233 | 18.807 | 20.4647 | 43.7656 | 20.0821 | 3.1832 | 17.2415 | 35.6175 | 4.7937 | 30.848 | 12.3546 | 22.9803 | 17.679 | 10.3038 | 30.5063 | 18.4116 | 528.1474
792 | 7.8356 | 39.5085 | 31.893 | 5.4872 | 34.4566 | 37.4872 | 26.6309 | 10.0432 | 17.9505 | 14.5624 | 19.3081 | 16.8106 | 46.4369 | 25.4226 | 2.9592 | 21.1484 | 27.1986 | 4.5786 | 30.0813 | 13.998 | 12.0439 | 21.8676 | 12.2294 | 29.0499 | 21.8383 | 530.8265
793 | 5.5923 | 42.0847 | 26.5997 | 8.1213 | 30.7291 | 50.9592 | 37.0491 | 7.7259 | 14.894 | 9.5835 | 19.3165 | 27.6351 | 48.7755 | 15.3715 | 2.9116 | 25.121 | 30.8497 | 5.8075 | 19.1217 | 11.4342 | 20.0786 | 14.5536 | 10.9222 | 37.8776 | 13.1976 | 536.3125
794 | 7.1664 | 43.1032 | 29.7125 | 8.4437 | 33.8177 | 44.5525 | 36.4419 | 10.4057 | 12.7683 | 15.3201 | 13.5774 | 25.8714 | 46.5318 | 22.9069 | 3.9217 | 21.7035 | 32.4359 | 5.6723 | 31.1223 | 13.5335 | 20.0855 | 17.8476 | 8.5939 | 40.6153 | 13.8315 | 559.9826
795 | 6.7362 | 33.7042 | 26.8392 | 6.1197 | 32.5789 | 38.4736 | 28.3606 | 10.7007 | 15.203 | 14.6563 | 19.6962 | 20.3405 | 38.4292 | 25.9832 | 3.9882 | 26.017 | 31.0869 | 5.5835 | 27.5968 | 13.3668 | 21.3405 | 19.6087 | 10.845 | 44.8637 | 15.3282 | 537.447
796 | 5.6195 | 39.6496 | 25.4576 | 4.6383 | 21.3719 | 33.1735 | 31.8989 | 9.0316 | 16.6218 | 14.7594 | 21.4515 | 25.6845 | 37.1287 | 22.6754 | 3.001 | 25.6202 | 32.3322 | 5.6314 | 29.3664 | 10.7857 | 23.684 | 21.8066 | 9.1447 | 46.4597 | 20.5014 | 537.4955
797 | 5.757 | 36.9402 | 26.9805 | 8.6299 | 38.6622 | 44.9232 | 26.9437 | 9.4397 | 11.4055 | 15.7336 | 21.7442 | 25.3601 | 40.7087 | 16.8913 | 2.1961 | 23.3411 | 21.5032 | 4.5796 | 25.1727 | 12.6263 | 16.3921 | 14.32 | 12.2838 | 51.3065 | 17.0249 | 530.8659
798 | 7.611 | 37.7952 | 29.8869 | 4.5501 | 34.7006 | 50.876 | 31.1537 | 8.3254 | 13.5882 | 13.5706 | 19.162 | 23.7321 | 22.6553 | 13.729 | 3.3331 | 25.6271 | 26.7981 | 5.346 | 30.0396 | 8.6996 | 21.6798 | 19.5826 | 11.9006 | 48.9823 | 17.6568 | 530.9818
799 | 7.3237 | 46.8502 | 25.3979 | 6.497 | 26.8293 | 41.2519 | 25.7803 | 9.1372 | 18.7929 | 13.0641 | 11.4646 | 23.2611 | 46.2985 | 25.2933 | 3.7365 | 15.0676 | 25.8205 | 5.9161 | 26.1786 | 11.4988 | 22.1331 | 20.4031 | 10.7077 | 38.118 | 16.9685 | 523.7905
800 | 5.344 | 33.4256 | 23.6324 | 7.5396 | 23.7758 | 33.4609 | 30.5924 | 7.5771 | 12.823 | 11.5956 | 14.1536 | 12.4699 | 39.7825 | 19.8971 | 3.8839 | 26.6751 | 37.5376 | 4.5542 | 23.8214 | 12.8281 | 24.7711 | 18.1586 | 9.3894 | 51.5904 | 15.2769 | 504.5562
801 | 4.8931 | 37.1407 | 27.4103 | 6.1328 | 35.7528 | 42.259 | 35.3917 | 9.4178 | 13.8739 | 15.6621 | 21.4901 | 24.32 | 41.0697 | 25.1324 | 2.45 | 23.745 | 28.5441 | 4.3878 | 26.6753 | 10.6721 | 18.3572 | 20.7904 | 9.6962 | 55.0279 | 17.4642 | 557.7569
802 | 7.1068 | 26.075 | 31.9353 | 7.9941 | 31.441 | 46.7662 | 32.02 | 9.7834 | 19.2677 | 12.4976 | 14.0848 | 24.4218 | 38.0819 | 25.7997 | 3.8453 | 27.2267 | 30.5607 | 4.0947 | 28.423 | 13.0361 | 19.5804 | 21.7573 | 9.2764 | 40.5892 | 15.1083 | 540.7734
803 | 8.1648 | 38.6886 | 27.0071 | 8.7708 | 25.7685 | 44.3445 | 28.9502 | 9.8563 | 12.1258 | 10.3717 | 14.8644 | 26.3354 | 27.4365 | 16.5204 | 3.6492 | 21.1272 | 35.3056 | 5.3345 | 30.6979 | 13.6938 | 23.5375 | 18.5513 | 8.4818 | 50.6217 | 15.7486 | 525.9538
804 | 7.2038 | 46.462 | 23.123 | 7.9496 | 34.3216 | 33.4394 | 36.9949 | 11.436 | 16.9096 | 16.5567 | 14.9711 | 21.7284 | 51.4448 | 24.5475 | 3.287 | 21.8993 | 36.9873 | 5.368 | 29.4283 | 9.9059 | 19.5482 | 14.0013 | 9.12 | 50.4167 | 20.6156 | 567.666
805 | 7.4908 | 36.705 | 31.4021 | 7.706 | 31.6148 | 47.4789 | 31.7777 | 11.0185 | 13.1939 | 9.7684 | 21.4459 | 19.8666 | 34.6868 | 20.526 | 3.2919 | 24.2516 | 37.9673 | 5.588 | 18.4061 | 13.1432 | 20.1851 | 20.128 | 11.0874 | 38.4266 | 19.301 | 536.4576
806 | 7.1881 | 37.6224 | 28.1093 | 8.1105 | 26.402 | 47.5315 | 27.3479 | 10.1774 | 13.7183 | 16.1609 | 17.0815 | 18.4097 | 33.3057 | 16.746 | 2.9683 | 26.5636 | 20.1586 | 4.6267 | 22.7145 | 11.8239 | 26.2952 | 18.2595 | 9.2715 | 50.2016 | 9.5495 | 510.3444
807 | 6.6932 | 27.0675 | 32.6845 | 8.4635 | 28.7054 | 42.0139 | 33.4723 | 10.3135 | 18.3986 | 12.6511 | 15.6885 | 25.4444 | 42.0149 | 23.3284 | 3.3013 | 20.4919 | 21.6233 | 5.1865 | 17.9995 | 8.4658 | 15.1686 | 11.5448 | 8.8424 | 45.721 | 18.8392 | 504.124
808 | 7.366 | 28.177 | 22.5448 | 7.2539 | 26.7354 | 49.1988 | 20.9681 | 10.9923 | 17.4074 | 16.3945 | 19.9907 | 22.0855 | 49.6952 | 20.9485 | 2.7753 | 22.5865 | 33.2131 | 5.9849 | 27.2308 | 11.2453 | 24.7556 | 20.9344 | 11.6892 | 42.7364 | 19.5705 | 542.4796
809 | 3.612 | 32.69 | 24.1234 | 6.7511 | 29.6784 | 48.1993 | 33.1506 | 7.5844 | 18.5201 | 8.2381 | 20.9293 | 21.3774 | 43.8649 | 23.3171 | 3.9781 | 23.0142 | 34.1485 | 5.0298 | 26.8747 | 13.9025 | 23.8132 | 18.7867 | 10.0321 | 33.3831 | 17.6606 | 532.6592
810 | 7.8116 | 48.0414 | 28.5926 | 6.6462 | 32.4934 | 47.4725 | 34.6049 | 7.9172 | 17.3243 | 11.8424 | 12.2586 | 22.7978 | 42.9242 | 16.6035 | 3.6046 | 18.5925 | 34.0356 | 4.2375 | 28.8867 | 13.6428 | 14.8784 | 16.4677 | 11.8148 | 55.1928 | 21.9977 | 560.6818
811 | 6.3073 | 46.7381 | 25.0214 | 8.4704 | 36.1905 | 35.2449 | 33.6231 | 9.5118 | 18.1593 | 13.6601 | 15.1235 | 26.6512 | 41.9249 | 22.4387 | 3.0954 | 20.5552 | 26.3103 | 5.7299 | 24.5028 | 9.5806 | 22.6725 | 19.7771 | 7.9137 | 27.3112 | 15.807 | 522.3208
812 | 7.5431 | 26.19 | 29.3843 | 7.5094 | 21.3934 | 35.6663 | 29.196 | 10.3209 | 15.0771 | 13.8266 | 20.9093 | 26.5595 | 41.7733 | 21.5385 | 3.6379 | 23.8073 | 35.865 | 5.6994 | 30.7263 | 11.877 | 23.4997 | 13.3381 | 8.0591 | 44.6976 | 18.8174 | 526.9121
813 | 7.1517 | 32.219 | 21.2459 | 6.908 | 22.9763 | 51.018 | 26.5637 | 11.1203 | 18.0525 | 11.8961 | 20.6015 | 24.6491 | 48.2601 | 25.2997 | 3.7636 | 24.5239 | 30.8085 | 4.2367 | 32.139 | 9.9829 | 15.5675 | 17.0579 | 9.0787 | 59.3283 | 19.43 | 553.8791
814 | 5.7752 | 35.5862 | 26.6009 | 7.9611 | 29.5993 | 44.5649 | 34.6765 | 10.0403 | 19.9813 | 15.9115 | 19.4099 | 23.5667 | 44.1928 | 15.9047 | 3.8782 | 22.7783 | 32.6399 | 4.3272 | 25.6927 | 12.2749 | 23.6224 | 19.1508 | 8.1702 | 55.9561 | 21.0934 | 563.3551
815 | 5.3235 | 32.4306 | 20.3191 | 6.2595 | 19.1682 | 52.0453 | 30.1283 | 7.298 | 14.7229 | 15.2866 | 19.4916 | 11.8509 | 40.3607 | 25.3452 | 3.2695 | 25.5836 | 29.1238 | 4.8663 | 28.7636 | 12.3659 | 24.6341 | 19.013 | 10.9417 | 27.88 | 16.102 | 502.574
816 | 7.4509 | 45.1023 | 26.5226 | 6.6134 | 21.2212 | 45.0462 | 34.3194 | 10.8207 | 15.2979 | 13.8091 | 20.3189 | 23.5104 | 38.906 | 16.3237 | 3.2923 | 18.07 | 35.6797 | 5.3914 | 31.4025 | 13.0024 | 16.3248 | 20.8668 | 8.3086 | 51.6091 | 21.3872 | 550.5977
817 | 7.8513 | 36.7938 | 19.904 | 7.1828 | 29.7412 | 43.352 | 30.2848 | 11.7916 | 18.7263 | 12.8628 | 22.203 | 27.2448 | 36.2279 | 25.4752 | 3.924 | 23.3945 | 25.107 | 5.7447 | 16.6843 | 13.9993 | 24.5655 | 21.5717 | 9.0785 | 54.2409 | 14.4222 | 542.3741
818 | 6.2091 | 45.6646 | 29.9528 | 8.0408 | 15.2242 | 39.1323 | 23.2435 | 9.4175 | 18.6226 | 16.7323 | 20.6293 | 19.0834 | 44.6363 | 24.1554 | 3.0984 | 21.75 | 35.9939 | 4.9618 | 31.5683 | 12.2022 | 17.5549 | 17.1883 | 10.6279 | 54.7555 | 20.4537 | 550.8989
819 | 7.499 | 42.564 | 27.2312 | 7.643 | 23.7635 | 42.8717 | 23.1088 | 9.6929 | 14.8142 | 10.5418 | 18.9844 | 27.2894 | 52.0302 | 24.945 | 2.5759 | 19.0664 | 37.0731 | 5.2493 | 31.8596 | 11.9015 | 21.071 | 21.6687 | 11.3253 | 41.8468 | 13.2457 | 549.8624
820 | 8.0393 | 41.8212 | 15.3662 | 7.6616 | 32.6086 | 45.9624 | 36.9672 | 11.7073 | 17.6471 | 13.8656 | 21.9941 | 16.5237 | 53.8302 | 17.0284 | 3.9187 | 21.3648 | 31.9202 | 5.5695 | 29.0261 | 7.7548 | 21.1403 | 20.3138 | 7.2692 | 45.8324 | 14.4959 | 549.6284
821 | 7.3784 | 43.2287 | 29.4632 | 5.8249 | 38.1362 | 36.4153 | 34.6455 | 6.5566 | 18.7599 | 15.8022 | 17.0314 | 24.4454 | 54.5127 | 25.5455 | 3.238 | 18.096 | 38.1017 | 5.4407 | 22.4901 | 9.5564 | 18.2019 | 14.783 | 8.822 | 58.1655 | 16.419 | 571.0602
822 | 6.7522 | 44.0306 | 28.9421 | 8.6501 | 30.4995 | 39.5189 | 34.8017 | 6.8124 | 19.5424 | 11.3049 | 19.212 | 16.7337 | 54.9823 | 19.0197 | 3.6179 | 18.8725 | 33.4734 | 5.1828 | 26.4668 | 11.6436 | 21.11 | 21.5445 | 10.9278 | 46.8407 | 18.8526 | 559.3352
823 | 5.1212 | 49.6141 | 29.3468 | 6.8914 | 38.834 | 42.843 | 27.4677 | 10.4486 | 16.8792 | 8.8459 | 18.2471 | 22.9778 | 49.0108 | 19.4283 | 3.9872 | 22.6566 | 29.6451 | 3.9732 | 24.4253 | 13.8028 | 22.4776 | 20.4789 | 10.4656 | 59.1763 | 21.9099 | 578.9546
824 | 6.4898 | 33.6853 | 29.4517 | 8.7759 | 38.6445 | 46.9569 | 32.653 | 7.7504 | 17.8519 | 10.4524 | 19.1958 | 15.2919 | 30.8924 | 22.1729 | 3.4598 | 22.9308 | 37.6862 | 5.3967 | 23.9266 | 13.6307 | 25.4417 | 17.2162 | 11.62 | 38.4503 | 21.3251 | 541.3488
825 | 5.9216 | 43.338 | 30.958 | 7.6595 | 31.8643 | 44.9595 | 36.7511 | 9.395 | 17.9003 | 10.2711 | 19.5561 | 25.0886 | 38.3064 | 24.5792 | 3.6539 | 23.9376 | 35.3799 | 4.4477 | 19.4609 | 7.6576 | 23.7586 | 14.9183 | 8.7342 | 53.2521 | 13.7521 | 555.5014
826 | 7.5566 | 45.4909 | 22.1719 | 8.0235 | 37.9745 | 46.973 | 36.0091 | 7.7379 | 12.9153 | 10.1654 | 21.2161 | 22.1325 | 37.7589 | 15.2235 | 2.966 | 19.0223 | 33.7289 | 5.4475 | 18.5648 | 9.8237 | 22.3136 | 19.8654 | 12.2359 | 36.0782 | 18.2884 | 529.6838
827 | 4.8331 | 38.9216 | 32.3782 | 7.1799 | 39.1385 | 45.8049 | 37.6817 | 10.9749 | 19.3134 | 12.4892 | 20.5963 | 22.8883 | 30.1061 | 24.8497 | 3.05 | 19.5521 | 21.1352 | 4.5769 | 25.272 | 11.4609 | 23.7938 | 14.538 | 8.8773 | 43.9373 | 19.7872 | 543.1364
828 | 4.522 | 45.4087 | 26.9826 | 6.6168 | 30.8703 | 47.8388 | 28.8901 | 8.6737 | 18.5082 | 15.845 | 12.2522 | 23.2387 | 40.6354 | 24.6531 | 3.4692 | 19.7022 | 30.1565 | 5.71 | 30.9555 | 10.8837 | 17.8733 | 20.9783 | 11.8118 | 50.4419 | 20.2794 | 557.1973
829 | 7.5002 | 39.1268 | 15.3485 | 6.911 | 34.3536 | 35.0675 | 37.0366 | 10.0167 | 13.9925 | 8.927 | 18.2101 | 22.6037 | 42.3765 | 19.4758 | 3.1005 | 22.6439 | 32.3997 | 5.072 | 27.825 | 12.6778 | 22.0982 | 20.7241 | 10.0879 | 38.6442 | 16.991 | 523.2107
830 | 6.1188 | 37.2207 | 14.8596 | 6.5713 | 35.0948 | 47.7958 | 35.1031 | 6.5686 | 18.3621 | 14.1818 | 21.8612 | 26.9323 | 31.3792 | 23.3169 | 3.5392 | 19.8695 | 36.8426 | 3.7604 | 31.1118 | 8.4048 | 21.5789 | 21.4389 | 10.9757 | 57.8468 | 20.1764 | 560.9112
831 | 7.4186 | 32.3324 | 27.7161 | 5.4329 | 35.3314 | 50.2336 | 28.3824 | 8.8329 | 17.544 | 15.637 | 20.2113 | 25.9999 | 52.4893 | 17.6343 | 3.3961 | 25.6969 | 38.104 | 5.6968 | 26.6219 | 12.3348 | 22.1568 | 19.5216 | 10.3383 | 40.6033 | 21.7421 | 571.4087
832 | 7.8009 | 37.7884 | 17.0443 | 6.4416 | 34.6723 | 49.9886 | 31.2319 | 10.7148 | 11.8729 | 9.9128 | 13.0909 | 24.9601 | 45.985 | 24.3857 | 2.9923 | 24.8448 | 31.6107 | 4.2598 | 25.4013 | 11.6182 | 22.3835 | 17.9978 | 10.896 | 52.2054 | 13.1665 | 543.2664
833 | 5.3377 | 44.0822 | 31.5895 | 6.4791 | 32.3109 | 47.7806 | 30.241 | 9.0241 | 17.261 | 13.7235 | 22.0187 | 19.1866 | 44.5456 | 25.7042 | 3.1552 | 27.5586 | 26.8149 | 4.726 | 28.9968 | 12.3461 | 25.5448 | 19.1071 | 11.6997 | 58.3631 | 18.0555 | 585.6525
834 | 7.3417 | 40.1117 | 30.082 | 6.0357 | 36.7547 | 47.1617 | 27.7506 | 11.1988 | 14.2875 | 15.5009 | 11.2614 | 17.5396 | 52.6986 | 21.291 | 2.444 | 21.6051 | 35.1078 | 4.9674 | 31.0649 | 10.1012 | 23.3248 | 19.8204 | 9.9421 | 46.1643 | 18.0214 | 561.5793
835 | 7.2936 | 46.5132 | 31.166 | 7.1104 | 17.0118 | 35.7413 | 27.7174 | 9.9074 | 19.9592 | 7.6635 | 20.7322 | 23.6731 | 52.7796 | 20.4112 | 3.6201 | 15.0009 | 34.9157 | 5.7305 | 24.4609 | 12.8952 | 24.0567 | 18.6697 | 5.7866 | 49.584 | 16.2273 | 538.6277
836 | 4.3524 | 42.6901 | 29.9131 | 7.9771 | 35.9829 | 36.4535 | 33.9095 | 8.3329 | 19.0127 | 15.734 | 9.87 | 21.1619 | 49.152 | 18.3181 | 3.1907 | 25.7842 | 36.4625 | 4.8945 | 28.3505 | 12.7324 | 22.4833 | 14.9396 | 7.5821 | 57.6302 | 10.4579 | 557.3681
837 | 6.3344 | 19.2162 | 32.358 | 7.6416 | 32.6011 | 52.048 | 35.8381 | 11.4647 | 14.3603 | 15.2506 | 18.3953 | 27.8566 | 47.7074 | 24.7543 | 3.6167 | 20.9366 | 23.1319 | 4.6559 | 29.0793 | 12.0073 | 20.2523 | 19.8028 | 11.8857 | 41.6993 | 17.459 | 550.3533
838 | 7.273 | 28.4158 | 30.8805 | 7.2239 | 33.811 | 33.8736 | 26.8373 | 9.3982 | 19.2464 | 11.912 | 14.4203 | 17.518 | 32.2275 | 25.3796 | 3.5947 | 26.6781 | 24.7223 | 5.1335 | 21.8333 | 9.4042 | 22.7317 | 20.5253 | 11.237 | 32.0937 | 16.4898 | 492.8606
839 | 8.3241 | 31.6534 | 17.2001 | 8.7347 | 16.9791 | 41.6082 | 38.5789 | 10.3101 | 16.07 | 13.2449 | 22.3139 | 26.2641 | 54.1682 | 25.9804 | 3.9694 | 21.5661 | 35.849 | 5.4736 | 27.2332 | 13.1585 | 17.153 | 21.73 | 10.9491 | 47.7635 | 19.8189 | 556.0944
840 | 8.2937 | 41.2256 | 23.9247 | 8.1986 | 30.897 | 50.6379 | 27.4748 | 9.3745 | 18.3615 | 16.0086 | 18.8588 | 21.2698 | 51.5891 | 24.9134 | 2.5492 | 21.6347 | 33.0614 | 4.2134 | 30.3897 | 10.0502 | 25.6251 | 21.8277 | 11.1537 | 54.4788 | 16.7943 | 582.8062
841 | 5.7446 | 37.9899 | 31.9137 | 5.5158 | 31.5385 | 34.2766 | 36.3244 | 10.1032 | 15.2317 | 16.5089 | 14.394 | 28.2646 | 34.0228 | 22.0397 | 3.2301 | 22.2156 | 24.2587 | 5.072 | 20.5497 | 11.78 | 25.6922 | 19.0091 | 9.8005 | 54.619 | 21.4667 | 541.5619
842 | 7.8337 | 41.0539 | 29.928 | 5.8253 | 33.4632 | 47.7172 | 36.2006 | 7.2497 | 14.8217 | 16.515 | 21.8421 | 26.6274 | 27.1505 | 22.5456 | 3.9142 | 17.3709 | 29.6901 | 5.2698 | 26.2834 | 12.7954 | 20.6751 | 15.3432 | 9.3128 | 39.9817 | 21.6243 | 541.035
843 | 6.7579 | 43.4912 | 29.8616 | 7.8287 | 32.6133 | 38.2219 | 35.3424 | 8.94 | 17.4717 | 16.1154 | 17.7437 | 20.2255 | 37.2336 | 19.2399 | 2.6735 | 14.0456 | 35.084 | 4.7812 | 25.2929 | 12.2626 | 19.1221 | 13.4009 | 10.8218 | 49.6863 | 17.7375 | 535.9953
844 | 7.2673 | 32.0349 | 22.3671 | 8.141 | 32.5874 | 42.9702 | 28.8058 | 7.306 | 15.3113 | 15.8933 | 16.0011 | 26.1983 | 47.7201 | 20.5835 | 2.5247 | 18.8926 | 32.6043 | 4.538 | 30.8324 | 11.8615 | 21.7702 | 11.5676 | 12.2189 | 50.1946 | 19.0628 | 539.2547
845 | 7.8336 | 48.6141 | 16.9837 | 6.8567 | 23.7781 | 50.3902 | 31.4116 | 9.115 | 17.6941 | 15.6988 | 17.2181 | 17.8492 | 37.0797 | 19.777 | 3.391 | 18.5562 | 37.2855 | 5.0531 | 23.684 | 12.816 | 18.2091 | 21.7347 | 9.4372 | 46.6933 | 12.1232 | 529.2831
846 | 5.6719 | 40.3144 | 28.8274 | 6.7003 | 18.8667 | 50.139 | 25.7499 | 8.7464 | 14.1082 | 13.8201 | 21.7322 | 19.3776 | 25.5466 | 21.4052 | 3.5822 | 21.7703 | 34.8553 | 3.6752 | 23.1766 | 10.9116 | 25.2714 | 14.2179 | 11.4896 | 38.6734 | 14.0841 | 502.7136
847 | 7.6576 | 29.0323 | 24.4671 | 8.0672 | 34.1607 | 28.556 | 36.8509 | 7.355 | 14.3627 | 16.0372 | 16.9329 | 28.0372 | 26.3371 | 21.4386 | 3.7028 | 19.1139 | 29.5458 | 5.9175 | 27.9393 | 10.4165 | 22.1964 | 14.3655 | 11.1275 | 43.2065 | 21.0054 | 507.8296
848 | 5.1921 | 36.7579 | 28.9464 | 6.4528 | 30.9496 | 52.3241 | 31.3966 | 11.1412 | 15.6562 | 14.5778 | 16.4579 | 15.1122 | 41.0323 | 22.4888 | 3.4266 | 23.4066 | 21.8304 | 4.2027 | 28.0313 | 13.0232 | 17.632 | 13.7215 | 9.5578 | 32.3949 | 11.9376 | 507.6505
849 | 6.877 | 47.8342 | 31.4388 | 5.1737 | 25.8351 | 44.5634 | 31.6695 | 11.3825 | 15.0538 | 15.4064 | 18.5586 | 28.6005 | 33.7599 | 23.7921 | 2.6466 | 18.316 | 38.3519 | 4.4947 | 29.454 | 10.103 | 20.293 | 18.088 | 9.0378 | 48.6555 | 18.5792 | 557.9655
850 | 6.5804 | 39.0173 | 27.6998 | 8.3062 | 38.0417 | 36.3216 | 34.1957 | 9.2784 | 13.8349 | 15.1483 | 21.5428 | 19.192 | 52.6896 | 15.1719 | 3.0544 | 18.8727 | 26.9716 | 5.2698 | 20.0164 | 13.766 | 23.6415 | 17.2985 | 6.4058 | 38.7508 | 20.8072 | 531.8753
851 | 5.4836 | 37.0472 | 17.8418 | 7.9263 | 27.3067 | 41.5703 | 30.3946 | 10.3335 | 12.4921 | 10.786 | 20.1413 | 14.4819 | 33.353 | 18.266 | 2.9264 | 13.4188 | 35.8091 | 3.2545 | 28.3751 | 12.8253 | 24.457 | 18.2589 | 11.8397 | 30.3808 | 21.4711 | 490.4409
852 | 4.6768 | 33.8341 | 18.4745 | 8.5719 | 33.4041 | 48.6631 | 20.4026 | 9.3842 | 17.8662 | 12.0499 | 18.3774 | 23.7828 | 35.3282 | 22.9821 | 3.9388 | 23.9968 | 31.8532 | 5.2476 | 22.8033 | 11.7422 | 20.3717 | 14.3805 | 11.382 | 46.1779 | 21.4019 | 521.0939
853 | 8.171 | 44.8671 | 25.0254 | 8.6235 | 37.2502 | 28.9828 | 30.2515 | 11.9259 | 19.5095 | 8.5065 | 17.4721 | 21.9884 | 51.5574 | 22.8074 | 3.7 | 26.2885 | 22.929 | 4.626 | 23.7098 | 12.5992 | 21.8801 | 18.099 | 10.176 | 56.3791 | 17.8579 | 555.1833
854 | 5.6969 | 41.9883 | 27.4627 | 7.4277 | 33.4094 | 44.2525 | 37.8336 | 9.2108 | 19.9142 | 15.76 | 18.844 | 24.7788 | 48.857 | 17.7305 | 2.7171 | 21.2771 | 25.178 | 5.2947 | 30.1933 | 10.1672 | 21.7732 | 20.259 | 6.4336 | 30.7763 | 19.1761 | 546.4122
855 | 7.6065 | 39.055 | 25.8554 | 7.3477 | 24.9936 | 31.977 | 20.8347 | 11.1443 | 18.0428 | 12.6298 | 20.2607 | 25.8679 | 43.9694 | 22.1508 | 3.6616 | 23.7653 | 34.5289 | 5.1806 | 24.914 | 12.7367 | 22.3587 | 16.973 | 7.5389 | 34.6171 | 20.2118 | 518.2224
856 | 7.6036 | 47.2843 | 30.7069 | 6.3912 | 34.2681 | 48.5148 | 27.9927 | 10.2364 | 15.815 | 15.7163 | 17.468 | 18.3464 | 31.9895 | 25.3627 | 3.7178 | 24.4384 | 29.12 | 3.3727 | 28.2841 | 13.3252 | 11.7763 | 19.6799 | 11.5476 | 40.0058 | 21.0725 | 544.0363
857 | 6.0932 | 41.8954 | 24.0244 | 7.3732 | 38.2183 | 46.5735 | 30.692 | 11.0934 | 14.8719 | 12.1937 | 16.518 | 27.3464 | 42.5359 | 21.9476 | 2.5514 | 26.8274 | 32.6851 | 5.9831 | 24.6982 | 12.7471 | 21.8518 | 20.8097 | 12.0435 | 52.8027 | 16.4716 | 570.8486
858 | 7.4646 | 41.4914 | 29.8635 | 6.6248 | 28.2592 | 29.9371 | 34.7621 | 9.7104 | 16.9967 | 14.5634 | 20.1824 | 25.4758 | 31.1444 | 15.0141 | 3.1391 | 22.5622 | 31.6426 | 5.9071 | 29.5852 | 12.7155 | 22.2216 | 15.8048 | 9.3508 | 43.5956 | 15.2376 | 523.2519
859 | 7.8051 | 41.3188 | 30.6088 | 6.6685 | 25.7789 | 51.8392 | 39.1393 | 9.9379 | 18.2658 | 11.3675 | 20.8728 | 20.5294 | 42.7259 | 21.553 | 3.2322 | 19.6995 | 35.4281 | 5.7701 | 31.1246 | 12.1119 | 22.7167 | 17.6386 | 7.2328 | 29.2847 | 19.2964 | 551.9464
860 | 6.7468 | 47.2129 | 27.4847 | 5.6589 | 36.5506 | 25.1747 | 33.628 | 10.6631 | 14.3313 | 16.4273 | 20.6173 | 24.4837 | 36.1376 | 19.3673 | 3.2354 | 25.0313 | 17.4377 | 4.3055 | 22.2932 | 12.5827 | 18.671 | 17.2615 | 6.2801 | 38.291 | 14.7417 | 504.6155
861 | 7.0047 | 41.575 | 26.4978 | 4.4338 | 36.4818 | 48.0133 | 29.4928 | 9.9862 | 16.5101 | 16.3638 | 22.368 | 23.6251 | 34.842 | 19.8016 | 3.5834 | 25.1626 | 26.0085 | 5.2146 | 26.882 | 11.4382 | 23.8359 | 17.0232 | 12.1068 | 45.4316 | 15.6642 | 549.347
862 | 7.4852 | 34.5232 | 24.8116 | 7.4725 | 35.8269 | 38.8359 | 25.6039 | 9.1157 | 10.7029 | 14.78 | 16.9872 | 21.6255 | 46.91 | 19.6043 | 3.4483 | 15.7871 | 21.5723 | 5.5567 | 31.2496 | 13.247 | 25.2468 | 15.1287 | 10.5972 | 59.828 | 20.2447 | 536.1914
863 | 6.1398 | 45.6704 | 24.4967 | 6.9385 | 33.8188 | 46.292 | 28.2204 | 11.0601 | 15.0875 | 15.2316 | 17.7834 | 18.6883 | 32.3967 | 22.6365 | 3.6307 | 16.8692 | 32.4618 | 4.2405 | 21.9234 | 13.711 | 23.3097 | 14.9485 | 10.5304 | 32.9546 | 20.2548 | 519.2958
864 | 7.6758 | 45.2506 | 25.4798 | 6.6645 | 34.689 | 43.7066 | 21.5847 | 10.8128 | 12.7877 | 14.437 | 18.0634 | 25.6332 | 46.2427 | 13.3899 | 3.3035 | 27.6576 | 32.0226 | 5.8701 | 31.6877 | 12.0068 | 23.4048 | 14.5235 | 12.4767 | 35.6065 | 20.1703 | 545.1478
865 | 5.6365 | 39.5312 | 21.4677 | 6.7725 | 33.5599 | 45.7932 | 35.6545 | 4.5946 | 13.6637 | 10.7855 | 13.5032 | 19.101 | 37.9907 | 14.3036 | 3.9926 | 23.9784 | 38.6587 | 5.0831 | 25.4749 | 13.3218 | 20.139 | 14.404 | 10.3972 | 43.0793 | 14.3006 | 515.1874
866 | 7.795 | 31.5539 | 27.0756 | 7.0803 | 31.7092 | 31.8697 | 36.8042 | 9.2849 | 18.6337 | 13.1945 | 13.4589 | 19.4634 | 53.8244 | 22.1606 | 3.8176 | 21.179 | 32.2054 | 5.3325 | 28.4416 | 8.6457 | 18.6373 | 12.4223 | 10.3245 | 43.1982 | 17.6966 | 525.8091
867 | 7.2198 | 41.1977 | 29.2831 | 6.908 | 31.7974 | 40.934 | 26.653 | 7.9614 | 14.103 | 12.8337 | 20.9454 | 22.5548 | 50.5852 | 20.1128 | 3.1666 | 23.3764 | 30.6371 | 5.5367 | 23.8175 | 12.1354 | 20.9646 | 19.1788 | 12.1423 | 50.154 | 14.5726 | 548.7711
868 | 4.2566 | 40.8144 | 25.8461 | 6.9794 | 29.2181 | 42.7948 | 36.2526 | 8.9875 | 18.9719 | 10.839 | 16.9895 | 22.5553 | 43.5932 | 24.9735 | 3.9657 | 25.9332 | 31.319 | 5.4088 | 30.2678 | 13.8104 | 23.2835 | 19.465 | 6.2891 | 36.833 | 17.4202 | 547.0674
869 | 6.475 | 34.1028 | 17.8556 | 6.243 | 34.484 | 53.5308 | 33.4256 | 11.0273 | 19.0725 | 14.4032 | 17.3241 | 20.495 | 38.082 | 20.9875 | 3.1627 | 25.6622 | 38.4427 | 3.9889 | 28.4311 | 11.6461 | 18.2074 | 17.7711 | 12.1139 | 51.499 | 18.1675 | 556.601
870 | 7.9017 | 44.2871 | 33.0871 | 7.6931 | 38.4578 | 37.8757 | 33.2999 | 10.1271 | 18.4043 | 13.7117 | 16.207 | 20.8763 | 22.8773 | 24.9716 | 2.8826 | 18.2201 | 34.2169 | 5.0101 | 22.8646 | 13.559 | 16.6119 | 20.0329 | 7.4876 | 44.4624 | 20.0713 | 535.1972
871 | 6.2873 | 35.5843 | 31.3496 | 6.2564 | 34.2418 | 50.5479 | 19.7682 | 10.3199 | 15.9836 | 13.9823 | 22.4468 | 27.0656 | 32.1376 | 25.6181 | 2.2526 | 18.4678 | 29.2187 | 5.8825 | 23.5881 | 13.8892 | 24.1387 | 20.8379 | 5.9607 | 43.7048 | 17.9534 | 537.4837
872 | 3.5425 | 39.9574 | 25.1804 | 7.8646 | 28.7814 | 36.0461 | 35.7694 | 10.2095 | 16.4842 | 11.9435 | 15.8784 | 19.5393 | 52.8154 | 24.3262 | 3.7861 | 25.4765 | 31.0721 | 5.8935 | 32.2635 | 12.7414 | 25.0216 | 21.9295 | 12.0223 | 55.0723 | 20.2579 | 573.875
873 | 5.386 | 43.4104 | 24.037 | 6.5041 | 34.392 | 41.5859 | 27.4178 | 7.8987 | 14.7811 | 12.7582 | 20.2434 | 22.8632 | 26.9068 | 19.8951 | 2.6201 | 23.5112 | 17.1274 | 5.2976 | 31.2571 | 12.9955 | 20.6496 | 21.3333 | 8.6426 | 38.7397 | 15.8239 | 506.0775
874 | 7.9602 | 42.6894 | 20.1028 | 5.5309 | 33.6283 | 38.5336 | 38.2856 | 6.6421 | 16.1056 | 6.7406 | 18.9986 | 21.9567 | 35.0063 | 18.8475 | 2.6963 | 17.5323 | 22.8942 | 3.9166 | 31.0573 | 12.8074 | 16.2053 | 16.7594 | 11.3982 | 58.8632 | 17.4291 | 522.5875
875 | 7.154 | 29.1598 | 21.2387 | 6.2018 | 30.9418 | 50.5326 | 20.8352 | 11.4578 | 17.959 | 16.7056 | 18.5808 | 19.7145 | 43.296 | 24.3741 | 2.3892 | 23.0349 | 37.8054 | 4.85 | 28.9262 | 10.8237 | 16.464 | 14.79 | 11.8662 | 39.8339 | 19.3361 | 528.2711
876 | 7.3519 | 41.0944 | 20.9822 | 6.9971 | 37.5829 | 48.1038 | 23.8568 | 7.8103 | 13.5132 | 12.4873 | 20.5262 | 12.99 | 55.2269 | 17.3007 | 3.3885 | 25.2829 | 38.6091 | 5.2101 | 28.2888 | 12.2655 | 19.0356 | 19.4499 | 12.3848 | 29.8718 | 21.3526 | 540.9634
877 | 7.5007 | 31.9794 | 28.4362 | 8.5222 | 34.2033 | 42.3779 | 36.2526 | 5.1613 | 12.6754 | 9.8879 | 20.9109 | 26.4638 | 39.7731 | 25.7488 | 3.0093 | 27.3362 | 34.7934 | 4.8852 | 23.4138 | 11.622 | 22.7047 | 21.653 | 11.021 | 52.5304 | 8.5131 | 551.3754
878 | 7.7602 | 44.9974 | 25.668 | 8.3717 | 32.3181 | 49.3466 | 29.6687 | 4.6861 | 16.3396 | 13.2497 | 18.9596 | 27.1597 | 47.7506 | 17.3871 | 2.7967 | 23.9701 | 32.7661 | 5.2225 | 21.2111 | 13.5061 | 16.4798 | 16.2519 | 11.94 | 59.4451 | 21.1385 | 568.3908
879 | 6.8969 | 28.6687 | 24.6 | 8.2671 | 26.5232 | 49.2066 | 24.579 | 9.7375 | 14.7403 | 14.8695 | 16.4802 | 23.1347 | 35.5898 | 19.776 | 3.7795 | 17.0602 | 27.1308 | 4.9207 | 32.6875 | 11.6224 | 25.7032 | 20.0826 | 9.7359 | 52.1475 | 18.0572 | 525.997
880 | 5.6394 | 36.8811 | 28.0252 | 6.4759 | 31.4737 | 50.3713 | 30.9809 | 10.2067 | 19.4293 | 14.7344 | 18.0235 | 16.7179 | 34.6834 | 23.9551 | 3.7914 | 26.2754 | 21.2521 | 4.5729 | 32.4274 | 13.0916 | 23.2691 | 17.553 | 9.9446 | 48.4218 | 17.9521 | 546.1491
881 | 7.9059 | 29.3715 | 23.3919 | 7.9031 | 30.5751 | 47.2371 | 30.6602 | 11.892 | 15.3747 | 14.3433 | 19.6742 | 18.3113 | 53.248 | 24.1392 | 3.44 | 17.1962 | 27.359 | 3.2251 | 18.7195 | 13.0124 | 19.1919 | 16.1998 | 7.6297 | 28.0175 | 20.8164 | 508.8349
882 | 5.735 | 32.7265 | 18.5604 | 5.4118 | 24.1394 | 46.0292 | 39.0515 | 11.1857 | 12.8989 | 14.1257 | 20.7619 | 27.2112 | 48.5619 | 18.1495 | 3.7975 | 22.5884 | 33.759 | 5.3038 | 25.914 | 13.6238 | 18.5369 | 16.5309 | 10.2509 | 42.2435 | 21.258 | 538.3555
883 | 6.4946 | 45.2056 | 33.1595 | 8.3155 | 38.9121 | 47.1265 | 20.9092 | 9.7896 | 19.1308 | 15.7065 | 17.0325 | 17.5241 | 22.2781 | 19.1436 | 2.8731 | 16.8978 | 32.0877 | 4.1564 | 31.2473 | 13.2592 | 24.1478 | 18.9401 | 9.9266 | 46.5092 | 16.7616 | 537.535
884 | 5.3357 | 36.3555 | 30.5096 | 7.2265 | 30.7834 | 43.8701 | 26.535 | 7.0878 | 11.6833 | 10.5517 | 16.0032 | 25.2474 | 49.9714 | 21.0473 | 3.8013 | 25.6336 | 28.6228 | 5.813 | 26.7498 | 11.1353 | 14.5604 | 18.1606 | 9.1207 | 47.2906 | 19.8452 | 532.9411
885 | 6.6302 | 35.1652 | 23.7643 | 7.6072 | 35.5845 | 48.4404 | 27.6955 | 9.2862 | 19.3735 | 10.8554 | 18.4557 | 15.3166 | 30.8895 | 23.1259 | 3.4866 | 22.7452 | 26.9801 | 5.2393 | 31.3989 | 13.9149 | 23.3489 | 21.3595 | 11.0671 | 44.1846 | 21.307 | 537.2222
886 | 7.3569 | 45.4684 | 17.5553 | 8.2393 | 27.067 | 38.7406 | 29.3069 | 7.4129 | 17.8893 | 15.4962 | 15.7782 | 20.3853 | 39.1307 | 20.0822 | 2.4513 | 21.7256 | 26.5684 | 5.9033 | 31.0428 | 12.4785 | 18.5925 | 18.4396 | 9.4758 | 32.588 | 20.8298 | 510.005
887 | 6.3976 | 27.5697 | 21.2023 | 5.5678 | 22.8745 | 38.0991 | 28.117 | 9.6689 | 16.0188 | 12.5093 | 17.488 | 28.0333 | 52.5696 | 19.6167 | 2.9951 | 23.1274 | 22.9371 | 5.0866 | 32.2245 | 9.4088 | 15.3133 | 19.8333 | 7.5982 | 39.3055 | 17.0291 | 500.5917
888 | 7.0555 | 40.3985 | 29.3141 | 8.6755 | 37.9341 | 24.6864 | 29.7146 | 8.5177 | 17.3444 | 9.9977 | 17.7444 | 21.2283 | 40.8266 | 23.3791 | 2.4559 | 23.7655 | 31.0945 | 4.749 | 29.5496 | 11.1086 | 23.1945 | 21.7319 | 9.4301 | 56.1443 | 17.5661 | 547.6067
889 | 7.357 | 40.3878 | 15.003 | 8.0526 | 34.2075 | 35.2406 | 33.3135 | 9.8386 | 17.9228 | 16.4782 | 14.8942 | 16.7635 | 38.3032 | 23.7147 | 3.8057 | 21.2316 | 34.4918 | 5.803 | 31.7206 | 9.6726 | 20.6215 | 14.4014 | 12.2201 | 48.7728 | 21.2642 | 535.4826
890 | 5.3629 | 39.3371 | 19.1871 | 6.38 | 35.0461 | 48.3806 | 30.5917 | 10.0673 | 17.8843 | 12.8393 | 17.4148 | 27.5688 | 47.4995 | 23.4244 | 2.8857 | 23.0476 | 32.4873 | 5.0854 | 20.5816 | 13.7665 | 13.561 | 19.7662 | 9.6863 | 56.3696 | 18.7046 | 556.9257
891 | 7.0688 | 36.3821 | 27.3138 | 7.79 | 24.9128 | 50.7682 | 27.1883 | 9.1834 | 16.1513 | 10.1334 | 15.6155 | 18.6041 | 52.7075 | 25.352 | 3.8005 | 19.9171 | 37.727 | 3.6419 | 31.1985 | 12.7458 | 20.3343 | 18.5445 | 9.6949 | 57.9078 | 19.8957 | 564.5793
892 | 7.9046 | 33.4785 | 19.8999 | 8.2131 | 29.3646 | 41.1719 | 31.2859 | 9.2785 | 12.6979 | 8.3452 | 15.0291 | 26.7435 | 45.9025 | 17.0909 | 3.5507 | 22.875 | 24.8937 | 5.5763 | 27.9324 | 12.4547 | 23.6218 | 19.9738 | 8.553 | 31.4275 | 15.363 | 502.628
893 | 8.1981 | 36.2042 | 24.9642 | 7.0968 | 29.5484 | 36.4942 | 34.8158 | 9.5336 | 19.7733 | 16.1796 | 16.9254 | 21.3472 | 42.3453 | 17.2626 | 2.8908 | 25.4984 | 30.6177 | 4.9668 | 29.6678 | 9.789 | 21.4659 | 20.6763 | 10.4683 | 42.7154 | 15.6487 | 535.0938
894 | 8.3027 | 42.4972 | 28.2406 | 6.6355 | 34.1585 | 43.1574 | 33.6418 | 8.6529 | 18.8404 | 14.7023 | 18.1815 | 16.6167 | 55.3714 | 21.3341 | 3.9061 | 23.5816 | 27.6703 | 5.207 | 20.746 | 12.1714 | 18.9511 | 19.1639 | 8.8766 | 43.951 | 18.3244 | 552.8824
895 | 5.617 | 32.1591 | 29.0443 | 8.1038 | 29.0957 | 30.4668 | 38.4363 | 10.8626 | 12.6011 | 15.5189 | 19.6997 | 26.5051 | 37.2069 | 23.9237 | 3.687 | 22.7656 | 32.0791 | 4.5684 | 31.9072 | 13.0185 | 20.8606 | 19.855 | 9.4349 | 47.5197 | 19.4463 | 544.3833
896 | 7.6614 | 23.2739 | 31.2043 | 8.1388 | 34.4019 | 50.4008 | 30.8012 | 9.1636 | 19.6154 | 12.9907 | 21.3969 | 26.8392 | 46.2583 | 19.1567 | 3.5332 | 26.6761 | 32.0115 | 4.9767 | 19.4837 | 7.3997 | 19.6433 | 21.8945 | 9.9804 | 47.6891 | 14.5348 | 549.1261
897 | 5.5045 | 46.6602 | 31.5929 | 6.8743 | 31.8421 | 50.0195 | 36.9995 | 6.2659 | 17.5601 | 13.8624 | 21.1594 | 24.2113 | 53.344 | 24.7079 | 3.8795 | 19.7767 | 20.3325 | 5.483 | 28.9509 | 12.3999 | 17.8083 | 20.3761 | 10.6074 | 57.9109 | 22.2533 | 590.3826
898 | 7.2502 | 35.1998 | 26.1301 | 7.6959 | 36.0368 | 48.2973 | 35.9295 | 6.4718 | 12.21 | 11.6874 | 15.9633 | 27.7593 | 46.9639 | 25.1606 | 3.7942 | 23.8008 | 32.6829 | 4.3647 | 26.9327 | 7.8293 | 22.7634 | 18.8009 | 8.3499 | 52.3488 | 11.3158 | 555.7395
899 | 4.6038 | 41.4984 | 33.3511 | 8.1185 | 26.2029 | 34.0483 | 30.6927 | 9.3135 | 19.1724 | 13.7547 | 20.6692 | 22.225 | 45.1411 | 24.5604 | 3.2059 | 13.8144 | 32.2466 | 5.2799 | 32.4338 | 10.575 | 19.2846 | 21.6612 | 11.1524 | 48.2095 | 19.7293 | 550.9447
900 | 6.9215 | 32.2026 | 31.8577 | 6.6823 | 31.8838 | 51.1976 | 29.1557 | 10.6923 | 18.6855 | 14.9409 | 22.4357 | 18.7518 | 53.4137 | 16.6504 | 3.7114 | 21.8361 | 36.2418 | 3.6422 | 19.6654 | 9.3337 | 16.7931 | 18.4231 | 11.0616 | 39.1488 | 18.4482 | 543.777
901 | 7.7505 | 42.7279 | 33.5019 | 7.9918 | 28.9749 | 43.2878 | 35.2093 | 6.9003 | 14.8813 | 15.3629 | 20.7245 | 16.3041 | 41.5157 | 23.5309 | 3.7666 | 16.5104 | 26.2855 | 5.5377 | 32.2759 | 12.0619 | 19.4163 | 15.4882 | 10.8192 | 58.0861 | 17.7125 | 556.6242
902 | 6.8377 | 30.3504 | 28.6488 | 8.5487 | 37.6193 | 34.4829 | 26.4867 | 9.2788 | 16.4117 | 14.2566 | 16.4985 | 23.425 | 41.1523 | 23.7376 | 3.2219 | 20.2316 | 27.5596 | 5.4895 | 27.7284 | 12.3652 | 19.3954 | 17.6035 | 8.1859 | 39.6282 | 19.2251 | 518.3696
903 | 6.7284 | 22.9321 | 28.3388 | 6.7407 | 34.4397 | 46.9526 | 32.9132 | 9.381 | 12.8931 | 16.4125 | 20.077 | 25.1495 | 51.8394 | 24.1188 | 2.3242 | 20.3914 | 24.3281 | 4.0376 | 22.2906 | 11.9356 | 25.8937 | 18.2074 | 12.1917 | 49.0173 | 16.6513 | 546.1856
904 | 6.2874 | 34.5148 | 31.0453 | 6.1539 | 32.9978 | 48.1222 | 38.0264 | 8.1678 | 15.6297 | 16.5049 | 21.0173 | 13.0158 | 44.7118 | 24.1623 | 3.5702 | 12.427 | 32.3298 | 5.4298 | 20.7562 | 9.9498 | 22.5624 | 21.3525 | 11.3232 | 49.2521 | 19.0981 | 548.4083
905 | 7.6933 | 34.5366 | 30.7063 | 4.5466 | 35.9905 | 46.9137 | 34.2346 | 11.6886 | 15.4231 | 11.6412 | 18.0558 | 13.3208 | 40.4986 | 18.2789 | 3.5862 | 20.4185 | 22.4616 | 5.7303 | 31.8777 | 10.6266 | 16.0588 | 17.7897 | 10.6865 | 51.2071 | 12.1562 | 526.1278
906 | 7.0894 | 41.8645 | 26.4425 | 6.8303 | 30.5745 | 43.9609 | 32.7206 | 8.2553 | 13.6025 | 10.0468 | 16.1075 | 18.7881 | 33.0983 | 21.8782 | 3.6692 | 20.387 | 28.9499 | 3.9617 | 32.0448 | 10.2239 | 11.882 | 19.7026 | 6.4204 | 48.9902 | 16.765 | 514.2563
907 | 6.8952 | 34.5921 | 26.3304 | 7.4375 | 37.1666 | 45.7226 | 33.2262 | 10.6256 | 18.7354 | 8.9732 | 15.8453 | 27.3733 | 35.896 | 25.8132 | 3.6048 | 18.5945 | 22.5727 | 4.3606 | 23.6136 | 13.2825 | 25.2027 | 18.6512 | 8.0565 | 49.571 | 19.8472 | 541.9899
908 | 6.6121 | 36.8892 | 28.3096 | 6.8135 | 28.0895 | 42.51 | 25.8303 | 10.1298 | 18.2206 | 16.3015 | 10.3948 | 18.8497 | 44.4011 | 25.1315 | 3.047 | 27.3607 | 20.4649 | 5.1268 | 26.8347 | 11.9168 | 25.0129 | 14.9574 | 9.5382 | 48.0827 | 13.9703 | 524.7956
909 | 6.7414 | 39.3646 | 28.0166 | 8.575 | 37.2611 | 49.1652 | 36.0807 | 10.7937 | 17.205 | 11.9425 | 17.3189 | 23.8041 | 54.1402 | 22.0746 | 2.9928 | 23.6748 | 26.9556 | 5.2878 | 28.3476 | 12.4333 | 19.8971 | 17.2833 | 8.5333 | 48.2623 | 19.7533 | 575.9048
910 | 5.6502 | 43.9751 | 30.5397 | 5.7393 | 28.5494 | 49.1986 | 23.5186 | 8.6556 | 17.9965 | 10.1972 | 21.2333 | 14.071 | 51.6079 | 21.6737 | 2.8562 | 23.1437 | 33.5067 | 4.6213 | 30.4337 | 12.7062 | 21.0002 | 20.3844 | 9.8084 | 50.8989 | 14.4118 | 556.3776
911 | 7.8111 | 37.9398 | 28.2111 | 7.366 | 32.6233 | 26.3156 | 28.4637 | 10.5628 | 15.2709 | 16.4173 | 13.9716 | 11.9702 | 49.9949 | 23.4958 | 3.6856 | 24.7243 | 23.5263 | 5.8137 | 22.6665 | 8.1699 | 19.373 | 20.8291 | 7.3988 | 44.1293 | 22.0231 | 512.7538
912 | 4.6219 | 42.3103 | 30.6459 | 7.6863 | 38.2737 | 50.6564 | 28.5586 | 10.6897 | 17.7468 | 11.8638 | 18.5757 | 23.7338 | 36.1721 | 19.8033 | 3.6613 | 23.2841 | 32.7398 | 5.8861 | 30.4759 | 11.9027 | 14.4728 | 16.9676 | 8.9962 | 55.0619 | 11.9804 | 556.7673
913 | 5.2443 | 44.6316 | 28.1321 | 7.1665 | 24.6032 | 43.5868 | 29.7095 | 8.5018 | 17.4733 | 16.7434 | 15.5941 | 23.6428 | 51.6614 | 25.5564 | 2.9167 | 20.6386 | 23.4905 | 4.3451 | 24.6713 | 11.7975 | 24.2892 | 19.5519 | 10.8651 | 51.3114 | 17.9222 | 554.0466
914 | 5.4974 | 39.1037 | 30.8857 | 7.4836 | 27.2667 | 39.817 | 28.667 | 9.3188 | 13.761 | 15.2038 | 14.9209 | 18.9659 | 51.2613 | 22.1796 | 2.9499 | 22.8832 | 34.0101 | 5.4888 | 31.3319 | 12.672 | 14.7626 | 19.5371 | 11.1882 | 37.3243 | 19.1085 | 535.5891
915 | 8.2105 | 44.0027 | 32.7504 | 4.9901 | 25.671 | 38.7675 | 28.2514 | 11.4286 | 15.9664 | 8.3204 | 22.2993 | 24.4386 | 36.1858 | 24.2776 | 3.5451 | 25.8171 | 22.9513 | 5.8937 | 31.4852 | 13.0912 | 19.0705 | 20.7401 | 10.9932 | 52.999 | 20.4145 | 552.5615
916 | 7.2369 | 48.163 | 21.8678 | 7.2929 | 34.4381 | 50.5542 | 19.5277 | 8.0368 | 18.062 | 15.671 | 21.3322 | 17.8223 | 34.8709 | 22.3992 | 3.023 | 22.2266 | 34.8436 | 4.7266 | 29.8375 | 9.8535 | 19.0781 | 21.8911 | 10.4986 | 39.1589 | 20.0504 | 542.463
917 | 7.8475 | 42.9321 | 19.6895 | 7.2891 | 33.8374 | 33.4253 | 38.2424 | 8.2215 | 16.3634 | 12.7945 | 15.6837 | 26.1292 | 43.4421 | 25.8367 | 3.2666 | 24.9249 | 23.9298 | 5.6145 | 24.765 | 13.5622 | 20.6007 | 18.1036 | 7.8928 | 51.348 | 16.4376 | 542.18
918 | 6.175 | 49.0184 | 26.318 | 6.3576 | 37.299 | 37.3061 | 34.614 | 10.3801 | 19.7969 | 10.0685 | 18.5427 | 19.2053 | 37.9619 | 18.6769 | 3.914 | 27.3282 | 27.6845 | 5.6254 | 30.6271 | 13.9981 | 23.5737 | 21.9902 | 12.2672 | 34.9562 | 15.6578 | 549.3426
919 | 5.9487 | 38.8161 | 31.3233 | 7.1135 | 29.7867 | 38.5048 | 32.2202 | 9.138 | 19.5078 | 13.1995 | 19.2349 | 25.4279 | 42.1123 | 18.459 | 2.8644 | 21.0408 | 27.4058 | 5.9581 | 32.3244 | 13.9332 | 23.6689 | 20.8454 | 11.9155 | 49.1305 | 21.8138 | 561.6931
920 | 4.8202 | 45.0662 | 25.883 | 6.3828 | 34.9183 | 37.9543 | 38.9104 | 9.7783 | 18.0752 | 7.6178 | 21.6376 | 24.7279 | 40.0963 | 15.3586 | 3.0042 | 25.6467 | 36.0717 | 5.3611 | 31.5293 | 11.0358 | 19.5581 | 17.68 | 11.1109 | 50.2728 | 17.3318 | 559.8293
921 | 6.598 | 37.6893 | 26.6252 | 7.8475 | 27.9764 | 34.7216 | 28.6204 | 8.8318 | 19.8161 | 12.7788 | 16.4111 | 27.1701 | 35.1961 | 21.1177 | 3.0215 | 22.187 | 31.9716 | 5.7434 | 25.7361 | 12.3572 | 22.7664 | 18.8112 | 11.942 | 57.4181 | 19.3666 | 542.721
922 | 7.9039 | 35.3937 | 29.8875 | 6.921 | 20.4375 | 49.7802 | 35.6016 | 7.6809 | 13.8829 | 15.6908 | 14.4624 | 26.4808 | 33.3854 | 16.8165 | 3.7816 | 27.612 | 36.0084 | 5.9994 | 26.3839 | 9.1442 | 24.6379 | 17.5624 | 11.6541 | 57.2024 | 21.7188 | 556.0304
923 | 7.3466 | 41.3269 | 19.2417 | 8.3724 | 30.3303 | 40.861 | 27.1849 | 6.7827 | 15.0619 | 15.1675 | 17.1998 | 20.8867 | 49.5398 | 25.9186 | 3.9328 | 18.4943 | 23.8953 | 5.3155 | 24.434 | 10.8136 | 24.3113 | 20.608 | 9.7681 | 45.3216 | 21.3452 | 533.4606
924 | 5.8892 | 43.3574 | 29.1323 | 5.8916 | 25.1067 | 51.9097 | 37.309 | 9.9 | 17.4452 | 15.0719 | 16.2272 | 27.2595 | 36.6834 | 23.3577 | 3.1092 | 18.8379 | 31.9829 | 4.084 | 24.0654 | 11.9552 | 18.3608 | 15.8091 | 11.1324 | 54.8295 | 20.1518 | 558.8589
925 | 6.7178 | 38.1382 | 26.5493 | 5.8657 | 32.2198 | 40.1211 | 34.5446 | 9.6337 | 19.6338 | 11.7285 | 21.376 | 27.9302 | 49.9945 | 19.0977 | 3.9073 | 25.7507 | 37.3638 | 4.6014 | 31.8032 | 10.5551 | 17.928 | 20.1804 | 6.9288 | 34.2039 | 21.7885 | 558.5619
926 | 7.9874 | 41.588 | 25.8593 | 6.7603 | 29.2466 | 47.237 | 34.4275 | 8.2122 | 13.2395 | 14.6312 | 20.1054 | 26.6538 | 54.9127 | 18.8778 | 3.7253 | 24.3785 | 27.0483 | 5.5323 | 22.7347 | 11.1223 | 21.9082 | 19.8219 | 8.3812 | 40.8707 | 16.755 | 552.0171
927 | 5.582 | 48.8328 | 22.9347 | 7.5404 | 35.8687 | 47.0862 | 29.8501 | 8.8205 | 18.8341 | 14.9584 | 16.79 | 25.405 | 50.3484 | 24.3806 | 2.4592 | 25.5327 | 31.4913 | 4.4595 | 32.0954 | 13.7546 | 21.3975 | 15.8085 | 11.1137 | 48.2383 | 15.9061 | 579.4886
928 | 7.1051 | 31.7755 | 15.1168 | 8.119 | 38.7283 | 40.0182 | 24.6748 | 11.602 | 12.5668 | 11.4564 | 15.8865 | 26.4636 | 44.1707 | 25.2592 | 3.7613 | 17.611 | 32.4969 | 5.4051 | 30.8528 | 13.9697 | 17.8985 | 18.7458 | 10.2789 | 32.2935 | 17.4292 | 513.6857
929 | 7.951 | 32.0736 | 31.5943 | 7.68 | 37.1858 | 49.7901 | 31.5757 | 10.4311 | 18.0553 | 13.2959 | 20.385 | 20.0289 | 39.8373 | 25.9611 | 2.9183 | 23.4296 | 34.196 | 4.3008 | 27.9057 | 12.8046 | 24.2331 | 21.0785 | 7.7802 | 48.1229 | 14.7311 | 567.3459
930 | 6.1496 | 41.2337 | 32.4291 | 7.1619 | 35.455 | 42.6468 | 34.9667 | 9.3843 | 15.0936 | 8.7023 | 14.9935 | 23.0141 | 34.8349 | 25.9928 | 3.706 | 24.9291 | 34.9691 | 3.4386 | 29.2229 | 9.5675 | 24.4124 | 20.9538 | 10.58 | 29.293 | 14.9573 | 538.0879
931 | 7.7996 | 30.0542 | 31.2101 | 8.7984 | 34.7291 | 36.5328 | 32.759 | 11.6043 | 17.5265 | 16.172 | 12.7717 | 18.4483 | 50.6547 | 25.5474 | 3.1685 | 24.85 | 25.9289 | 4.3885 | 28.3086 | 11.2153 | 18.9607 | 12.1399 | 10.4841 | 57.1624 | 17.5556 | 548.7705
932 | 6.1528 | 46.8553 | 22.8455 | 6.9049 | 32.7727 | 39.2422 | 24.5047 | 9.5913 | 15.4619 | 15.9823 | 10.3179 | 28.2971 | 46.6444 | 22.0601 | 2.7064 | 22.9782 | 32.4295 | 5.513 | 26.5116 | 10.1554 | 22.5632 | 16.074 | 11.8966 | 49.2522 | 15.7607 | 543.4739
933 | 5.7715 | 42.7897 | 19.6256 | 8.4852 | 34.1602 | 45.006 | 34.3896 | 7.0301 | 16.1846 | 15.8149 | 21.8808 | 23.9163 | 51.9128 | 18.1965 | 3.8592 | 21.8254 | 26.5214 | 5.7599 | 29.8389 | 11.3954 | 24.6485 | 20.5805 | 11.6038 | 41.1995 | 14.2297 | 556.6256
934 | 8.2244 | 27.6364 | 21.263 | 8.0785 | 36.3931 | 33.7291 | 36.1728 | 9.0416 | 13.651 | 11.7037 | 20.1892 | 19.5385 | 48.5687 | 24.5372 | 3.5522 | 22.0541 | 22.4233 | 5.3758 | 29.1707 | 13.5746 | 18.0864 | 17.6467 | 7.1898 | 47.7498 | 19.6501 | 525.2007
935 | 5.1707 | 46.909 | 17.4888 | 8.5764 | 35.9855 | 48.3223 | 31.9661 | 9.653 | 18.7666 | 13.3515 | 17.667 | 24.1879 | 55.0362 | 15.6321 | 3.5937 | 22.166 | 34.7656 | 5.3253 | 24.6476 | 13.6891 | 21.8457 | 16.5382 | 8.7557 | 43.4996 | 17.9689 | 561.5086
936 | 4.065 | 26.6836 | 23.2056 | 6.7686 | 31.5114 | 49.3853 | 33.2889 | 10.383 | 17.9922 | 16.4561 | 21.146 | 27.6843 | 51.3694 | 25.8324 | 3.36 | 26.6209 | 31.2939 | 4.3142 | 30.816 | 11.0168 | 12.1422 | 21.9973 | 10.5519 | 48.6547 | 14.7316 | 561.2713
937 | 5.3689 | 42.5469 | 31.8064 | 5.9968 | 37.5935 | 38.8467 | 28.154 | 8.5018 | 17.9421 | 11.3976 | 20.2698 | 17.1913 | 44.7823 | 25.952 | 3.3302 | 21.4773 | 36.3863 | 4.5903 | 26.1812 | 12.5573 | 17.8256 | 16.4999 | 10.5538 | 32.0075 | 18.7665 | 536.526
938 | 5.3023 | 37.5235 | 14.9418 | 5.8006 | 34.1437 | 46.1421 | 35.8359 | 8.92 | 19.9476 | 16.3135 | 19.5525 | 27.343 | 29.2832 | 21.1846 | 3.9001 | 20.6406 | 34.3585 | 5.8173 | 29.6604 | 11.6192 | 20.6812 | 21.9081 | 10.0231 | 54.8209 | 15.5847 | 551.2485
939 | 7.8068 | 47.0582 | 22.1723 | 8.5226 | 30.8961 | 38.1211 | 17.9948 | 10.8325 | 17.0613 | 13.2421 | 17.3199 | 22.1324 | 25.5009 | 24.6188 | 3.9814 | 14.7404 | 27.2222 | 5.7832 | 30.5445 | 11.4316 | 26.103 | 21.7712 | 10.0305 | 48.3602 | 17.7927 | 521.0406
940 | 7.8294 | 34.7743 | 27.9816 | 8.5874 | 19.8521 | 48.8782 | 26.1319 | 9.7346 | 18.0487 | 15.4298 | 20.676 | 27.6672 | 44.9015 | 19.7631 | 2.5837 | 15.9177 | 35.1725 | 3.9429 | 24.2145 | 11.5396 | 26.6457 | 20.1407 | 10.5223 | 41.5866 | 14.0742 | 536.5962
941 | 5.5879 | 46.6066 | 30.7956 | 5.3556 | 35.2729 | 51.8546 | 29.8789 | 10.3583 | 16.3888 | 13.9658 | 20.3195 | 23.3704 | 44.5967 | 22.7042 | 3.909 | 27.0335 | 26.2663 | 5.5495 | 30.3341 | 13.971 | 20.2392 | 19.7285 | 12.4602 | 37.175 | 20.0414 | 573.7634
942 | 7.9226 | 40.9379 | 26.4321 | 4.9365 | 26.8116 | 48.2477 | 31.8457 | 10.0266 | 18.7653 | 16.1467 | 21.9944 | 24.6118 | 49.8041 | 17.5635 | 3.9738 | 15.364 | 24.547 | 5.0962 | 26.8287 | 13.949 | 23.8515 | 14.5069 | 8.7296 | 30.8001 | 15.254 | 528.9475
943 | 4.4329 | 46.0389 | 31.7358 | 6.9224 | 30.2152 | 46.8085 | 29.2767 | 10.4284 | 16.4514 | 15.9221 | 22.095 | 26.5128 | 51.8253 | 25.421 | 2.8861 | 24.7021 | 35.6417 | 5.9991 | 31.5459 | 13.9611 | 26.2962 | 11.6266 | 10.1811 | 48.5431 | 15.4344 | 590.904
944 | 5.5138 | 32.6718 | 29.7793 | 5.548 | 36.1742 | 42.5473 | 32.5891 | 11.7519 | 18.0694 | 10.9151 | 15.3232 | 21.84 | 41.959 | 25.7526 | 3.6413 | 24.8263 | 21.2957 | 5.8128 | 31.989 | 8.4005 | 24.6313 | 21.0667 | 7.9698 | 27.7221 | 20.4638 | 528.2539
945 | 6.31 | 46.6474 | 30.869 | 5.8864 | 35.6514 | 46.8673 | 16.494 | 10.9075 | 14.7955 | 15.1326 | 17.1229 | 27.9692 | 36.3833 | 17.5768 | 3.9929 | 16.5398 | 26.2976 | 3.1338 | 27.1508 | 11.2637 | 17.0729 | 21.759 | 7.4967 | 48.5111 | 17.868 | 529.6994
946 | 6.6975 | 38.0691 | 30.6679 | 6.6942 | 30.8575 | 46.2829 | 31.8256 | 5.9296 | 17.5691 | 11.7465 | 17.485 | 22.6418 | 37.7832 | 19.2116 | 3.0921 | 17.1789 | 38.6282 | 5.9744 | 30.5127 | 12.5591 | 24.1914 | 19.3777 | 10.7092 | 55.9441 | 16.916 | 558.5454
947 | 8.0313 | 42.1935 | 20.078 | 8.6057 | 35.7078 | 46.7258 | 37.8133 | 8.0112 | 17.559 | 12.3758 | 19.0572 | 28.1308 | 55.3031 | 21.0982 | 3.4341 | 21.3949 | 31.3573 | 5.8074 | 29.9003 | 10.9213 | 23.2225 | 17.1005 | 11.7023 | 47.7576 | 20.8322 | 584.1213
948 | 7.9979 | 40.4342 | 33.0314 | 7.0942 | 26.1377 | 44.0422 | 23.5483 | 6.8323 | 13.5847 | 15.7606 | 10.6342 | 13.55 | 38.207 | 21.4186 | 3.6244 | 25.2926 | 21.0413 | 4.7311 | 24.7632 | 7.5511 | 25.6254 | 21.9219 | 12.26 | 49.3348 | 19.7911 | 518.2103
949 | 7.0527 | 44.0913 | 25.287 | 6.4469 | 32.6988 | 48.2087 | 37.6031 | 11.0122 | 17.1281 | 14.7895 | 17.1106 | 27.7299 | 55.3364 | 20.2543 | 3.7117 | 21.8063 | 25.963 | 3.7583 | 27.4598 | 11.144 | 22.7819 | 20.6604 | 11.4749 | 34.781 | 20.605 | 568.8958
950 | 8.2485 | 42.14 | 28.7859 | 6.4511 | 35.8055 | 37.6842 | 17.4137 | 9.4026 | 16.2508 | 8.1609 | 19.1377 | 27.3788 | 53.9845 | 21.1125 | 2.4668 | 24.5941 | 21.5594 | 5.9011 | 25.8249 | 9.0468 | 18.5263 | 12.6822 | 9.4062 | 49.0341 | 17.8265 | 528.8248
951 | 7.9412 | 47.2485 | 21.6553 | 6.6972 | 31.1585 | 51.3856 | 27.9263 | 9.7636 | 18.9132 | 14.1145 | 20.2585 | 22.3958 | 38.8685 | 16.2593 | 3.2818 | 24.1389 | 29.8451 | 5.794 | 27.3688 | 9.341 | 20.7978 | 16.3546 | 11.5094 | 33.5146 | 17.1397 | 533.6717
952 | 5.8864 | 44.26 | 23.4276 | 5.9386 | 34.6599 | 41.6328 | 35.803 | 9.8764 | 19.0215 | 14.5268 | 15.0737 | 19.2622 | 50.7462 | 18.2828 | 3.563 | 24.7826 | 32.0879 | 4.4853 | 28.5426 | 8.7244 | 20.7272 | 19.5608 | 8.3082 | 54.7986 | 11.1563 | 555.1346
953 | 6.6866 | 30.6371 | 29.3878 | 8.644 | 23.4713 | 50.6942 | 27.617 | 11.3242 | 18.7975 | 10.2152 | 20.5325 | 15.9078 | 45.9396 | 19.8918 | 2.4964 | 19.75 | 27.1286 | 5.8011 | 28.1291 | 12.3229 | 24.972 | 19.6518 | 7.2628 | 47.8273 | 21.1953 | 536.284
954 | 6.6591 | 44.4121 | 17.8933 | 7.276 | 24.2883 | 50.3781 | 37.7885 | 9.1438 | 14.0596 | 13.096 | 20.2699 | 27.4489 | 41.9212 | 22.3782 | 3.5874 | 27.417 | 34.075 | 5.6496 | 19.8526 | 13.7953 | 21.1011 | 21.0611 | 9.3012 | 45.0808 | 18.3897 | 556.3238
955 | 4.222 | 34.767 | 32.8671 | 8.4533 | 23.6366 | 50.967 | 29.9802 | 7.9131 | 16.4042 | 16.625 | 18.8668 | 17.146 | 44.438 | 24.6668 | 3.7317 | 22.4043 | 33.2429 | 5.4432 | 26.2537 | 11.7605 | 19.8801 | 19.8912 | 11.6933 | 58.4215 | 20.687 | 564.3624
956 | 7.8154 | 28.3165 | 22.8445 | 5.6992 | 32.0656 | 40.1395 | 30.0614 | 9.7625 | 14.8113 | 12.2516 | 17.3382 | 18.1565 | 52.0984 | 25.3313 | 2.9302 | 27.4502 | 36.3948 | 4.838 | 29.4169 | 10.789 | 24.0217 | 13.7495 | 6.462 | 47.7213 | 18.2505 | 538.7162
957 | 8.0601 | 25.2019 | 21.4616 | 7.6218 | 28.8517 | 41.3904 | 27.6161 | 7.139 | 14.4682 | 14.7952 | 14.7945 | 22.8949 | 33.6084 | 21.7459 | 3.9564 | 21.4227 | 26.5977 | 5.6619 | 30.3604 | 10.0812 | 17.232 | 21.9276 | 12.0918 | 46.7942 | 20.2758 | 506.0514
958 | 6.7883 | 44.8456 | 20.9796 | 5.7452 | 35.9561 | 44.1352 | 36.6386 | 10.4562 | 19.2144 | 13.4366 | 14.5074 | 28.1826 | 35.7648 | 20.7897 | 3.1719 | 23.2278 | 33.0994 | 4.8249 | 31.0321 | 13.9822 | 21.5692 | 20.6144 | 9.144 | 52.7408 | 18.929 | 569.7759
959 | 6.3719 | 25.6115 | 26.8953 | 7.7095 | 32.8607 | 42.1871 | 35.8169 | 10.9344 | 13.0162 | 16.1013 | 21.5276 | 22.0321 | 39.6316 | 25.3045 | 2.3184 | 26.3861 | 32.3065 | 5.2999 | 29.8985 | 11.2245 | 23.1158 | 17.1106 | 11.6349 | 48.2011 | 17.2989 | 550.7957
960 | 6.8244 | 42.8535 | 14.5527 | 7.4226 | 26.3661 | 39.0985 | 23.3685 | 10.5733 | 17.1604 | 10.852 | 12.7384 | 25.5725 | 29.4384 | 25.4295 | 3.3676 | 15.3028 | 34.6595 | 5.6805 | 22.1656 | 8.0446 | 15.3855 | 20.067 | 10.8771 | 54.4558 | 12.2829 | 494.5397
961 | 8.3923 | 33.55 | 27.7373 | 8.0396 | 22.4821 | 42.5514 | 19.5411 | 8.4929 | 16.6742 | 12.9224 | 16.3723 | 20.2199 | 31.9528 | 20.2699 | 2.4126 | 26.4812 | 31.8575 | 5.8308 | 24.6698 | 10.8369 | 17.6591 | 20.5125 | 12.2343 | 46.688 | 19.6208 | 508.0018
962 | 6.9937 | 39.7311 | 30.6639 | 7.0871 | 31.1398 | 40.9967 | 29.2235 | 9.592 | 17.1133 | 15.3873 | 22.0932 | 19.4551 | 35.973 | 23.1491 | 3.319 | 24.8855 | 29.5473 | 4.8891 | 21.6457 | 11.495 | 19.7021 | 17.124 | 7.6172 | 34.7211 | 20.6238 | 524.169
963 | 4.6209 | 39.605 | 28.3858 | 7.8171 | 37.6628 | 53.7193 | 34.757 | 7.0988 | 16.7949 | 9.8965 | 17.5167 | 15.2965 | 32.3254 | 20.7602 | 3.0087 | 18.2536 | 27.6854 | 5.7225 | 32.42 | 8.7488 | 21.2145 | 21.9626 | 9.1083 | 49.9016 | 15.6784 | 539.9614
964 | 6.4814 | 35.3157 | 32.6883 | 4.2031 | 24.0448 | 50.2256 | 22.3387 | 9.3961 | 18.9183 | 14.3382 | 21.9127 | 25.8338 | 49.4217 | 23.9641 | 2.4351 | 20.7628 | 25.3501 | 5.5501 | 21.5401 | 11.4715 | 26.0974 | 19.039 | 10.736 | 53.2335 | 22.0259 | 557.3242
965 | 6.1357 | 35.1432 | 28.5527 | 8.6578 | 23.8468 | 53.0098 | 22.4458 | 8.9501 | 19.1299 | 12.4966 | 19.9999 | 18.9164 | 47.5058 | 18.5523 | 3.592 | 11.2919 | 38.735 | 5.4489 | 21.8395 | 13.3157 | 21.7607 | 19.9937 | 8.6999 | 54.8283 | 14.9208 | 537.7691
966 | 4.3131 | 45.6224 | 26.3795 | 7.6248 | 30.7322 | 41.8884 | 31.4727 | 9.956 | 18.6391 | 10.6895 | 19.0031 | 20.1433 | 44.93 | 24.8021 | 3.4358 | 22.6393 | 31.4666 | 5.3286 | 30.4077 | 13.2281 | 21.1102 | 19.3048 | 10.6944 | 44.2484 | 21.2897 | 559.3498
967 | 4.3176 | 43.3345 | 26.4985 | 7.1339 | 37.3999 | 42.9969 | 36.2801 | 11.2525 | 15.1626 | 15.0638 | 18.9391 | 28.5482 | 41.9323 | 23.1665 | 3.7898 | 24.4815 | 28.1915 | 5.2811 | 27.718 | 10.7116 | 22.6787 | 17.2922 | 10.5104 | 56.8509 | 13.9691 | 573.5012
968 | 7.7281 | 32.7878 | 18.9753 | 5.4303 | 31.3326 | 33.3094 | 27.3612 | 9.2654 | 18.4058 | 15.2049 | 21.6555 | 23.5657 | 48.951 | 23.0191 | 3.7014 | 22.3607 | 38.7379 | 5.0829 | 21.5807 | 11.2887 | 21.2397 | 12.2994 | 10.6618 | 40.402 | 21.975 | 526.3224
969 | 7.7609 | 32.9521 | 20.0994 | 6.74 | 35.1398 | 29.9917 | 32.3268 | 8.7656 | 19.0322 | 14.3141 | 11.0357 | 27.2106 | 45.1648 | 19.5147 | 2.6346 | 21.7345 | 28.5157 | 5.8441 | 20.8096 | 10.5267 | 19.802 | 20.7739 | 11.3909 | 54.1568 | 20.7267 | 526.964
970 | 6.9701 | 35.9267 | 17.002 | 7.1207 | 34.9908 | 48.3446 | 35.1049 | 8.4728 | 19.0383 | 13.2988 | 11.7468 | 22.6446 | 35.6615 | 21.0232 | 3.8038 | 22.1082 | 26.1344 | 4.498 | 30.0474 | 9.838 | 21.7203 | 12.7211 | 9.5952 | 23.7012 | 16.148 | 497.6615
971 | 5.5092 | 35.8754 | 20.9332 | 7.9092 | 25.6373 | 23.8464 | 26.248 | 7.8688 | 13.9734 | 13.7272 | 22.0786 | 27.1274 | 51.5293 | 23.1915 | 2.8128 | 20.5142 | 34.2486 | 5.2078 | 22.7466 | 13.8211 | 24.8683 | 18.7908 | 11.659 | 32.1087 | 15.2953 | 507.5279
972 | 5.6752 | 30.3777 | 21.6045 | 4.5928 | 19.2562 | 46.0991 | 34.0452 | 10.4796 | 12.6037 | 15.1015 | 17.3976 | 26.6065 | 49.6677 | 25.5931 | 3.2181 | 24.6747 | 21.8375 | 5.8947 | 23.4871 | 13.952 | 24.4223 | 20.0994 | 12.2544 | 46.9034 | 18.8092 | 534.6531
973 | 6.2383 | 47.9841 | 30.9736 | 7.231 | 34.4065 | 24.8047 | 31.0108 | 5.9897 | 18.7066 | 14.9325 | 17.6377 | 26.7704 | 44.2082 | 25.4854 | 3.4103 | 25.3858 | 33.3826 | 5.8759 | 27.5269 | 11.0459 | 15.6406 | 19.3562 | 10.8312 | 52.5966 | 15.6589 | 557.0904
974 | 7.0003 | 40.0071 | 29.4587 | 6.1833 | 36.3915 | 46.2523 | 27.8661 | 9.2173 | 12.3665 | 14.9484 | 22.316 | 16.7568 | 20.9908 | 21.3684 | 3.3889 | 23.6242 | 25.898 | 5.2291 | 31.2832 | 12.7476 | 18.9958 | 21.0328 | 8.1525 | 42.8543 | 17.4272 | 521.757
975 | 6.8474 | 38.8334 | 19.5816 | 8.5955 | 38.9368 | 40.2159 | 31.2302 | 10.324 | 16.104 | 12.5124 | 20.1897 | 20.6133 | 51.4849 | 24.9603 | 3.6477 | 14.8312 | 30.2484 | 5.5525 | 28.6593 | 8.813 | 21.4097 | 21.5058 | 10.3105 | 25.6922 | 18.7193 | 529.819
976 | 7.5921 | 37.3495 | 30.1477 | 8.337 | 24.1548 | 52.519 | 29.476 | 10.1592 | 19.4021 | 11.3167 | 17.2424 | 27.3322 | 37.0645 | 14.7643 | 3.0913 | 18.1872 | 22.2002 | 4.7422 | 32.932 | 13.7254 | 21.6789 | 17.6985 | 8.9667 | 43.8946 | 17.2216 | 531.1963
977 | 6.508 | 48.0175 | 29.3715 | 5.4894 | 29.5118 | 38.522 | 26.4857 | 7.6059 | 17.8551 | 14.5985 | 13.2694 | 25.2124 | 46.4996 | 20.3269 | 3.0346 | 24.1316 | 32.2501 | 5.471 | 26.2499 | 10.1031 | 16.4854 | 18.0199 | 9.6056 | 45.9884 | 15.5519 | 536.1653
978 | 7.4993 | 28.8535 | 29.4124 | 6.9 | 24.3943 | 47.2909 | 30.074 | 11.6879 | 15.6233 | 11.6808 | 19.3061 | 26.3606 | 52.4913 | 25.2923 | 3.9704 | 11.2394 | 28.4116 | 4.4874 | 22.8581 | 10.0729 | 21.6127 | 18.9532 | 10.8369 | 36.6424 | 15.4876 | 521.4392
979 | 6.8221 | 36.1513 | 31.1914 | 5.9431 | 18.1113 | 49.328 | 35.0779 | 6.8352 | 18.4775 | 11.9278 | 18.0394 | 27.8016 | 42.8241 | 20.4748 | 3.7787 | 26.2885 | 25.1111 | 5.8375 | 25.8778 | 12.1331 | 23.8578 | 15.6351 | 10.4711 | 49.7923 | 17.4908 | 545.2795
980 | 7.1977 | 43.2204 | 28.8007 | 7.909 | 36.9614 | 43.2669 | 27.9523 | 11.3606 | 18.7503 | 6.5847 | 19.6268 | 19.2085 | 31.8723 | 18.3463 | 3.0253 | 18.5206 | 33.9559 | 5.6509 | 23.5589 | 10.906 | 13.1039 | 21.2487 | 9.4129 | 27.7982 | 18.214 | 506.4533
981 | 7.9655 | 38.8612 | 28.6991 | 6.2737 | 21.5456 | 46.0492 | 31.6051 | 7.9753 | 14.2377 | 13.4081 | 19.4495 | 14.0041 | 36.4265 | 20.4992 | 3.3735 | 25.6626 | 35.3203 | 4.3973 | 25.5329 | 11.8824 | 14.3198 | 19.6982 | 7.3836 | 54.5376 | 18.8441 | 527.9521
982 | 7.8262 | 35.0528 | 14.9079 | 8.5028 | 38.1839 | 36.6749 | 37.5453 | 9.8995 | 18.8723 | 12.5385 | 14.6445 | 20.5448 | 31.8607 | 25.0486 | 3.8843 | 24.3875 | 30.7384 | 4.7845 | 17.5461 | 10.0751 | 25.4207 | 14.5143 | 7.3666 | 55.0139 | 20.4975 | 526.3316
983 | 6.4037 | 27.6009 | 22.5019 | 8.7157 | 26.1813 | 48.9021 | 37.6805 | 7.28 | 19.3101 | 14.0876 | 19.8342 | 27.5043 | 44.362 | 22.5965 | 3.2733 | 27.8986 | 38.8612 | 5.1484 | 28.6318 | 13.8061 | 24.0446 | 17.6804 | 11.9074 | 54.2069 | 20.0733 | 578.4931
984 | 7.3487 | 43.8311 | 25.5422 | 8.3644 | 21.2229 | 44.3666 | 32.1142 | 9.428 | 19.1561 | 12.331 | 20.3331 | 22.7658 | 41.0963 | 22.7263 | 3.9878 | 25.9861 | 32.2671 | 4.2478 | 32.2395 | 13.8865 | 16.1412 | 19.493 | 10.6454 | 48.6365 | 19.3082 | 557.4657
985 | 4.5538 | 47.2733 | 28.13 | 8.2686 | 36.9634 | 37.069 | 20.1562 | 4.9017 | 17.7145 | 14.7864 | 17.0141 | 24.2407 | 52.9178 | 21.4605 | 2.9521 | 22.7888 | 37.171 | 3.5267 | 29.7105 | 8.1274 | 18.7197 | 21.4604 | 10.0728 | 58.9356 | 17.2703 | 566.1854
986 | 7.6078 | 46.4292 | 30.662 | 8.1751 | 22.9107 | 36.7212 | 38.6782 | 9.9259 | 17.9441 | 15.2506 | 18.9896 | 27.3214 | 48.5377 | 24.3953 | 3.5032 | 25.1011 | 26.7439 | 5.3671 | 21.8901 | 12.8094 | 23.9469 | 12.8575 | 10.8349 | 50.637 | 20.7125 | 567.9525
987 | 7.9607 | 22.2654 | 19.5762 | 7.2383 | 38.556 | 37.982 | 20.3902 | 11.6229 | 13.4978 | 15.1388 | 13.9333 | 28.1085 | 46.0003 | 24.5177 | 3.7298 | 23.5995 | 23.2267 | 3.6168 | 29.3816 | 9.6167 | 21.593 | 18.1392 | 7.5283 | 45.9056 | 13.9064 | 507.0315
988 | 5.0462 | 32.5836 | 32.8233 | 8.6251 | 35.2251 | 48.0627 | 29.944 | 10.6091 | 19.9531 | 14.0317 | 21.265 | 26.9255 | 52.2845 | 20.1644 | 3.9824 | 25.1828 | 35.113 | 5.3891 | 32.6599 | 13.8429 | 25.5113 | 19.8956 | 10.9831 | 55.4396 | 13.8225 | 599.3657
989 | 7.6325 | 38.0286 | 26.6434 | 6.821 | 28.4543 | 52.3723 | 35.9805 | 10.1641 | 17.2431 | 11.5199 | 12.823 | 25.1653 | 50.6462 | 23.6357 | 2.347 | 22.2217 | 35.5234 | 5.6056 | 30.8011 | 13.7766 | 18.4933 | 15.8561 | 10.7713 | 38.4024 | 21.6736 | 562.6022
990 | 5.7293 | 33.1819 | 25.5549 | 7.3984 | 35.8994 | 43.837 | 38.3244 | 8.3674 | 16.5116 | 15.627 | 19.2804 | 27.9075 | 48.4401 | 25.9041 | 3.6348 | 25.411 | 22.4257 | 3.6428 | 21.4097 | 10.0648 | 18.8074 | 19.7023 | 10.3501 | 54.7682 | 20.187 | 562.3671
991 | 6.5674 | 40.2075 | 22.3978 | 7.6473 | 36.4647 | 36.0905 | 32.7049 | 9.3319 | 19.6285 | 12.38 | 15.4089 | 24.2148 | 48.1223 | 22.33 | 3.8939 | 24.2561 | 34.7888 | 4.3802 | 26.6097 | 10.7829 | 20.1448 | 16.3607 | 8.4439 | 52.7304 | 22.0285 | 557.9165
992 | 6.7648 | 37.7705 | 29.0892 | 8.5429 | 35.0574 | 37.6183 | 30.3134 | 10.9133 | 18.0523 | 12.3991 | 22.3236 | 27.4335 | 46.7221 | 20.6001 | 3.4711 | 15.0864 | 33.1704 | 5.276 | 25.2981 | 8.1948 | 23.5519 | 21.2576 | 9.4279 | 52.7304 | 11.5272 | 552.5921
993 | 6.9436 | 44.2119 | 28.1188 | 8.7736 | 31.3222 | 27.4466 | 29.9754 | 7.2768 | 17.2643 | 15.0932 | 22.2077 | 25.3031 | 44.5477 | 21.2582 | 3.9424 | 24.9203 | 36.0062 | 4.796 | 31.0093 | 12.4359 | 24.2255 | 19.6772 | 11.0485 | 54.8971 | 20.1844 | 572.8861
994 | 7.9102 | 42.4142 | 25.3151 | 7.2695 | 30.8988 | 33.2453 | 36.5001 | 9.1363 | 18.7841 | 15.5098 | 12.8744 | 24.6744 | 38.6506 | 13.6856 | 3.0803 | 21.6891 | 38.1676 | 4.3414 | 32.4106 | 9.4518 | 22.0893 | 21.636 | 11.4941 | 51.804 | 20.3157 | 553.3481
995 | 6.634 | 42.3321 | 33.0254 | 6.6407 | 31.4166 | 42.8454 | 32.1286 | 7.0609 | 16.1951 | 9.2509 | 19.787 | 26.3595 | 47.135 | 25.9331 | 3.8229 | 18.46 | 34.7336 | 3.7146 | 32.2975 | 13.4375 | 23.4914 | 15.6984 | 11.7703 | 39.3226 | 20.7133 | 564.2063
996 | 7.6134 | 37.9841 | 25.1216 | 5.6104 | 31.4242 | 32.9671 | 19.1419 | 11.2636 | 13.1663 | 11.8663 | 18.1959 | 28.5645 | 46.7504 | 24.1334 | 3.2284 | 25.3588 | 37.7436 | 5.9508 | 30.9018 | 11.2274 | 14.3816 | 19.437 | 11.615 | 50.2102 | 19.0316 | 542.8896
997 | 7.9748 | 41.1987 | 32.3178 | 6.1426 | 30.8798 | 49.3487 | 29.7828 | 11.7382 | 19.856 | 9.3558 | 15.9919 | 20.6964 | 34.7406 | 22.2637 | 3.7239 | 16.3366 | 31.7069 | 4.9441 | 29.7937 | 13.5146 | 16.4823 | 15.106 | 11.6491 | 40.8533 | 20.9391 | 537.3374
998 | 7.9984 | 29.6748 | 29.0849 | 6.2664 | 31.507 | 49.0377 | 36.4937 | 10.4944 | 10.3939 | 15.8102 | 19.9994 | 21.0575 | 40.8547 | 15.6876 | 2.3446 | 21.1096 | 37.2868 | 4.4252 | 27.665 | 13.5766 | 15.2693 | 20.4542 | 11.5574 | 54.5199 | 10.1024 | 542.6717
999 | 4.1516 | 48.6981 | 27.6023 | 8.3262 | 24.2152 | 53.2112 | 37.752 | 5.5229 | 16.6731 | 14.5651 | 14.3332 | 26.5732 | 47.1237 | 19.2375 | 2.5422 | 26.4022 | 32.1252 | 4.6519 | 21.1269 | 13.7019 | 21.948 | 15.0248 | 6.6155 | 33.5361 | 17.7979 | 543.458
1000 | 6.2085 | 46.277 | 19.6171 | 7.8496 | 34.2473 | 39.4141 | 29.8032 | 9.1602 | 17.4649 | 13.2515 | 19.6899 | 23.9453 | 44.1964 | 25.6368 | 3.3854 | 19.6847 | 34.4979 | 4.2737 | 18.0348 | 11.7141 | 25.9178 | 14.0245 | 12.0992 | 48.9294 | 18.1188 | 547.4419

## Distribution Curves
Parameter | Value |  | Triangle | PERT | Beta 50% | Beta 80%
Min | 5 |  | 11.9167 | 10.0833 | 9.6852 | 12.5943
Likely | 8.25
Max | 22.5
Uncertainty | High+
Alpha | 1.8647 | 1.7429 | Col C is PERT alpha
Beta | 4.5549 | 4.2571 | Col C is PERT beta
Index | Range | Beta C | Beta P | Triangle C | Triangle P | PERT C | PERT P
0% | 5 | 0 | 0 | 0 | 0 | 0 | 0
1% | 5.175 | 0.0020417 | 0.021484 | 0.00053846 | 0.0061538 | 0.0028721 | 0.028263
2% | 5.35 | 0.0072646 | 0.037736 | 0.0021538 | 0.012308 | 0.0094148 | 0.045759
3% | 5.525 | 0.015116 | 0.051665 | 0.0048462 | 0.018462 | 0.018691 | 0.059811
4% | 5.7 | 0.025247 | 0.063861 | 0.0086154 | 0.024615 | 0.030218 | 0.071603
5% | 5.875 | 0.037383 | 0.074623 | 0.013462 | 0.030769 | 0.043652 | 0.081679
6% | 6.05 | 0.051292 | 0.084141 | 0.019385 | 0.036923 | 0.058724 | 0.090357
7% | 6.225 | 0.066768 | 0.092552 | 0.026385 | 0.043077 | 0.075208 | 0.097851
8% | 6.4 | 0.083627 | 0.099964 | 0.034462 | 0.049231 | 0.092912 | 0.10432
9% | 6.575 | 0.1017 | 0.10646 | 0.043615 | 0.055385 | 0.11167 | 0.10987
10% | 6.75 | 0.12084 | 0.11213 | 0.053846 | 0.061538 | 0.13132 | 0.11462
11% | 6.925 | 0.1409 | 0.11702 | 0.065154 | 0.067692 | 0.15174 | 0.11863
12% | 7.1 | 0.16176 | 0.1212 | 0.077538 | 0.073846 | 0.1728 | 0.12198
13% | 7.275 | 0.18328 | 0.12471 | 0.091 | 0.08 | 0.1944 | 0.12472
14% | 7.45 | 0.20537 | 0.12761 | 0.10554 | 0.086154 | 0.21642 | 0.12691
15% | 7.625 | 0.22791 | 0.12994 | 0.12115 | 0.092308 | 0.23879 | 0.12859
16% | 7.8 | 0.25082 | 0.13174 | 0.13785 | 0.098462 | 0.2614 | 0.1298
17% | 7.975 | 0.27399 | 0.13304 | 0.15562 | 0.10462 | 0.28419 | 0.13059
18% | 8.15 | 0.29735 | 0.13389 | 0.17446 | 0.11077 | 0.30709 | 0.13098
19% | 8.325 | 0.32083 | 0.13431 | 0.19426 | 0.11368 | 0.33001 | 0.131
20% | 8.5 | 0.34434 | 0.13433 | 0.21404 | 0.11228 | 0.35292 | 0.1307
21% | 8.675 | 0.36782 | 0.13399 | 0.23356 | 0.11088 | 0.37574 | 0.13008
22% | 8.85 | 0.39122 | 0.13332 | 0.25284 | 0.10947 | 0.39843 | 0.12918
23% | 9.025 | 0.41447 | 0.13233 | 0.27188 | 0.10807 | 0.42094 | 0.12802
24% | 9.2 | 0.43752 | 0.13106 | 0.29067 | 0.10667 | 0.44322 | 0.12663
25% | 9.375 | 0.46032 | 0.12952 | 0.30921 | 0.10526 | 0.46524 | 0.12501
26% | 9.55 | 0.48284 | 0.12775 | 0.32751 | 0.10386 | 0.48697 | 0.1232
27% | 9.725 | 0.50502 | 0.12575 | 0.34556 | 0.10246 | 0.50836 | 0.12121
28% | 9.9 | 0.52684 | 0.12356 | 0.36337 | 0.10105 | 0.52938 | 0.11906
29% | 10.075 | 0.54826 | 0.12119 | 0.38093 | 0.099649 | 0.55002 | 0.11677
30% | 10.25 | 0.56925 | 0.11866 | 0.39825 | 0.098246 | 0.57024 | 0.11434
31% | 10.425 | 0.58978 | 0.11599 | 0.41532 | 0.096842 | 0.59003 | 0.11179
32% | 10.6 | 0.60983 | 0.11319 | 0.43214 | 0.095439 | 0.60936 | 0.10914
33% | 10.775 | 0.62939 | 0.11027 | 0.44872 | 0.094035 | 0.62823 | 0.10641
34% | 10.95 | 0.64842 | 0.10727 | 0.46505 | 0.092632 | 0.6466 | 0.10359
35% | 11.125 | 0.66693 | 0.10418 | 0.48114 | 0.091228 | 0.66448 | 0.10071
36% | 11.3 | 0.68488 | 0.10102 | 0.49698 | 0.089825 | 0.68185 | 0.097779
37% | 11.475 | 0.70228 | 0.097815 | 0.51258 | 0.088421 | 0.6987 | 0.0948
38% | 11.65 | 0.71912 | 0.094562 | 0.52793 | 0.087018 | 0.71503 | 0.091786
39% | 11.825 | 0.73538 | 0.091278 | 0.54304 | 0.085614 | 0.73082 | 0.088748
40% | 12 | 0.75106 | 0.087975 | 0.55789 | 0.084211 | 0.74609 | 0.085692
41% | 12.175 | 0.76617 | 0.084661 | 0.57251 | 0.082807 | 0.76082 | 0.082629
42% | 12.35 | 0.78069 | 0.081347 | 0.58688 | 0.081404 | 0.77501 | 0.079566
43% | 12.525 | 0.79464 | 0.078042 | 0.601 | 0.08 | 0.78866 | 0.07651
44% | 12.7 | 0.80801 | 0.074754 | 0.61488 | 0.078596 | 0.80179 | 0.073468
45% | 12.875 | 0.8208 | 0.071492 | 0.62851 | 0.077193 | 0.81438 | 0.070446
46% | 13.05 | 0.83303 | 0.068263 | 0.64189 | 0.075789 | 0.82644 | 0.067452
47% | 13.225 | 0.8447 | 0.065073 | 0.65504 | 0.074386 | 0.83799 | 0.06449
48% | 13.4 | 0.85581 | 0.06193 | 0.66793 | 0.072982 | 0.84902 | 0.061566
49% | 13.575 | 0.86638 | 0.058839 | 0.68058 | 0.071579 | 0.85954 | 0.058684
50% | 13.75 | 0.87641 | 0.055806 | 0.69298 | 0.070175 | 0.86956 | 0.055851
51% | 13.925 | 0.88591 | 0.052836 | 0.70514 | 0.068772 | 0.87909 | 0.053069
52% | 14.1 | 0.8949 | 0.049933 | 0.71705 | 0.067368 | 0.88814 | 0.050343
53% | 14.275 | 0.90339 | 0.047102 | 0.72872 | 0.065965 | 0.89671 | 0.047676
54% | 14.45 | 0.91139 | 0.044346 | 0.74014 | 0.064561 | 0.90483 | 0.045072
55% | 14.625 | 0.91892 | 0.041669 | 0.75132 | 0.063158 | 0.91249 | 0.042534
56% | 14.8 | 0.92598 | 0.039074 | 0.76225 | 0.061754 | 0.91972 | 0.040065
57% | 14.975 | 0.9326 | 0.036563 | 0.77293 | 0.060351 | 0.92652 | 0.037666
58% | 15.15 | 0.93879 | 0.034139 | 0.78337 | 0.058947 | 0.93291 | 0.035341
59% | 15.325 | 0.94455 | 0.031803 | 0.79356 | 0.057544 | 0.93889 | 0.033091
60% | 15.5 | 0.94992 | 0.029556 | 0.80351 | 0.05614 | 0.94449 | 0.030917
61% | 15.675 | 0.9549 | 0.027401 | 0.81321 | 0.054737 | 0.94972 | 0.028822
62% | 15.85 | 0.95952 | 0.025338 | 0.82267 | 0.053333 | 0.95458 | 0.026805
63% | 16.025 | 0.96378 | 0.023368 | 0.83188 | 0.05193 | 0.9591 | 0.024869
64% | 16.2 | 0.9677 | 0.02149 | 0.84084 | 0.050526 | 0.96329 | 0.023013
65% | 16.375 | 0.97131 | 0.019704 | 0.84956 | 0.049123 | 0.96716 | 0.021239
66% | 16.55 | 0.9746 | 0.018011 | 0.85804 | 0.047719 | 0.97073 | 0.019546
67% | 16.725 | 0.97761 | 0.01641 | 0.86626 | 0.046316 | 0.97401 | 0.017934
68% | 16.9 | 0.98035 | 0.014899 | 0.87425 | 0.044912 | 0.97701 | 0.016403
69% | 17.075 | 0.98283 | 0.013478 | 0.88198 | 0.043509 | 0.97976 | 0.014953
70% | 17.25 | 0.98508 | 0.012145 | 0.88947 | 0.042105 | 0.98225 | 0.013583
71% | 17.425 | 0.98709 | 0.010899 | 0.89672 | 0.040702 | 0.98451 | 0.012292
72% | 17.6 | 0.98889 | 0.009738 | 0.90372 | 0.039298 | 0.98656 | 0.011079
73% | 17.775 | 0.9905 | 0.0086597 | 0.91047 | 0.037895 | 0.9884 | 0.0099423
74% | 17.95 | 0.99193 | 0.0076621 | 0.91698 | 0.036491 | 0.99004 | 0.0088816
75% | 18.125 | 0.99319 | 0.0067428 | 0.92325 | 0.035088 | 0.99151 | 0.0078948
76% | 18.3 | 0.99429 | 0.0058991 | 0.92926 | 0.033684 | 0.99281 | 0.0069802
77% | 18.475 | 0.99526 | 0.0051285 | 0.93504 | 0.032281 | 0.99396 | 0.006136
78% | 18.65 | 0.99609 | 0.004428 | 0.94056 | 0.030877 | 0.99496 | 0.00536
79% | 18.825 | 0.99681 | 0.0037947 | 0.94584 | 0.029474 | 0.99584 | 0.0046502
80% | 19 | 0.99743 | 0.0032253 | 0.95088 | 0.02807 | 0.99659 | 0.0040042
81% | 19.175 | 0.99794 | 0.0027168 | 0.95567 | 0.026667 | 0.99724 | 0.0034195
82% | 19.35 | 0.99838 | 0.0022656 | 0.96021 | 0.025263 | 0.99779 | 0.0028936
83% | 19.525 | 0.99874 | 0.0018685 | 0.96451 | 0.02386 | 0.99826 | 0.0024238
84% | 19.7 | 0.99904 | 0.0015219 | 0.96856 | 0.022456 | 0.99864 | 0.0020073
85% | 19.875 | 0.99928 | 0.0012224 | 0.97237 | 0.021053 | 0.99896 | 0.0016411
86% | 20.05 | 0.99947 | 0.00096623 | 0.97593 | 0.019649 | 0.99922 | 0.0013222
87% | 20.225 | 0.99962 | 0.00074991 | 0.97925 | 0.018246 | 0.99943 | 0.0010476
88% | 20.4 | 0.99973 | 0.00056981 | 0.98232 | 0.016842 | 0.99959 | 0.00081408
89% | 20.575 | 0.99982 | 0.00042232 | 0.98514 | 0.015439 | 0.99972 | 0.00061835
90% | 20.75 | 0.99988 | 0.00030387 | 0.98772 | 0.014035 | 0.99981 | 0.0004571
91% | 20.925 | 0.99993 | 0.00021095 | 0.99005 | 0.012632 | 0.99988 | 0.00032699
92% | 21.1 | 0.99996 | 0.0001401 | 0.99214 | 0.011228 | 0.99993 | 0.00022462
93% | 21.275 | 0.99998 | 8.7973e-05 | 0.99398 | 0.0098246 | 0.99996 | 0.00014657
94% | 21.45 | 0.99999 | 5.1331e-05 | 0.99558 | 0.0084211 | 0.99998 | 8.9423e-05
95% | 21.625 | 0.99999 | 2.7094e-05 | 0.99693 | 0.0070175 | 0.99999 | 4.9769e-05
96% | 21.8 | 1 | 1.2368e-05 | 0.99804 | 0.005614 | 1 | 2.4249e-05
97% | 21.975 | 1 | 4.4881e-06 | 0.99889 | 0.0042105 | 1 | 9.5739e-06
98% | 22.15 | 1 | 1.0714e-06 | 0.99951 | 0.002807 | 1 | 2.5754e-06
99% | 22.325 | 1 | 9.1967e-08 | 0.99988 | 0.0014035 | 1 | 2.7141e-07
100% | 22.5 | 1 | 0 | 1 | 0 | 1 | 0